## Inventory Instructions
CART- Deliverable Inventory Instructions
The CART Master Deliverable Inventory is a document to be used by each workstream to document all year 1 deliverables and associated milestones.
The expectation is that all items defined as a Year 1 priority will have at least one concrete year 1 deliverable associated with them. Each deliverable is expected to have between 1-5 major milestones associated with achieving the deliverable. The number of milestones will vary based on the nature of the deliverables.
To use the Deliverable Inventory and add a deliverable please do the following:
1. Select the tab associated with your workstream
2. In column A, select the Priority from the pull down menu that the deliverable you are creating is associated with
3. Enter a description for the new deliverable in Column B, next to the priority you have just selected
4. In Column C, please identify a proposed owner for the deliverable if it is currently known
5. In Column D, please enter the proposed delivery date (if currently known)
6. In column E, please identify if the deliverable has any IT dependency (if currently known)
7. In columns F- O, please enter any associated milestones (and known dates) with the deliverable
8. Columns P-S are intended to be completed later this week, but can be completed now if data is known
9. To enter the next deliverable on the following line, repeats steps 1-8.
Please note that you can have more than one deliverable associated with a priority. To do this, just select the priority in column A for as many deliverables that are associated with the priority. For example, if you have 5 deliverables associated with your first priority on your list, the first 5 lines in your inventory would have the same priority selected with a different deliverable on each line.

## Risk Transformation
| Yes | [12 empty] | High
| No | [12 empty] | Medium
Low
Priority | Deliverable | Owner | Proposed Date | IT Dependency (Y/N) | Milestone 1 | Proposed Date2 | Milestone 2 (If applicable) | Proposed Date3 | Milestone 3 (If applicable) | Proposed Date4 | Milestone 4 (If applicable) | Proposed Date5 | Milestone 5 (If applicable) | Proposed Date6 | Level of Effort/Complexity | Delivery Risk | Resources Required | Comments | Finance Transformation
Re-design RAS for SHUSA enterprise | SHUSA Board-level Risk Appetite Statement −Risk appetite statements for most material risks (considering most recent enterprise strategy) −List of metrics and calibrated limits that define quantifiable RA statements -Draft the SHUSA RAS reporting process, breach escalation process and breach penalty mechanism | Edward Smith | 2015-08-10 | Yes | Draft RAS |  | Final RAS |  | Draft process |  | Final process |  |  |  | High | Low | Yes
Re-design RAS for SHUSA enterprise | Delivery of RAS training to Board (materials drafted in Board Risk Committee training project), includes: - Overview of new RAS structure and metrics - Board roles and responsibilities with respect to RAS | Edward Smith | 2015-08-31 | No | Delivery of training | [9 empty] | Medium | Low | Yes
Re-design RAS for SHUSA enterprise | Board-approved SHUSA RAS and reporting process | Edward Smith | 2015-09-07 | No | Board approval | [9 empty] | Low | Low | Yes
Re-design RAS for SHUSA enterprise | Delivery of Board-level RAS communication and socialization materials to the Enterprise e.g. emails, townhalls | Edward Smith | 2015-09-29 | No | Draft of materials |  | Final materials and delivery of communication | [7 empty] | Medium | Low | Yes
Re-design RAS for SHUSA enterprise | Defined RAS business and data requirements, communicated to T&O | Edward Smith | 2015-09-29 | Yes | Draft BRD |  | Final BRD and communication to T&O | [7 empty] | Low | Low | No
Cascade RAS to priority subsidiaries | Define approach to cascading SHUSA level Risk Appetite Statement to subsidiaries and levels below | Edward Smith | 2015-08-24 | No | Draft approach |  | Final approach | [7 empty] | Medium | Low | Yes
Cascade RAS to priority subsidiaries | Risk Appetite Statements for priority subsidiaries i.e. SBNA and SCUSA (aligned with overall SHUSA RAS) −Risk appetite statements for most material risks −List of metrics and calibrated limits | Edward Smith | 2015-10-05 | Yes | Draft RAS for priority subs and list of metrics |  | Input from subs |  | Final RAS for priority subs and list of metrics | [5 empty] | High | Low | Yes
Cascade RAS to priority subsidiaries | RAS escalation and reporting process (cascaded version), including definition of consequences for RAS limit breaches and more detailed RAS limits | Edward Smith | 2015-09-21 | No | Draft process |  | Final process | [7 empty] | Medium | Low | Yes
Cascade RAS to priority subsidiaries | Board-approved RAS for priority subsidiaries | Edward Smith | 2015-10-05 | No | Board approval | [9 empty] | Low | Low | Yes
Board Risk Committee Training | Development of risk training curriculum and schedule for the Board Risk committee: −Training materials [for first 2 sessions, including RAS training] −Detailed risk training objectives | John Hennessey | 2015-07-27 | No | Draft of training materials, including training schedule |  | Final training materials, including training schedule |  | Delivery of two training sessions | [5 empty] | Medium | Low | Yes
Formalize engagement model between SHUSA and Parent Group | Established governance and coordination mechanisms within Group (i.e. engagement model in terms of linkage between SHUSA and Parent Group committees, etc.) | John Hennessey | 2015-07-27 | No | Key stakeholder engagement |  | Draft governance and coordination mechanisms |  | Final governance and coordination mechanisms | [5 empty] | High | Medium | Yes
Formalize engagement model between SHUSA and Parent Group | Board-approved governance and coordination mechanisms | John Hennessey | 2015-08-10 | No | Board approval | [9 empty] | Low | Low | Yes
Formalize engagement model between SHUSA and Parent Group | Group-approved governance and coordination mechanisms | John Hennessey | TBD | No | Group approval | [9 empty] | Medium | Medium | Yes
Strengthen SHUSA Board and Management Committee guidance | Diagnostic of Risk Management Committee oversight effectiveness over SHUSA subsidiaries | John Hennessey | 2015-06-29 | No | Draft of diagnostic materials |  | Final materials and delivery of diagnostic | [7 empty] | Medium | Low | Yes
Strengthen SHUSA Board and Management Committee guidance | Updated committee composition, mandates, and charters for priority committees (Board level and Management Committees [Level 1]): −Review enterprise committee suite/structure −Identify and execute necessary changes to high priority committee composition, mandates, processes, charters | John Hennessey | 2015-07-27 | No | Draft of committee composition, mandates, and charters |  | Final committee composition, mandates, and charters | [7 empty] | High | Medium | Yes
Strengthen SHUSA Board and Management Committee guidance | Board-approved committee compositions, mandates and charters (Board level and Management Committees (Level 1)) | John Hennessey | 2015-08-10 | No | Board approval | [9 empty] | Low | Low | Yes
Strengthen SHUSA Board and Management Committee guidance | Updated committee composition, mandates, and charters for remaining committees (Management Committees [Level 2], Sub-Committees) | John Hennessey | 2015-09-07 | No | Draft of committee composition, mandates, and charters |  | Final committee composition, mandates, and charters | [7 empty] | High | Medium | Yes
Strengthen SHUSA Board and Management Committee guidance | Board-approved committee compositions, mandates and charters (Management Committees (Level 2), Sub-Committees) | John Hennessey | 2015-10-05 | No | Board approval | [9 empty] | Low | Low | Yes
Recruit priority staff | Recruitment of senior Risk leadership staff where gaps exist | Kerrie Maitland | 2015-08-24 | No | Identification of open positions |  | Engagement with HR |  | Recruitment rounds |  | Hiring of positions |  |  |  | High | High | No
Recruit priority staff | Recruitment of other priority staff where gaps exist e.g. model validators | Kerrie Maitland | 2015-08-24 | No | Identification of open positions |  | Engagement with HR |  | Recruitment rounds |  | Hiring of positions |  |  |  | High | High | No
Design risk management organizational structure in accordance with 3LoD principles | Articulation and formalization of 3LOD principles | John Hennessy | 2015-06-15 | No | Draft 3LoD principles |  | Final 3LoD principles | [7 empty] | Low | Low | Yes
Design risk management organizational structure in accordance with 3LoD principles | Definition and formalization of reporting lines at the C-Suite: - Articulation of reporting lines and implications e.g. centralized risk function, 'double-hatting' of roles | John Hennessy | 2015-07-13 | No | Draft reporting lines |  | Key stakeholder engagement |  | Final (formalization of) reporting lines | [5 empty] | Low | Low | Yes
Design risk management organizational structure in accordance with 3LoD principles | Board-approved C-Suite reporting lines | John Hennessy | 2015-08-10 | No | Board approval | [9 empty] | Medium | Low | Yes
Design risk management organizational structure in accordance with 3LoD principles | Detailed operating model design aligned with 3LoD principles: -Future risk operating model design for SHUSA / subsidiaries -Design of organizational structure for each Risk type in each subsidiary (aligned with 3LoD) -Designation of roles and responsibilities and senior job descriptions | John Hennessy | 2015-07-27 | No | Draft of operating model |  | Final operating model | [7 empty] | High | Medium | Yes
Design risk management organizational structure in accordance with 3LoD principles | Headcount analysis aligned with updated operating model design: -Includes determination of FTE at all levels of the enterprise (across all 3 LoD) -Skills / staffing assessment to identify additional staffing needs or changes | John Hennessy | 2015-09-21 | No | Draft headcount |  | Delivery of skills / staffing assessment |  | Hiring / redeployment strategy | [5 empty] | High | Medium | Yes
Implementation of risk management organizational structure in accordance with 3LoD principles | Roll-out of new operating model, in terms of: -Communications -Development and delivery of materials to convey organizational changes to enterprise -Enterprise-wide training and development of job descriptions (link to execution of Talent Management Strategy) with explicit focus on 3LOD -Embedded structure with all roles and responsibilities filled | John Hennessy | TBD | No | Draft of communication and training materials for enterprise-wide communication |  | Delivery of final communication and training materials for enterprise-wide communication |  | Development of job descriptions |  | Delivery of enterprise-wide training |  |  |  | High | Medium | Yes
Improve effectiveness of policies and procedures | Frameworks designed and approved across all risk types (continuation of in-flight project for following frameworks: ERM, Credit Risk, Market / Liquidity Risk, Operational Risk) | John Hennessy | 2015-06-29 | No | Validation of updated frameworks | [9 empty] | Low | Low | No
Improve effectiveness of policies and procedures | Board-approved frameworks | John Hennessy | 2015-07-13 | No | Board approval | [9 empty] | Low | Low | No
Improve effectiveness of policies and procedures | Assessment of existing enterprise-wide policies and procedures, and prioritization of improvement actions, including: -Ongoing work regarding policy templates, administration and standards -Coordination with other Management Committees to determine ownership of and “hand-off” points for enhancements -Review of policy attestation process and linkage to Senior Management incentives -Ensure standardization across all policies/procedures | John Hennessy | TBD | No | Draft of assessment |  | Delivery of assessment |  | Prioritization of enhancements |  | Final plan for enhancements, given stakeholder input |  | Standardization of all policies / procedures |  | Medium | Low | No
Enhance risk identification and assessment process | Completed definition of the risk ID and assessment process and execution: −Process maps −Tools/templates | Edward Smith / Diane Allaire | 2015-06-15 | Yes | Draft definition of risk ID/assessment process and plan for execution |  | Final definition of risk ID/assessment process and plan for execution |  | Communication to key stakeholders | [5 empty] | Low | Medium | No
Enhance risk identification and assessment process | Board-approved risk ID and assessment program | Edward Smith / Diane Allaire | 2015-07-13 | No | Board approval | [9 empty] | Low | Low | No
Enhance risk identification and assessment process | Register of risks, encompassing both modeled and non-modeled risks across all relevant legal entities / BUs: −Informed by existing Operational Risk, Compliance, and Audit frameworks as possible | Edward Smith / Diane Allaire | 2015-08-10 | Yes | Conduct bottom-up risk identification |  | Aggregate, review & challenge |  | Conduct top-down risk identification |  | Draft of risk register |  | Final risk register |  | High | High | Yes
Enhance risk identification and assessment process | Policy/procedure for Risk Identification and Assessment cycle (specifying frequency, stakeholders, duration, approvals, management / mitigation actions, updates to RAS, etc.) | Edward Smith / Diane Allaire | 2015-07-27 | No | Draft policy and procedures for risk ID and assessment cycle |  | Final policy and procedures for risk ID and assessment cycle |  | Communication of policies/procedures to key stakeholders | [5 empty] | Medium | Low | No
Enhance risk identification and assessment process | Defined business and data requirements for enhanced risk identification and assessment process | Edward Smith / Diane Allaire | 2015-09-07 | Yes | Draft BRD |  | Final BRD and communication to T&O | [7 empty] | Low | Medium | No
Conduct high level credit risk review and deliver quick wins | High level review and revision of wholesale credit process limits / controls and delegation of authority (potential quick win) at SHUSA and SBNA | TBD | 2015-10-05 | No | Proposed recommendations |  | Approved recommendations |  | Updated Credit Policy | [5 empty] | Medium | Medium | Yes
Create IRR and Liquidity Risk framework | High level review of key IRR and liquidity risk assumptions and parameters, including: governance, metrics and reporting to manage liquidity and IRR risk | TBD | 2015-09-21 | No | Draft framework |  | Final framework | [7 empty] | Medium | Medium | Yes
Conduct liquidity risk gap analysis | Definition of liquidity risk capabilities across Treasury, Risk, including areas identified in “tasks” and evaluation of current state against capabilities and remediation plan | TBD | 2015-10-05 | No | Definition of liquidity risk capabilities |  | Current state vs. capabilities |  | Remediation plan | [5 empty] | Medium | Medium | Yes
Conduct Reputational / Strategic Risk Management Framework Review | Review of the Reputational/Strategic Risk Management Framework: −Review existing reputational and strategic risk lists, determine link with other major risk types (liquidity risk, op risk, etc.) −Conduct structured workshops to narrow down top risks −Translate top risk triggers into scenarios and leverage expert opinion to assess impacts −Evaluate mitigating actions and implement necessary controls -Define business and data requirements and communicate to T&O | John Hennessey | 2015-09-12 | No | Initial review of risks |  | Scenario and impact analysis |  | Remediation plan |  | Business and data requirements |  |  |  | TBD | TBD | Yes
Conduct new Product / New Business process Review | Review of the New Product / New Business Framework (with Risk participation) - Review roles and responsibilities -Design tools to make process systematic (e.g. risk assessment templates) −Define decision authority mechanism -Define business and data requirements and communicate to T&O | TBD | 2015-09-12 | No | Initial review of framework |  | Process and associated tools |  | Documented decision authority |  | Business and data requirements |  |  |  | TBD | TBD | Yes
Enhance internal reporting | Risk reporting landscape, by audience and risk type −Determine different audiences of risk reporting −For each audience outline essential content and frequency of reporting | Edward Smith | 2015-07-27 | No | Risk reporting landscape outline | [9 empty] | Low | Low | Yes
Enhance internal reporting | Prototype reports and socialization of high priority reports to: −Board −Senior management (Management Committee Level 1) | Edward Smith | 2015-09-07 | No | Board prototype reports |  | Senior management prototype reports | [7 empty] | Low | Medium | Yes
Enhance internal reporting | Risk data requirements for reporting: −Based on desired reporting contents and frequency, define business requirements incl. both type and frequency of data −Prioritize business requirements based on report and metric materiality -Identify risk aggregation needs to support reporting | Edward Smith | 2015-09-21 | Yes | Risk reporting data requirements - Board |  | Risk reporting data requirements - Senior Management | [7 empty] | Medium | High | Yes
Enhance internal reporting | Reporting resourcing: −Identify reporting groups within SHUSA and subsidiaries −Define target organizational structure for reporting groups (e.g., central aggregation team at SHUSA level) −Define resource needs to support desired reporting, both in current and future state −Train and onboard resources for reporting | Edward Smith | 2015-09-21 | No | Target org structure for reporting groups |  | Definition of reporting resource requirements |  | Training for reporting resources | [5 empty] | Low | Medium | Yes
Update internal monitoring process | Risk IT, RDA and IT service performance dashboard | Edward Smith | 2016-05-10 | Yes | Outlined target performance dashboard |  | Business and data requirements |  | Roadmap / plan for implementation |  | Prototype performance dashboard |  | Implemented performance dashboard |  | High | High | Yes
Define initial business and data requirements | Coordination and aggregation of all business and data requirements, defined for key data-related risk measurement, management, and reporting activities, including: −Information needed and business purpose −Level of aggregation / granularity −Expected provisioning frequency −Expected turn-around times for data (e.g. provided within 10 days after month-end close) -Links to individual workstream initiatives to define business and data requirements | T&O | 2015-10-19 | Yes | Stakeholder engagement |  | Draft data requirements |  | Final data requirements | [5 empty] | High | High | No
Define initial business and data requirements | Prioritization of data requirements, both within and across individual business requirement documents −In line with overall risk-related CART prioritization | T&O | 2015-11-23 | Yes | Data prioritization criteria |  | List of prioritized data | [7 empty] | Medium | Medium | No
Review current systems architecture and identify improvements | Definition of target risk data management IT architecture | T&O | 2015-08-31 | Yes | Draft target state |  | Final target state | [7 empty] | Low |  | No
Review current systems architecture and identify improvements | Assessment of current systems architecture and identification of required enhancements to support data needs, incorporating: −Above business requirements −BCBS 239 compliance needs −Technology solutions consistent with defined architecture | T&O | 2015-10-27 | Yes | Current systems architecture |  | Remediation plan | [7 empty] | High | Medium | No
CART- Risk Transformation Deliverable Inventory
Expected By 5/15/15

## Data Sheet
Workstream | Element | Topic | Year 1 Requirement
Data & IT | Data Quality | Data Quality | Establish Key Data Elements (KDEs) for prioritized CCAR data (including models and schedules), including documenting data dictionary and lineage, measuring and remediating data quality, deploying data controls.
Data & IT | Data Quality | Data Quality | Implement a Data Quality Center of Excellence to improve the quality of the company’s data (SHUSA and all the related US entities) by centralizing the collection of data defects, analyzing and assigning the issues causing the defects, and ensuring remediation activities are completed.
Data & IT | Data Governance | Data Governance | Conduct a data industry maturity model assessment for SBNA, SCUSA and SHUSA to identify capability gaps that require further remediation.
Data & IT | Data Governance | Data Governance | Establish strict governance on KDEs to assess, ensure and report on compliance with data policies and standards.
Data & IT | Data Governance | Data Governance | Define a comprehensive data control framework, and apply it for critical CCAR and EPS / ELS related processes
Data & IT | Data Governance | Data Governance | Create the structure and organization of the CDO for SHUSA
Data & IT | Data Governance | Data Governance | Conduct data industry maturity model assessment for SHUSA, SBNA and SCUSA on an annual basis
Data & IT | Data Governance | Data Governance | Clearly define roles, responsibilities and ownership for data collection, quality, maintenance (Data Manager, Data Owner, Data Steward, DQ Admin, Tech Data Owner,……) as well as a list of Data Domains.
Data & IT | Data Governance | Data Governance | Organize data management roles along the three lines of defense model (Business, Chief Data Officer and Independent Audit)
Data & IT | Data Governance | Data Governance | Socialize data management program and implementation plan with key stakeholders.
Data & IT | Data Governance | Data Governance | Define domain scope and boundaries
Data & IT | Data Governance | Data Governance | Launch a SHUSA Data Governance Council attended by Data Manager, Data Owners, Data Stewards and CDO.
Data & IT | Data Governance | Data Governance | Assess and ensure compliance of SHSUA, SBNA and SCUSA practices against the Data Management Policy and Standards
Data & IT | Infosecurity | Infosecurity | IT Risk Assessment and Risk Reporting (CCAR, RCSA, ERM, MRP, OCC, HS, etc.)
Data & IT | Infosecurity | Infosecurity | Finding and Remediation Management Capability and Governance (including 2014 IT SOX Finding Remediations)
Data & IT | Infosecurity | Infosecurity | Governance: Policy, Standards, Roles and Responsibilities Development (EPAP, RTS)
Data & IT | Infosecurity | Infosecurity | Identity and Access Management Solution (SailPoint for Attestation, Access Request)
Data & IT | Infosecurity | Infosecurity | Data Flow Control from Upstream Feeders into Golden Sources and from Golden Sources to Downstream Reporting Systems
Model Development | Governance Tools | Governance Tools | Enterprise Model Policy
Model Development | Governance Tools | Governance Tools | Best Practices Library
Model Development | Governance Tools | Governance Tools | LOB Modeling Frameworks and Procedures
Model Development | Governance Tools | Governance Tools | Templates, checklists, and other standardized (but adaptable) controls
Model Development | Professional Development | Professional Development | Standardized skills assessments for senior analysts and managers
Model Development | Professional Development | Professional Development | Comprehensive and standardized job descriptions
Model Development | Professional Development | Professional Development | Professional Qualifications Standards (PQS)
Model Development | Professional Development | Professional Development | Classroom and online training
Model Development | Professional Development | Professional Development | Establish Model Forum
Model Development | CCAR | CCAR | FRB letter gap analysis
Model Development | CCAR | CCAR | Inventory of models needed for CCAR 2016
Model Development | CCAR | CCAR | Construct at least one set of models with dual CCAR and business purposes
Model Development | CCAR | CCAR | Demonstrate substantial improvement on Model Development
Operational Risk | Risk Appetite | SHUSA Operational Risk Tolerance Statement | Simplify SHUSA Operational Risk Tolerance Statement Limits
Operational Risk | Risk Appetite | SHUSA Operational Risk Tolerance Statement | Align with Capital Measures described in the Basel Consultative document (Total Potential OR Losses as a % of Gross Income, Single OR Loss Event > $10MM)
Operational Risk | Governance & Organization | Establish a SHUSA Operational Risk Management Framework | Develop ORM principles, 3 LoD roles and responsibilities, SHUSA ORM organizational structure, ORM ERM methodology
Operational Risk | Governance & Organization | Enhance Ops Risk Policies | Perform gap analysis of policy inventory in line with regulatory guidance supporting SHUSA policy requirements
Operational Risk | Governance & Organization | Enhance Ops Risk Policies | Update SHUSA enterprise Ops Risk policies as required
Operational Risk | Governance & Organization | Training & Awareness | Gap analysis to identify training needs for staff of SHUSA and Subsidiaries with respect to SHUSA enterprise Ops Risk policies and standards
Operational Risk | Governance & Organization | Establish Ops Risk Operating Model | Determine OR organizational structure between SHUSA and Subsidiaries
Operational Risk | Governance & Organization | Establish Ops Risk Operating Model | Determine and select short-term / medium-term resource requirements (internal and external) to deliver Year 1/2/3 priorities
Operational Risk | Governance & Organization | Establish Ops Risk Operating Model | Recruit and onboard necessary talent
Operational Risk | Risk Measurement | Risk Identification and Assessment Design & Implementation | Establish the process to enforce and improve the identification and management of open issue and remediation efforts
Operational Risk | Risk Measurement | Risk Identification and Assessment Design & Implementation | Implement the issue management tool for the identification, capture and management of issues
Operational Risk | Risk Measurement | Material Event Escalation Process | Review the Material/Significant Event thresholds in line with peer institutions
Operational Risk | Risk Measurement | Enhance/Refine ORM Risk Identification and Assessment Tools and Processes | Review, evaluate and select RCSA methodology based on industry standards
Operational Risk | Risk Measurement | Enhance/Refine ORM Risk Identification and Assessment Tools and Processes | Review, evaluate and select RCSA methodology based on industry standards
Operational Risk | Risk Measurement | Scenario Analysis Tool | Evaluate Scenario Analysis Tools and Processes
Operational Risk | Risk Measurement | Scenario Analysis Tool | Complete scenario analysis program for SHUSA and Subsidiaries
Operational Risk | Risk Measurement | ORM Modeling Tool | Complete CCAR OR Loss Estimates
Operational Risk | Risk Measurement | ORM Modeling Tool | Refine operational risk loss forecasting model - Internal/External Loss Data Tools and Processes
Operational Risk | Risk Measurement | ORM Modeling Tool | Improve manual processes for OR Loss Event/Incident identification and collection
Operational Risk | Risk Measurement | Enhance IRM Assessment Tools and Processes | Refine methodology to focus on emerging threats and vulnerabilities
Operational Risk | Risk Measurement | Enhance IRM Assessment Tools and Processes | Evaluate threats and changes across regulatory landscape and industry standards
Operational Risk | Risk Measurement | Enhance IRM Assessment Tools and Processes | Develop and automate assessment processes
Operational Risk | Risk Measurement | Enhance/Refine VRM Assessment Tools and Processes | Refine methodology to focus on emerging threats and vulnerabilities
Operational Risk | Risk Measurement | Enhance/Refine VRM Assessment Tools and Processes | Evaluate threats and changes across regulatory landscape and industry standards
Operational Risk | Risk Measurement | Enhance/Refine VRM Assessment Tools and Processes | Develop and automate assessment processes
Operational Risk | Risk Measurement | Enhance/Refine BCM Assessment Tools and Processes | Review for program changes as a result of regulatory and SHUSA Policy changes
Operational Risk | Risk Measurement | Enhance/Refine BCM Assessment Tools and Processes | Review and refine existing Business Impact Analysis (BIA) of all SHUSA Subsidiaries
Operational Risk | Risk Measurement | Enhance/Refine BCM Assessment Tools and Processes | Identify gaps in critical processes, applications and testing
Operational Risk | Risk Measurement | Enhance/Refine BCM Assessment Tools and Processes | Review existing exercise results for each entity
Operational Risk | Risk Management | Update Internal Reporting | Continue to complete the baseline Ops Risk dashboard reporting for all Subsidiaries
Operational Risk | Risk Monitoring | Refine External Reporting | Develop timely reporting mechanisms and processes to satisfy OR Y-14Q reporting requirements
Operational Risk | Risk Monitoring | Refine External Reporting | Define automated system requirements for Ops Risk
Operational Risk | Risk Monitoring | Refine External Reporting | Hiperos roll-out in SBNA, begin implementation for New York branch
Operational Risk | Risk Monitoring | Refine External Reporting | Everbridge Crisis Management System roll-out to SHUSA and Subsidiaries
Operational Risk | Data & Systems | Data & Systems | Continue roll-out of iGRC within SBNA
Operational Risk | Data & Systems | Data & Systems | Select BCM tool across all SHUSA subsidiaries
Finance Transformation | Finance Planning and Analysis | Strategic Planning and Forecasting | Establish and execute foundational Planning and Forecasting framework including process governance, process timelines, clear roles and responsibilities and controlled approval processes
Finance Transformation | Finance Planning and Analysis | Strategic Planning and Forecasting | Ensure consistency between Strategic and Capital planning processes through appropriate controls, documentation, governance and aggregation and reporting tools to create Strategic and Capital planning outputs (ownership shared with Capital Management)
Finance Transformation | Finance Planning and Analysis | Business Performance | Incorporate cost of contingent liquidity across all IHC entities
Finance Transformation | Finance Planning and Analysis | Business Performance | Create high-level cost allocation model to support organizational and product group profitability to improve accuracy of contribution and ROE reporting
Finance Transformation | Finance Planning and Analysis | SHUSA Reporting & Analysis | Finalize build out of team dedicated to define and produce SHUSA and board management reporting
Finance Transformation | Finance Planning and Analysis | SHUSA Reporting & Analysis | Definition of requirement to supporting effective management decision making at SHUSA
Finance Transformation | Finance Planning and Analysis | Target Operating Model | Define FP&A Target Operating Model (clear roles and responsibilities, ownership and governance between holdco and entities)
Finance Transformation | Capital Management | Strengthen Capital planning governance and policy, and contingent capital planning and policy | Enhance capital policy and capital contingency policy to address FRS and IA feedback, satisfying ROPE and CCAR capital goals requirement
Finance Transformation | Capital Management | Strengthen Capital planning governance and policy, and contingent capital planning and policy | Develop capital expectations for IHC entities commensurate with size / complexity
Finance Transformation | Capital Management | Strengthen Capital planning governance and policy, and contingent capital planning and policy | Establish hand-off process from businesses to aggregation team, with a clearly defined operating model of sub-functions and activities to be centralized at SHUSA vs performed at each entity (specifically, NY, MIA, PR)
Finance Transformation | Capital Management | Strengthen Capital planning governance and policy, and contingent capital planning and policy | Operationalize processes for escalation to board, potential suspension of capital actions, and implementation of contingency plans (improve analysis and documentation of contingency actions)
Finance Transformation | Capital Management | Capital policy and planning | Develop granular forecast of baseline and stress scenarios to test capital adequacy, incorporating IHC entities
Finance Transformation | Capital Management | Capital policy and planning | Enhance the structure, transparency, and control of the process that produces capital forecasts, including validated models and assumptions, to ensure capital levels meet policy thresholds/ limits under normal and stressful conditions (where stressed conditions are specific to the BHC)
Finance Transformation | Capital Management | Capital policy and planning | Fully operationalize quarterly capital adequacy assessment with senior-level decision-making rooted in credit considerations, market expectations, and regulatory requirements
Finance Transformation | Capital Management | Capital policy and planning | Develop and assess future-focused alternative capital actions, ensuring full transparency of capital ratios relative to binding limits, to present to Board
Finance Transformation | Capital Management | Enhance Capital management aggregation, tracking, and reporting | Develop clear linkage of Risk, Capital, liquidity, and strategic planning across reporting and Risk Tolerances
Finance Transformation | Capital Management | Enhance Capital management aggregation, tracking, and reporting | Establish enhanced capital reporting, including monthly capital tracking
Finance Transformation | Capital Management | Enhance Capital management aggregation, tracking, and reporting | Improve financial analysis at consolidated and legal entity view, as required to establish a robust review, challenge, and sign-off for supporting documentation to the Capital Plan (e.g., review requirements by Internal Audit)
Finance Transformation | Capital Management | Enhance Capital management aggregation, tracking, and reporting | Conduct training sessions to prepare reviewers of aggregated results
Finance Transformation | Capital Management | RWA modeling and calculation methodology | Define and approve process for calculating RWA with appropriate governance, controls, and supporting documentation of RWA calculations, process and methodologies
Finance Transformation | Treasury | Operating Model | Complete execution of Target Operating Model (T.O.M.) with a focus on ALM and LRM functions
Finance Transformation | Treasury | Intraday Cash and Collateral Management | Establish local intraday cash and collateral management at each entity, and establish process for SHUSA to consolidate information and coordinate
Finance Transformation | Treasury | Intraday Cash and Collateral Management | Incorporate intraday procedures in SHUSA’s Cash Management and Funding policy and procedures
Finance Transformation
Finance Transformation | Treasury | Asset/Liability Management | Develop first version of Board-approved Enterprise and Operating policies, procedure and charter for Interest Rate Risk
Finance Transformation | Treasury | Asset/Liability Management | Enhance QRM operating environment including prudent mix of Chart of Accounts and dimensions, access controls and optimization of processes
Finance Transformation | Treasury | Stress Testing/Cash Flow Projections | Complete first round of stress testing, and re-iterate with additional scenarios once the framework is enhanced
Finance Transformation | Treasury | Stress Testing/Cash Flow Projections | Enhance stress testing assumptions, and update liquidity buffer based on results of the stress tests
Finance Transformation | Treasury | Regulatory Reporting (Treasury) | Develop capability to submit 2052a reports by 1/1/16
Finance Transformation | Treasury | Regulatory Reporting (Treasury) | U.S. LCR reporting (though not currently required, is expected to be produced as a result of the granularity of 2052a reporting)
Finance Transformation | Accounting | SHUSA / IHC Data Consolidation | Establish a set of reconciled and clean current and historical financial data (internal sources where possible) to use for reporting and to support forecasting capabilities (CCAR and Strategic Planning)
Finance Transformation | Accounting | SHUSA / IHC Data Consolidation | Enhanced current and historical consolidation of existing SHUSA entities supported by automated consolidation tool
Finance Transformation | Accounting | SHUSA / IHC Data Consolidation | Implement effective governance and controls around Chart of Accounts
Finance Transformation | Accounting | Data Reconciliation & Reporting Capabilities at SHUSA Level | Enhance reporting tools (FRS, Moody’s, and Workiva) to pull directly from consolidation tool (HFM) where possible
Finance Transformation | Accounting | Data Reconciliation & Reporting Capabilities at SHUSA Level | Sufficient reconciliation across all sources of financial historical data for financial/regulatory reports (Y-9C, Y-14’sA, Y-9C). Dependent upon robust contributor model with adequate controls at the entities and at holdco
Finance Transformation | Accounting | Data Reconciliation & Reporting Capabilities at SHUSA Level | Fully documented controls over reporting process (centralized and distributed components)
Finance Transformation | Accounting | End User Application Controls | All critical End User Application sources remediated with an industry standard and regulator recognized spreadsheet control tool
Finance Transformation | Internal Controls | Operating Model | Implementation of Target Operating Model with a focus on SBNA and SHUSA. Develop an operating structure that establishes a control framework for 1st, 2nd and 3rd line defense
Finance Transformation | Internal Controls | Operating Model | Development and/or enhancement of framework and methodology governing SOX, CCAR and EUA for SHUSA
Finance Transformation | Internal Controls | Reporting & Tools | Implementation of common software tools such as Cluster7 and Archer to manage the documentation, monitoring, evaluation, governance and reporting of internal control across all IHC entities
Risk Transformation | Re-design and embed Risk Appetite Statement | Re-design RAS for SHUSA enterprise | SHUSA Board-level Risk Appetite Statement
Risk Transformation | Re-design and embed Risk Appetite Statement | Re-design RAS for SHUSA enterprise | RAS reporting, breach escalation and breach penalty mechanism
Risk Transformation | Re-design and embed Risk Appetite Statement | Re-design RAS for SHUSA enterprise | Preliminary RAS communication and socialization materials
Risk Transformation | Re-design and embed Risk Appetite Statement | Cascaded RAS at subsidiary, BU levels and individual risk types | Approach to cascading SHUSA level Risk Appetite Statement to subsidiaries and levels below
Risk Transformation | Re-design and embed Risk Appetite Statement | Cascaded RAS at subsidiary, BU levels and individual risk types | RAS for all subsidiaries/BUs (aligned with overall SHUSA RAS)
Risk Transformation | Re-design and embed Risk Appetite Statement | Cascaded RAS at subsidiary, BU levels and individual risk types | RAS reporting, breach escalation and breach penalty mechanism (cascaded version)
Risk Transformation | Re-design and embed Risk Appetite Statement | Embed RAS in material processes | Delivery of Board-level RAS training: 1) Materials and 2) Delivery
Risk Transformation | Strengthen Board and Management oversight | Strengthen SHUSA Committee guidance | Review of Risk Management Committee oversight effectiveness
Risk Transformation | Strengthen Board and Management oversight | Strengthen SHUSA Committee guidance | Governance and co-ordination mechanisms within Group (i.e. engagement model in terms of linkage between SHUSA and Parent Group committees, etc.)
Risk Transformation | Strengthen Board and Management oversight | Strengthen SHUSA Committee guidance | Board Risk Committee reporting
Risk Transformation | Strengthen Board and Management oversight | Strengthen SHUSA Committee guidance | Updated committee composition, mandates, charters and compensation structure for high priority committees
Risk Transformation | Strengthen Board and Management oversight | Set a strong ‘Tone at the top | Revised and consistent risk-related messaging (link to articulation of ‘risk culture’):
Risk Transformation | Strengthen Board and Management oversight | Develop link between risk mgt. and performance assessment and compensation | Risk based / risk aware performance assessments and compensation framework and principles:
Risk Transformation | Strengthen Board and Management oversight | Continue and enhance Risk training for the Board Risk Committee | Risk training curriculum and schedule for Board Risk Committee including: (Training Materials, Detailed risk training objectives, Assessment and improvement process, Delivery)
Risk Transformation | Enhance Limits and Controls Framework | Review and update credit process controls and limits for underwriting and origination | High level review of credit process limits / controls
Risk Transformation | Enhance Limits and Controls Framework | Define risk oversight framework for IRR / liq. risk | Framework for risk oversight of key IRR and liquidity risk assumptions and parameters
Risk Transformation | Re-design operating model and talent management | Rationalize risk org structure | Future risk organizational model for SHUSA / subsidiaries
Risk Transformation | Re-design operating model and talent management | Rationalize risk org structure | Organizational structure design (including headcount)
Risk Transformation | Re-design operating model and talent management | Rationalize risk org structure | Communication materials to convey org. changes to enterprise
Risk Transformation | Re-design operating model and talent management | Articulate and embed 3LoD principles | Updated articulation of risk management roles and responsibilities across the three lines
Risk Transformation | Re-design operating model and talent management | Articulate and embed 3LoD principles | Training materials to explain model and key changes
Risk Transformation | Re-design operating model and talent management | Articulate and embed 3LoD principles | Initial roll out of 3 LOD
Risk Transformation | Re-design operating model and talent management | Design risk staff recruitment / retention strategy and onboard talent | Development and execution of Phase 1 Talent Management Strategy,
Risk Transformation | Re-design operating model and talent management | Improve risk culture | Risk culture assessment across the organization
Risk Transformation | Create/update policies and procedures | Improve effectiveness of policies and procedures | Assessment of existing current policies and procedures, and prioritization of improvement actions
Risk Transformation | Create/update policies and procedures | Improve effectiveness of policies and procedures | Frameworks defined and approved across all risk types
Risk Transformation | Create/update policies and procedures | Improve effectiveness of policies and procedures | Policy attestation process
Risk Transformation | Create effective risk identification and assessment process | Enhance risk identification and assessment process | Defined risk ID and assessment process, integrated into the end-to-end CCAR process:
Risk Transformation | Create effective risk identification and assessment process | Enhance risk identification and assessment process | Initial register of risks, encompassing both modeled and non-modeled risks across all relevant legal entities / BUs
Risk Transformation | Create effective risk identification and assessment process | Enhance risk identification and assessment process | Policy/procedure for Risk Identification and Assessment cycle (specifying frequency, stakeholders, duration, approvals, etc.)
Risk Transformation | Create effective risk identification and assessment process | Enhance risk identification and assessment process | Demonstrated linkage of risk ID process to capital planning (CCAR) process
Risk Transformation | Create effective risk identification and assessment process | Enhance risk identification and assessment process | Demonstrated linkage of risk ID process to risk mitigation, management and reporting
Risk Transformation
Risk Transformation | Design & Operationalize Financial Risk Management | Align credit risk mgt. activities alignment with 3LOD roles | Definition of credit-related roles and responsibilities and lines of control across 3LoD
Risk Transformation | Design & Operationalize Financial Risk Management | Align credit risk mgt. activities alignment with 3LOD roles | Initial roll-out of 3LOD across credit risk management
Risk Transformation | Design & Operationalize Financial Risk Management | Define expected liquidity risk capabilities and conduct gap analysis | Evaluation of current state against target capabilities and remediation plan
Risk Transformation | Design & Operationalize Financial Risk Management | Define expected liquidity risk capabilities and conduct gap analysis | Improvement of liquidity stress-testing
Risk Transformation | Update internal monitoring and reporting | Define risk reporting landscape | Risk reporting landscape, by audience and risk type
Risk Transformation | Update internal monitoring and reporting | Develop and socialize prototype reports | Prototype reports and socialization of high priority reports to Board & Senior Management
Risk Transformation | Update internal monitoring and reporting | Develop business requirements | Risk data requirements for reporting:
Risk Transformation | Update internal monitoring and reporting | Develop business requirements | Identification of risk aggregation needs to support reporting
Risk Transformation | Update internal monitoring and reporting | Determine resourcing needs to produce reports | Reporting resourcing
Risk Transformation | Improve data quality and aggregation and strengthen systems infrastructure | Create business and data requirements | Requirements defined for all data-related risk measurement, management, and reporting activities
Risk Transformation | Improve data quality and aggregation and strengthen systems infrastructure | Create business and data requirements | Prioritization of data requirements, both within and across individual business requirement documents
Risk Transformation | Improve data quality and aggregation and strengthen systems infrastructure | Define systems architecture to support data needs | Assessment of current systems architecture and identification of required enhancements to support data needs
Model Risk Management | Governance Oversight and Reporting | Strengthen oversight of the MRM framework by the Board and senior management | Provide training on MRM regulatory requirements and industry practices (Board, BERC, EMC)
Model Risk Management | Governance Oversight and Reporting | Strengthen oversight of the MRM framework by the Board and senior management | Clarify the roles of BERC, ERMC, EMC, MRMC in MRM. Revise committee charters and mandates to strengthen MRM o/s role
Model Risk Management | Governance Oversight and Reporting | Enhance Model Risk Reporting | Enhance model risk remediation reporting, governance, controls
Model Risk Management | Governance Oversight and Reporting | Enhance Model Risk Reporting | Enhance model risk BAU reporting standards. Deliver enhanced reporting (including Sen Leadership & Board)
Model Risk Management | Governance Oversight and Reporting | Enhance Model Risk Reporting | Define requirements for long term Model Inventory and Reporting system. Conduct vendor selection
Model Risk Management | Talent and Staffing | Talent and Staffing | Hire for known staffing openings
Model Risk Management | Talent and Staffing | Talent and Staffing | Conduct talent and staffing assessment for MRMG
Model Risk Management | Talent and Staffing | Talent and Staffing | Conduct First Line and auxiliary functions (IT, etc.) staffing assessment (Dependency on Model Development)
Model Risk Management | Talent and Staffing | Talent and Staffing | Develop staffing/hiring strategy (including external resources) and plan based on assessment, backlogs, and workloads
Model Risk Management | Talent and Staffing | Talent and Staffing | Implement hiring strategy/plan in partnership with the First Line/Model Development
Model Risk Management | SCUSA Pricing Governance and Oversight | SCUSA Pricing Governance and Oversight | Include MRMG specialist in SCUSA pricing governance
Model Risk Management | SCUSA Pricing Governance and Oversight | SCUSA Pricing Governance and Oversight | Strengthen oversight of the pricing of SCUSA retail financial products including committee charter updates
Model Risk Management | SCUSA Pricing Governance and Oversight | SCUSA Pricing Governance and Oversight | Enhance SCUSA pricing policies and procedures
Model Risk Management | MRM Policy, Procedures / Standards, Controls, and Training | Enhance MRM Policy/Procedures/Standards/Templates: | Update policy and procedure based on SR 11-7 guidance (gap analysis) including detailed model validation testing procedures
Model Risk Management | MRM Policy, Procedures / Standards, Controls, and Training | Enhance MRM Policy/Procedures/Standards/Templates: | Enhance Provisional Approval (PA) process, clarify roles and responsibilities
Model Risk Management | MRM Policy, Procedures / Standards, Controls, and Training | Enhance MRM Policy/Procedures/Standards/Templates: | Enhance decision making authority & roles and responsibilities for approving models and model changes (including model retirement)
Model Risk Management | MRM Policy, Procedures / Standards, Controls, and Training | Enhance MRM Policy/Procedures/Standards/Templates: | Redesign Risk Rating Methodology
Model Risk Management | MRM Policy, Procedures / Standards, Controls, and Training | Develop and deliver Training on updated Policy and Procedures | Enhance training based on updated Policy, Procedures, and Development Standards
Model Risk Management | MRM Policy, Procedures / Standards, Controls, and Training | Develop and deliver Training on updated Policy and Procedures | Train MRMG staff on the new validation procedures
Model Risk Management | MRM Policy, Procedures / Standards, Controls, and Training | Develop and deliver Training on updated Policy and Procedures | Begin targeted training on enhanced MRM Policy and Model Development Standards including training on SR 11-7 Standards and expectations (as a precursor to the Policy/Procedure rollout)
Model Risk Management | MRM Policy, Procedures / Standards, Controls, and Training | MRM Policy, Procedures / Standards, Controls, and Training | Implement Policy and Procedures/Standards
Model Risk Management | Model Validation | Address Legacy Models Validation Backlog: | Conduct gap assessment (e.g. conceptual soundness, etc.)
Model Risk Management | Model Validation | Address Legacy Models Validation Backlog: | Commence Validation not completed in in the initial gap assessment and initial validation for all models. Updates to Findings Log
Model Risk Management | Model Validation | Model Validation | Evaluate internal/external model pipeline management and reporting tools/process
Model Risk Management | Model Validation | Model Validation | Define and implement CCAR model validation schedule with Model Development
Model Risk Management | Data | Data | Define model data validation data and reporting requirements aligned to model risk management framework and validation standards
CART Workstream Year 1 Requirements Initiative Mapping