## Slide 1: Current projects that may overlap Risk Transformation Plan (1/2) Preliminary view
Theme | Current projects with potential overlap | Proposed action
Re-design and embed risk appetite statement (RAS) | SBNA Risk Tolerance Statement – May overlap with plans to re-develop RAS for priority subsidiaries SCUSA Risk Tolerance Statement – Framework is currently under review | Leverage existing work on SBNA Risk Tolerance Statement Communicate to SCUSA the overall RT plan and the intention to re-design and embed SHUSA and entity level RAS to inform decisions regarding in-flight work
Strengthen Board and Management Committees | SBNA Committee Structure - Reviewed earlier this year | Leverage existing work on SBNA Committee structure for project to ‘Strengthen SHUSA Board and Mgt. Committee Structure’
Re-design operating model and talent management | Staffing model review – A review of SBNA and SCUSA headcount is partially complete; may duplicate planned work to re-design the operating model | Assess existing work on staffing model review and leverage as appropriate
 | Performance Scorecard – Launched last year for EMC with commitment to enhance in 2015; potential conflict with plan to develop link between risk performance and compensation | Continue planned refresh on Performance Scorecard as in-depth CART initiative to develop link between risk performance and compensation is currently not scheduled until 2016
Draft
Note, this represents a ‘best efforts’ assessment of current projects with a potential overlap with planned RT projects. Additional projects may exist that overlap with planned RT projects.

## Slide 2: Ongoing initiatives that may overlap Risk Transformation Plan (2/2) Preliminary view
Theme | Current projects with potential overlap | Proposed action
Create / update policies and procedures | Risk Frameworks – Frameworks created for ERM, Credit, Market & Liquidity, Operational Risk, and MRM planned; overlaps with project to improve policies and procedures | Leverage existing work on Framework development as first stage in project to improve policies and procedures
Create effective risk identification and assessment process | Risk identification tool (iGRC) for risk capture at SBNA – Currently mapping risks and customizing for risk ID implementation; potential overlap with plans to develop risk register across all legal entities / BUs | Assess fit of iGRC tool for risk capture and support of risk identification and assessment process; make decision accordingly
Design and operationalize Financial Risk Mgt. | IHC market risk / IRR / liquidity risk – Existing projects in place to review risks from IHC perspective | Leverage existing work as part of high level gap analysis on market risk / IRR
Update internal monitoring and reporting | Risk Reporting Framework – Extensive work underway to improve risk data aggregation and reporting with current focus on rationalizing existing reports and defining business requirements; overlaps with work to enhance internal reporting | Assess progress of Risk Reporting work and compare to new RT plan priorities; leverage existing work and prioritize planned enhancements accordingly
Improve data quality, aggregation & systems | No upcoming overlaps identified | N/A
Draft
Note, this represents a ‘best efforts’ assessment of current projects with a potential overlap with planned RT projects. Additional projects may exist that overlap with planned RT projects.