## Interdependency Instructions
The CART Deliverable Interdependency workbook is intended for use by the horizontal workstreams to identify non-IT interdependencies between horizontal workstreams or dependencies outside of the CART Program.
The expectation is that any deliverable that is impacted by another workstream (with the exception of Data / IT) will be identified in this exercise. We understand that it is not a one to one mapping in many cases, so we have provided the opportunity to provide up to 4 major dependencies. If there are more than this for a particular deliverable, then please add columns. Each dependency is to be identifed in the "Workstream Interdependency" fields and comments field are provided to allow you to specify the nature of the interdependency. The Central Team will then do an initial mapping of your dependencies against actual deliverables from other workstreams leveraging your comments.
To use the Deliverable Inventory and add a deliverable please do the following:
1. Select the Risk Transformation tab
2. In column G, select the workstream upon which your deliverable is dependent
3. In colum H, provide a comment describing the sub workstream and details of what is driving the interdependency
4. Repeat in subsequent columns if more than 1 interdependency affects your deliverable
Please note that you can have more than one interdependency for a deliverable. Be sure to capture all of the workstreams that will affect your ability to execute your deliverables on the planned date.
CART- Interdependency Identifcation Instructions

## Risk Transformation
| Yes | [22 empty] | High
| No | [22 empty] | Medium
Low
Priority | Deliverable | Owner | Proposed Date | IT Dependency (Y/N) | Workstream Interdependency | Inter-dependency Comment | Workstream Interdependency2 | Inter-dependency Comment2 | Workstream Interdependency3 | Inter-dependency Comment3 | Workstream Interdependency4 | Inter-dependency Comment4 | Workstream Interdependency5 | Inter-dependency Comment5 | Milestone 1 | Proposed Date2 | Milestone 2 (If applicable) | Proposed Date3 | Milestone 3 (If applicable) | Proposed Date4 | Milestone 4 (If applicable) | Proposed Date5 | Milestone 5 (If applicable) | Proposed Date6 | Level of Effort/Complexity | Delivery Risk | Resources Required | Comments | Finance Transformation
Re-design SHUSA RAS | SHUSA RAS reporting and breach escalation processes | Edward Smith | 2015-08-10 | No | [10 empty] | Draft RAS |  | Final RAS |  | Draft process |  | Final process |  |  |  | High | Low | Yes
Re-design SHUSA RAS | SHUSA-level RAS | Edward Smith | 2015-08-10 | Yes | [10 empty] | Delivery of training | [9 empty] | Medium | Low | Yes
Re-design SHUSA RAS | Board approval for SHUSA RAS | Edward Smith | 2015-09-07 | No | Non CART Workstream | Ensure integration into Board agenda | [8 empty] | Board approval | [9 empty] | Low | Low | Yes
Re-design SHUSA RAS | RAS business and data requirements | Edward Smith | 2015-09-25 | Yes | [10 empty] | Draft of materials |  | Final materials and delivery of communication | [7 empty] | Medium | Low | Yes
Re-design SHUSA RAS | Board-level RAS communications | Edward Smith | 2015-09-25 | No | Non CART Workstream | Ensure integration into Board agenda | [8 empty] | Draft BRD |  | Final BRD and communication to T&O | [7 empty] | Low | Low | No
Cascade RAS to priority subsidiaries | RAS for priority subsidiaries (SBNA & SCUSA) | Edward Smith | 2015-11-06 | Yes | [10 empty] | Draft approach |  | Final approach | [7 empty] | Medium | Low | Yes
Cascade RAS to priority subsidiaries | Delivery of enterprise-level RAS comms. & socialization materials | Edward Smith | 2015-12-28 | No | Non CART Workstream | Enterprise wide comms need to be co-ordinated | [8 empty] | Draft RAS for priority subs and list of metrics |  | Input from subs |  | Final RAS for priority subs and list of metrics | [5 empty] | High | Low | Yes
Initialize embedding of RAS in material processes | Updated process maps for key processes with explicit RAS links | Edward Smith | 2015-11-27 | No | Non CART Workstream | Need to coordinate with process owners | [8 empty] | Draft process |  | Final process | [7 empty] | Medium | Low | Yes
Board risk committee training | Board risk training curriculum and schedule | Edward Smith | 2015-07-27 | No | [10 empty] | Board approval | [9 empty] | Low | Low | Yes
Board risk committee training | Board risk training sessions delivered - e.g. RAS | Edward Smith | 2015-09-28 | No | Non CART Workstream | Ensure integration into Board agenda
Board risk committee training | Board risk training sessions delivered - e.g. CCAR Governance | Edward Smith | 2015-11-30 | No | Non CART Workstream | Ensure integration into Board agenda
Strengthen SHUSA Board / Mgt. Committee guidance | Diagnostic of Risk Mgt. Committee (includes relationship with parent) | John Hennessey | 2015-06-29 | No | [10 empty] | Draft of training materials, including training schedule |  | Final training materials, including training schedule |  | Delivery of two training sessions | [5 empty] | Medium | Low | Yes
Strengthen SHUSA Board / Mgt. Committee guidance | Definition of composition / mandates / charters for priority committees | John Hennessey | 2015-09-28 | No | Operational Risk |  | Model Development |  | Model Risk Management | [5 empty] | Key stakeholder engagement |  | Draft governance and coordination mechanisms |  | Final governance and coordination mechanisms | [5 empty] | High | Medium | Yes
Strengthen SHUSA Board / Mgt. Committee guidance | Board approval for high priority committee changes | John Hennessey | 2015-09-28 | No | Non CART Workstream | Ensure integration into Board agenda | [8 empty] | Board approval | [9 empty] | Low | Low | Yes
Strengthen SHUSA Board / Mgt. Committee guidance | Definition of composition / mandates / charters for remaining committees | John Hennessey | 2015-12-28 | No | Operational Risk |  | Model Development |  | Model Risk Management | [5 empty] | Group approval | [9 empty] | Medium | Medium | Yes
Strengthen SHUSA Board / Mgt. Committee guidance | Board approval for low priority committee changes | John Hennessey | 2015-12-28 | No | Non CART Workstream | Ensure integration into Board agenda | [8 empty] | Draft of diagnostic materials |  | Final materials and delivery of diagnostic | [7 empty] | Medium | Low | Yes
Change & enforce Risk Leadership reporting lines | Updated Risk leadership reporting lines | John Hennessey | 2015-06-15 | No | Operational Risk |  | Model Development |  | Model Risk Management | [5 empty] | Draft of committee composition, mandates, and charters |  | Final committee composition, mandates, and charters | [7 empty] | High | Medium | Yes
Change & enforce Risk Leadership reporting lines | Board-approved Risk leadership organization | John Hennessey | 2015-06-29 | No | [10 empty] | Board approval | [9 empty] | Low | Low | Yes
Articulate 3 LoD across SHUSA-subsidiary relationships | Board-approved SHUSA frameworks | John Hennessey | 2015-07-27 | No | Non CART Workstream | Ensure integration into Board agenda | [8 empty] | Draft of committee composition, mandates, and charters |  | Final committee composition, mandates, and charters | [7 empty] | High | Medium | Yes
Articulate 3 LoD across SHUSA-subsidiary relationships | Cascaded SHUSA frameworks to subsidiaries | John Hennessey | 2015-09-28 | Yes | Operational Risk |  | Model Development |  | Model Risk Management | [5 empty] | Board approval | [9 empty] | Low | Low | Yes
Articulate 3 LoD across SHUSA-subsidiary relationships | Standardized policies and procedures, aligned to new frameworks for key risk types | John Hennessey | 2015-12-28 | No | Operational Risk |  | Model Development |  | Model Risk Management | [5 empty] | Identification of open positions |  | Engagement with HR |  | Recruitment rounds |  | Hiring of positions |  |  |  | High | High | No
Design Risk management organizational structures & staffing | Operating model design including headcount analysis | John Hennessey | 2015-08-03 | No | Operational Risk |  | Model Development |  | Model Risk Management | [5 empty] | Identification of open positions |  | Engagement with HR |  | Recruitment rounds |  | Hiring of positions |  |  |  | High | High | No
Design Risk management organizational structures & staffing | Recruitment of senior Risk and other high priority staff | Kerrie Maitland | 2015-11-30 | No | Operational Risk |  | Model Development |  | Model Risk Management | [5 empty] | Draft 3LoD principles |  | Final 3LoD principles | [7 empty] | Low | Low | Yes
Detail interactions between risk groups for critical processes | Interaction definition | John Hennessey | 2015-10-03 | No | Operational Risk |  | Model Development |  | Model Risk Management | [5 empty] | Draft reporting lines |  | Key stakeholder engagement |  | Final (formalization of) reporting lines | [5 empty] | Low | Low | Yes
Detail interactions between risk groups for critical processes | Critical processes updated | John Hennessey | 2015-09-14 | No | Operational Risk |  | Model Development |  | Model Risk Management | [5 empty] | Board approval | [9 empty] | Medium | Low | Yes
Talaent management | Perform a talent review and assessment of key risk staff and develop a strategy to address gaps (e.g. hiring, training, leadership programs, etc.) and begin rolling out hiring strategy to fill staffing gaps | John Hennessey | TBC | No | Operational Risk |  | Model Development |  | Model Risk Management |  | Model Risk Management
Talaent management | Articulation of a strong and desired risk culture and creation of risk communication forums (e.g. intranet, Risk Town Halls, etc.) | John Hennessey | TBC | No
Enhance Risk ID and Assessment process | Documentation of top-down risk aggregation | Edward Smith / Diane Allaire | 2015-06-29 | No | Non CART Workstream | Data & IT | [8 empty] | Draft of operating model |  | Final operating model | [7 empty] | High | Medium | Yes
Enhance Risk ID and Assessment process | Framework to identify material risks, including tools, templates, risk taxonomy, guidance, policies and procedures | Edward Smith / Diane Allaire | 2015-07-27 | No | [10 empty] | Draft headcount |  | Delivery of skills / staffing assessment |  | Hiring / redeployment strategy | [5 empty] | High | Medium | Yes
Enhance Risk ID and Assessment process | Definition of risk ID foundational elements, multi-year enhancement goals | Edward Smith / Diane Allaire | 2015-09-07 | No | Operational Risk | [9 empty] | Draft of communication and training materials for enterprise-wide communication |  | Delivery of final communication and training materials for enterprise-wide communication |  | Development of job descriptions |  | Delivery of enterprise-wide training |  |  |  | High | Medium | Yes
Enhance Risk ID and Assessment process | Clear linkages established between Risk ID output to capital planning scenario generation process | Edward Smith / Diane Allaire | 2015-11-01 | No | Non CART Workstream | CCAR | [8 empty] | Validation of updated frameworks | [9 empty] | Low | Low | No
Enhance Risk ID and Assessment process | Risk ID / Assess. business and data requirements, drawing upon process to create risk register | Edward Smith / Diane Allaire | 2015-11-01 | Yes | [10 empty] | Board approval | [9 empty] | Low | Low | No
Enhance Risk ID and Assessment process | Risk register for modeled and non-modeled risk with reporting to Board and Snr mgt. | Edward Smith / Diane Allaire | 2015-11-01 | Yes | [10 empty] | Draft of assessment |  | Delivery of assessment |  | Prioritization of enhancements |  | Final plan for enhancements, given stakeholder input |  | Standardization of all policies / procedures |  | Medium | Low | No
Conduct high level of credit risk management | High level wholesale credit process review incl. limits / controls and DoA at SCUSA and SBNA | TBD | 2015-11-15 | No | [10 empty] | Board approval | [9 empty] | Low | Low | No
Conduct liquidity risk gap analysis | Definition of target liq. risk capabilities, current state review and remediation plan | TBD | 2015-12-14 | No | [10 empty] | Conduct bottom-up risk identification |  | Aggregate, review & challenge |  | Conduct top-down risk identification |  | Draft of risk register |  | Final risk register |  | High | High | Yes
Enhance internal reporting | Assessment of current reporting landscape with quick win enhancements | Edward Smith | 2015-06-29 | No | [10 empty] | Draft policy and procedures for risk ID and assessment cycle |  | Final policy and procedures for risk ID and assessment cycle |  | Communication of policies/procedures to key stakeholders | [5 empty] | Medium | Low | No
Enhance internal reporting | Definition of target risk reporting landscape | Edward Smith | 2015-08-10 | Yes | Non CART Workstream | Data & IT | [8 empty] | Draft BRD |  | Final BRD and communication to T&O | [7 empty] | Low | Medium | No
Enhance internal reporting | Template reports and socialization of high priority reports | Edward Smith | 2015-09-21 | No | [10 empty] | Proposed recommendations |  | Approved recommendations |  | Updated Credit Policy | [5 empty] | Medium | Medium | Yes
Enhance internal reporting | Operationalization of high priority reports e.g. allocate reporting resources | Edward Smith | 2015-11-15 | Yes | Non CART Workstream | Data & IT | [8 empty] | Draft framework |  | Final framework | [7 empty] | Medium | Medium | Yes
Enhance internal reporting | Template reports and socialization of low priority reports | Edward Smith | 2015-12-28 | No | [10 empty] | Definition of liquidity risk capabilities |  | Current state vs. capabilities |  | Remediation plan | [5 empty] | Medium | Medium | Yes
[15 empty] | Initial review of risks |  | Scenario and impact analysis |  | Remediation plan |  | Business and data requirements |  |  |  | TBD | TBD | Yes
[15 empty] | Initial review of framework |  | Process and associated tools |  | Documented decision authority |  | Business and data requirements |  |  |  | TBD | TBD | Yes
[15 empty] | Risk reporting landscape outline | [9 empty] | Low | Low | Yes
[15 empty] | Board prototype reports |  | Senior management prototype reports | [7 empty] | Low | Medium | Yes
[15 empty] | Risk reporting data requirements - Board |  | Risk reporting data requirements - Senior Management | [7 empty] | Medium | High | Yes
[15 empty] | Target org structure for reporting groups |  | Definition of reporting resource requirements |  | Training for reporting resources | [5 empty] | Low | Medium | Yes
[15 empty] | Outlined target performance dashboard |  | Business and data requirements |  | Roadmap / plan for implementation |  | Prototype performance dashboard |  | Implemented performance dashboard |  | High | High | Yes
[15 empty] | Stakeholder engagement |  | Draft data requirements |  | Final data requirements | [5 empty] | High | High | No
[15 empty] | Data prioritization criteria |  | List of prioritized data | [7 empty] | Medium | Medium | No
[15 empty] | Draft target state |  | Final target state | [7 empty] | Low |  | No
[15 empty] | Current systems architecture |  | Remediation plan | [7 empty] | High | Medium | No
CART- Risk Transformation Deliverable Inventory

## Master Deliverable Inventory
. |  |  | Yes | [12 empty] | High
|  |  | No | [12 empty] | Medium
Low
Workstream | Initiative | Priority | Deliverable | Owner | Proposed Date | IT Dependency (Y/N) | Milestone 1 | Proposed Date2 | Milestone 2 (If applicable) | Proposed Date3 | Milestone 3 (If applicable) | Proposed Date4 | Milestone 4 (If applicable) | Proposed Date5 | Milestone 5 (If applicable) | Proposed Date6 | Level of Effort/Complexity | Delivery Risk | Resources Required | Comments | Finance Transformation
Finance Transformation | Internal Controls | Development and/or enhancement of framework and methodology governing SOX, CCAR and EUA for SHUSA | Enhance existing SOX internal controls framework and methodology | M. Munoz | 2015-12-31 | No | [10 empty] | Medium | High | Yes | Resources need to be approved, identified, and hired
Finance Transformation | Internal Controls | Development and/or enhancement of framework and methodology governing SOX, CCAR and EUA for SHUSA | Develop the CCAR internal controls framework and methodology | M. Munoz | 2015-12-31 | No | Conduct gap assessment against SOX framework | 2015-06-30 | Enhance framework to align with CCAR internal controls requirements | 2015-09-30 | Benchmark framework against industry standard/regulatory expectations | 2015-12-31 |  |  |  |  | Medium | Medium | Yes
Finance Transformation | Internal Controls | Development and/or enhancement of framework and methodology governing SOX, CCAR and EUA for SHUSA | Develop EUA internal controls framework and methodology | M. Munoz | 2015-12-31 | No | [10 empty] | Medium | Medium | No
Finance Transformation | Internal Controls | Implement SOX, CCAR, and EUA programs to manage the internal controls contruct and environment at SHUSA and all subsidiaries | Implement SOX internal controls program | M. Munoz | 2015-12-31 | yes | Approve and hire resources for open SOX positions across SHUSA | 2015-07-31 | Acquire tool (Archer) to manage the documentation, monitoring, evaluation, governance and reporting of internal controls across SHUSA | 2015-06-30 | Configure (Archer) tool to manage the documentation, monitoring, evaluation, governance and reporting of internal controls across SHUSA | 2015-07-31 | Source clean data into the tool to enable adherence with enhanced SOX methodology | 2015-11-30 | Complete testing and certification for SOX | 2015-12-31 | High | Medium | No
Finance Transformation | Internal Controls | Implement SOX, CCAR, and EUA programs to manage the internal controls contruct and environment at SHUSA and all subsidiaries | Implement CCAR internal controls program | M. Munoz | 2015-12-31 | yes | Approve and hire resources for open SOX positions across SHUSA | 2015-07-31 | Leverage tool used for SOX compliance to manage the documentation, monitoring, evaluation, governance and reporting of internal controls across SHUSA | 2015-11-30 | Conduct gap assessment against existing CCAR controls and documentation | 2015-09-30 | Develop and execute on remediation plan based on gap findings | 2015-09-30 | Complete testing and certification for CCAR | 2015-12-31 | Medium | Medium | No
Finance Transformation | Internal Controls | Implement SOX, CCAR, and EUA programs to manage the internal controls contruct and environment at SHUSA and all subsidiaries | Implement EUA internal controls program | M. Munoz | 2015-12-31 | No | Operationalize existing tool across all new SHUSA subsidiaries to remediate existing MRIA on spreadsheet risk management | 2015-06-30 | Execute active identification and management of critical spreadsheets | 2015-12-31 | [6 empty] | Medium | High | Yes | Need to approve, identify, and hire resources (also tool needs to be installed)
Finance Transformation | Finance Planning and Analysis | Define FP&A Target Operating Model (clear roles and responsibilities, ownership and governance between holdco and entities) | Develop FP&A Policy Document | D. Budington | 2015-07-10 | No | Review and Approve Governance Model Design | 2015-06-05 | Review and approve Planning process Design | 2015-06-30 | Review and approve data flow map and reconciliation points | 2015-07-10 | Review and approve Planning Guide Framework | 2015-07-10 |  |  | Medium | Medium | Yes | Delivery Risk: Requires executive approval and entity buy-in on process design and roles/responsibilities
Finance Transformation | Finance Planning and Analysis | Execute 2015 P-18 process ensuring consistency between Strategic and Capital planning processes to create Strategic and Capital planning outputs (ownership shared with Capital Management) | Saffing of critical positions within strategic planning and PPNR teams. | D. Budington | 2015-07-30 | Yes | Define new Product Planning Tree. ) (Sign-off required by Finance/Accounting, Strategic Planning, Treasury & Market Risk | 2015-06-15 | Contract-level actual and historical data (7 years) for SBNA and SCUSA (from CCMIS, RDM, EDW, ALM datamart) - consistent across entities and reconcilable with GL | TBD | Implementation of forecasting engine | TBD |  |  |  |  | High | High | Yes | SAS, Moody's as data repository for contract level information and RWA.
Finance Transformation | Finance Planning and Analysis | Execute 2015 P-18 process ensuring consistency between Strategic and Capital planning processes to create Strategic and Capital planning outputs (ownership shared with Capital Management) | Develop 2015 Strategic Plan Timeline (Planning Calendar) | D. Budington | 2015-06-15 | No | [10 empty] | Medium | Medium | Yes | Delivery Risk: Data availability, resource/ entity commitment to timeline and process
Finance Transformation | Finance Planning and Analysis | Execute 2015 P-18 process ensuring consistency between Strategic and Capital planning processes to create Strategic and Capital planning outputs (ownership shared with Capital Management) | Strategic Plan / Investor Day 3 year plan | D. Budington | 2015-09-30 | No | Complete high-level 3 year strategic priorities | 2015-06-30 | Deliver Investor Day Presentation | 2015-09-15 | Final Board Approval Strat Plan | 2015-09-30 |  |  |  |  | Medium | Medium | Yes | Delivery Risk: Data availability, resource/ entity commitment to timeline and process
Finance Transformation | Finance Planning and Analysis | Execute 2015 P-18 process ensuring consistency between Strategic and Capital planning processes to create Strategic and Capital planning outputs (ownership shared with Capital Management) | Develop Interim Planning Guide (Instructions for 2015) | D. Budington | 2015-10-15 | No | [10 empty] | Medium | Medium | Yes | Delivery Risk: Data availability, resource/ entity commitment to timeline and process
Finance Transformation | Finance Planning and Analysis | Execute 2015 P-18 process ensuring consistency between Strategic and Capital planning processes to create Strategic and Capital planning outputs (ownership shared with Capital Management) | Deliver 2016 Budget | D. Budington | 2015-12-31 | No | Complete mapping process of Budget to Strat plan | 2015-12-01 | Entity submission | 2015-12-01 | Complete Review & Challenge Process | 2015-12-15 | Final submission | 2015-12-15 | Final Board Approval | 2015-12-31 | Medium | Medium | Yes | Delivery Risk: Data availability, resource/ entity commitment to timeline and process
Finance Transformation | Finance Planning and Analysis | Execute 2015 P-18 process ensuring consistency between Strategic and Capital planning processes to create Strategic and Capital planning outputs (ownership shared with Capital Management)
Finance Transformation | Finance Planning and Analysis | Execute 2015 P-18 process ensuring consistency between Strategic and Capital planning processes to create Strategic and Capital planning outputs (ownership shared with Capital Management)
Finance Transformation | Finance Planning and Analysis | Finalize build out of team dedicated to define and produce SHUSA and board management reporting | Identify and hire team | D. Budington | 2015-09-30 | No | [10 empty] | Medium | Medium | Yes | Delivery Risk: Hiring of team to execute reporting process
Finance Transformation | Finance Planning and Analysis | Finalize build out of team dedicated to define and produce SHUSA and board management reporting | Develop Reporting Package Templates | D. Budington | 2015-06-30 | No | [10 empty] | Medium | Medium | Yes | Delivery Risk: Hiring of team to execute reporting process
Finance Transformation | Finance Planning and Analysis | Finalize build out of team dedicated to define and produce SHUSA and board management reporting | Complete Consolidated and Entity Forecast Reporting Package | D. Budington | Monthly | No | [10 empty] | Medium | Medium | Yes | Delivery Risk: Hiring of team to execute reporting process
Finance Transformation | Finance Planning and Analysis | Finalize build out of team dedicated to define and produce SHUSA and board management reporting | Develop Monthly Board Report Package | D. Budington | Monthly | No | [10 empty] | Medium | Medium | Yes | Delivery Risk: Hiring of team to execute reporting process
Finance Transformation | Finance Planning and Analysis | Finalize build out of team dedicated to define and produce SHUSA and board management reporting | Develop Monthly Profitability Reporting Package | D. Budington | Monthly | No | [10 empty] | Medium | Medium | Yes | Delivery Risk: Hiring of team to execute reporting process
Finance Transformation | Finance Planning and Analysis | Define requirements to support interim and target state business, data and reporting requirements to support planning and forecasting, management reporting and multi-dimensional profitability | Complete Business Requirement Documents (process areas covered include BS/NIM Planning, Non-Interest Income, Non-Interest Expense, FTP, Cost Allocation, Capital Allocation, Planning Process) | D. Budington | 2015-06-10 | No | [10 empty] | Medium | Medium | Yes | Delivery Risk: Resource availability to review and approve requirement documents
Finance Transformation | Finance Planning and Analysis | Define requirements to support interim and target state business, data and reporting requirements to support planning and forecasting, management reporting and multi-dimensional profitability | Complete High-level Technical Architecture | D. Budington | 2015-06-10 | No | [10 empty] | Medium | Medium | Yes | Delivery Risk: Resource availability to review and approve requirement documents
Finance Transformation | Finance Planning and Analysis | Technology design and rationalization based on methodology and system decisions for planning, forecasting and reporting | Complete Detailed System Design | D. Budington | 2015-10-30 | Yes | [10 empty] | Medium | Medium | Yes | Delivery Risk: Technology resource availability for design meetings
Finance Transformation | Finance Planning and Analysis | Develop a detailed project plan with T&O based on release schedule for target state implementation | Complete Detailed Project Plan for implementation of technology solution | D. Budington | 2015-12-31 | Yes | [10 empty] | Medium | Medium | Yes | Delivery Risk: Technology resource availability for design meetings
Finance Transformation | Treasury | Complete execution of Target Operating Model (T.O.M.) with a focus on ALM and LRM functions | Establish policies, procedures and MIS per regulatory requirements and enhanced internal practices | Manuel Aya | 2015-10-20 | No | Fulfill all open Treasury positions | 2015-09-30 | Target Operating Model Implemented | 2015-06-30 | Enhanced Internal practices identified and distributed for implementation | 2015-09-30 |  |  |  |  | Medium | Medium | No
Finance Transformation | Treasury | Complete execution of Target Operating Model (T.O.M.) with a focus on ALM and LRM functions | Independent Review of LRM adequacy and effectiveness | Manuel Aya | 2015-10-20 | No | Establish policies and procedures to facilitate the independent review of the LRM policies, procedures and generation of analytics | 2015-10-20 | [8 empty] | Medium | Low | No
Finance Transformation | Treasury | Establish local intraday cash and collateral management at each entity, and establish process for SHUSA to consolidate information and coordinate | Establish Policies and Procedures to Consolidate Intraday Liquidity Management | Manuel Aya | 2015-09-30 | No | Intraday Liquidity Management consolidation policies and procedures developed | 2015-09-30 | Intraday Liquidity Management consolidation policies and procedures approved by all applicable management committees | 2015-09-30 | [6 empty] | High | Medium | Yes
Finance Transformation | Treasury | Establish local intraday cash and collateral management at each entity, and establish process for SHUSA to consolidate information and coordinate | Establish Policies and Procedures to Consolidate Intraday Collateral Management | Manuel Aya / Ed Cipullo | 2015-09-30 | Yes | Intraday Collateral Management consolidation policies and procedures developed | 2015-09-30 | Intraday Collateral Management consolidation policies and procedures approved by all applicable management committees | 2015-09-30 | Bank of New York (BONY Collateral Management System implemented | 2015-09-30 |  |  |  |  | High | Medium | Yes
Finance Transformation | Treasury | Incorporate intraday procedures in SHUSA’s Cash Management and Funding policy and procedures | Incorporate intraday procedures and intraday metrics into SHUSA’s Liquidity Management and Funding policy and procedures | Manuel Aya, Bill Brundige, Andy Withers | 2015-12-31 | Yes | Intraday Liquidity Management consolidation policies and procedures implemented | 2015-12-31 | Intraday Collateral Management consolidation policies and procedures implemented | 2015-12-31 | Consolidated Intraday Liquidity Management information available for use by SHUSA | 2015-12-31 | Consolidated Intraday Collateral Management information available for use by SHUSA | 2015-12-31 |  |  | High | High | Yes
Finance Transformation | Treasury | Develop first version of Board-approved Enterprise and Operating policies, procedure and charter for Interest Rate Risk | Produce Board approved Enterprise Operating Liquidity Risk Management Policy (OLRPM) and associated procedure(s) | Victor Morillo | 2015-12-31 | No | Enterprise Operating Liquidity Risk Management Policies (OLRMP) developed | 2015-06-30 | Enterprise Operating Liquidity Risk Management Policies (OLRMP) approved by all applicable management committees | 2015-06-30 | Enterprise Operating Liquidity Risk Management Policies (OLRMP) implemented for SHUSA, SCUSA, SBNA | 2015-09-23 | Enterprise Operating Liquidity Risk Management Policies (OLRMP) implemented for all IHC entities | 2015-12-31 |  |  | Medium | Medium | No
Finance Transformation | Treasury | Enhance QRM operating environment including prudent mix of Chart of Accounts and dimensions, access controls and optimization of processes | Analyze and Revise QRM environment including Chart of Accounts, dimensions, controls and optimization of processes | Niraj Biswas | 2015-12-31 | Yes | QRM Chart of Accounts and Dimensions analyzed, reviewed and enhanced | 2015-09-30 | QRM access control and information distribution / sharing analyzed, reviewed and enhanced | 2015-09-30 | QRM processes reviewed and enhanced to provide improved availability of QRM information and implementation of "best practices" | 2015-12-31 |  |  |  |  | High | High | Yes
Finance Transformation | Treasury | Complete first round of stress testing, and re-iterate with additional scenarios once the framework is enhanced | Cash Flow Projections | Manuel Aya | 2015-12-31 | Yes | Baseline Cashflow Projections | 2015-06-01 | Cash Flow Projection tool / reporting developed and deployed | 2015-12-31 | [6 empty] | High | Medium | No
Finance Transformation | Treasury | Complete first round of stress testing, and re-iterate with additional scenarios once the framework is enhanced | Model Validation | MRM | 2015-12-31 | Yes | Conduct formal Model Validation on Stress testing Scenarios | 2015-12-31 | [8 empty] | High | Medium | No
Finance Transformation | Treasury | Complete first round of stress testing, and re-iterate with additional scenarios once the framework is enhanced | First round of stress testing completed and documented | Manuel Aya | 2015-05-29 | Yes | Stress Testing Tool developed and available | 2015-05-04 | First round of stress test generating scenarios and assumptions approved by all applicable management committees | 2015-05-29 | First round of stress test scenarios executed and complete results generated | 2015-05-29 | First round of stress test results fully documented and analyzed | 2015-05-29 | First round of stress test results published to all applicable management parties | 2015-05-29 | High | Medium | No
Finance Transformation | Treasury | Complete first round of stress testing, and re-iterate with additional scenarios once the framework is enhanced | Enhance stress testing process with additional "framework" scenarios | Manuel Aya | 2015-12-31 | Yes | First round of enhanced stress test generating scenarios and assumptions approved by all applicable management committees | 2015-12-31 | Enhanced first round of stress test scenarios executed and complete results generated | 2015-12-31 | Enhanced first round of stress test results fully documented and analyzed | 2015-12-31 | Enhanced first round of stress test results published to all applicable management parties | 2015-12-31 |  |  | High | Medium | No
Finance Transformation | Treasury | Enhance stress testing assumptions, and update liquidity buffer based on results of the stress tests | Enhance stress testing process | Manuel Aya | 2016-04-18 | No | Conduct regression analysis of stress testing scenarios and assumptions for applicability, accuracy, and adjustment | 2016-04-18 | Revalidate, via formal Model Risk Management process, proposed adjustments to stress testing scenarios and / or assumptions | 2016-04-18 | Revised (if applicable) stress testing scenarios and assumptions approved by all applicable management committees | 2016-04-18 |  |  |  |  | High | Medium | No
Finance Transformation | Treasury | Enhance stress testing assumptions, and update liquidity buffer based on results of the stress tests | Operationalization of stress testing completed and documented | Manuel Aya | 2016-04-18 | Yes | Second round of stress test generating scenarios and assumptions approved by all applicable management committees | 2016-04-18 | Second round of stress test scenarios executed and complete results generated | 2016-04-18 | Second round of stress test results fully documented and analyzed | 2016-04-18 | Second round of stress test results published to all applicable management parties | 2016-04-18 |  |  | High | Medium | No
Finance Transformation | Treasury | Enhance stress testing assumptions, and update liquidity buffer based on results of the stress tests | Update Liquidity Buffer | Manuel Aya | 2015-09-30 | No | Evaluate results of second round of stress testing to identify required adjustments to the Liquidity Buffer | 2015-06-30 | Proposed changes to the Liquidity Buffer approved by all applicable management committees | 2015-06-30 | Implement adjustments to the Liquidity Buffer via established procedures | 2015-09-30 |  |  |  |  | Medium | Medium | No
Finance Transformation | Treasury | Develop capability to submit 2052a reports by 1/1/16 | Develop solution for data acquisition and storage to support 2052A regulatory reporting | Manuel Aya | 2015-12-31 | Yes | All required source data identified and availability/ location confirmed and documented | 2015-12-31 | All required source data extracted from identified source(s) and available for testing | 2015-12-31 | 2052A reporting solution developed and available for testing | 2015-12-31 | Quality Assurance testing for 2052A Reporting solution complete | 2015-12-31 | 2052A Reporting solution tested and deployed. | 2015-12-31 | High | High | No
Finance Transformation | Treasury | U.S. LCR reporting (though not currently required, is expected to be produced as a result of the granularity of 2052a reporting) | Develop reporting solution to generate Liquidity Coverage Ratio (LCR) reporting based upon data submitted via 2052A | Manuel Aya | 2015-12-31 | Yes | Liquidity Coverage Ratio (LCR) reporting solution developed and available for testing | 2015-12-31 | Quality Assurance testing for Liquidity Coverage Ratio (LCR) reporting solution complete | 2015-12-31 | [6 empty] | High | High | No
Finance Transformation | Accounting, Tax, & Reporting | Establish a set of reconciled and clean current and historical financial data (internal sources where possible) to use for reporting and to support forecasting capabilities (CCAR and Strategic Planning) | Define historical reporting requirements (from CCAR/Strategic Plan perspective) | Eric Ratican | 2015-12-31 | Yes | [10 empty] | High | High | Yes | Need RCRD resources; Delivery Risk: Data Quality and Data Sourcing
Finance Transformation | Accounting, Tax, & Reporting | Enhance current and historical consolidation of existing SHUSA entities and all IHC entities supported by a consolidation tool with automated general ledger feeds and a robust contributor process for supplemental data with adequate distributed and centralized controls | Implement Hyperion Consolidation (SBNA) | Nancy Reinhard | 2015-11-06 | Yes | Establish CoA and map SBNA to CoA | 2015-05-22 | Identify, Prioritize, & Remediate Gaps in SBNA GL mapping | 2015-05-22 | Identify and develop process for feeding supplemental information from SBNA to Hyperion | 2015-05-22 | Develop both subsidiary-level and holdco-level controls over process to feed supplemental information from SBNA to Hyperion, including control testing scope | 2015-05-22 | Assess staffing levels to support process at SBNA | 2015-05-22 | High | High | Yes | Additional internal and consulting resource. Delivery Risk: Sufficient entity ability to support.
Finance Transformation | Accounting, Tax, & Reporting | Enhance current and historical consolidation of existing SHUSA entities and all IHC entities supported by a consolidation tool with automated general ledger feeds and a robust contributor process for supplemental data with adequate distributed and centralized controls | Implement Hyperion Consolidation (SCUSA) | Nancy Reinhard | 2015-11-06 | Yes | Establish CoA and map SCUSA to CoA | 2015-05-22 | Identify, Prioritize, & Remediate Gaps in SCUSA GL mapping | 2015-05-22 | Identify and develop process for feeding supplemental information from SCUSA to Hyperion | 2015-05-22 | Develop both subsidiary-level and holdco-level controls over process to feed supplemental information from SCUSA to Hyperion, including control testing scope | 2015-05-22 | Assess staffing levels to support process at SCUSA | 2015-05-22 | High | High | Yes | Additional internal and consulting resource. Delivery Risk: Sufficient entity ability to support.
Finance Transformation | Accounting, Tax, & Reporting | Enhance current and historical consolidation of existing SHUSA entities and all IHC entities supported by a consolidation tool with automated general ledger feeds and a robust contributor process for supplemental data with adequate distributed and centralized controls | Implement Hyperion Consolidation (BSI) | Nancy Reinhard | 2015-11-06 | Yes | Establish CoA and map BSI to CoA | 2015-05-22 | Identify, Prioritize, & Remediate Gaps in BSI GL mapping | 2015-05-22 | Identify and develop process for feeding supplemental information from BSI to Hyperion | 2015-05-22 | Develop both subsidiary-level and holdco-level controls over process to feed supplemental information from BSI to Hyperion, including control testing scope | 2015-05-22 | Assess staffing levels to support process at BSI | 2015-05-22 | High | High | Yes | Additional internal and consulting resource. Delivery Risk: Sufficient entity ability to support.
Finance Transformation | Accounting, Tax, & Reporting | Enhance current and historical consolidation of existing SHUSA entities and all IHC entities supported by a consolidation tool with automated general ledger feeds and a robust contributor process for supplemental data with adequate distributed and centralized controls | Implement Hyperion Consolidation (PR) | Nancy Reinhard | 2015-11-06 | Yes | Establish CoA and map PR to CoA | 2015-05-22 | Identify, Prioritize, & Remediate Gaps in PR GL mapping | 2015-05-22 | Identify and develop process for feeding supplemental information from PR to Hyperion | 2015-05-22 | Develop both subsidiary-level and holdco-level controls over process to feed supplemental information from PR to Hyperion, including control testing scope | 2015-05-22 | Assess staffing levels to support process at PR | 2015-05-22 | High | High | Yes | Additional internal and consulting resource. Delivery Risk: Sufficient entity ability to support.
Finance Transformation | Accounting, Tax, & Reporting | Enhance current and historical consolidation of existing SHUSA entities and all IHC entities supported by a consolidation tool with automated general ledger feeds and a robust contributor process for supplemental data with adequate distributed and centralized controls | Implement Hyperion Consolidation (SIS) | Nancy Reinhard | 2015-11-06 | Yes | Establish CoA and map SIS to CoA | 2015-05-22 | Identify, Prioritize, & Remediate Gaps in SIS GL mapping | 2015-05-22 | Identify and develop process for feeding supplemental information from SIS to Hyperion | 2015-05-22 | Develop both subsidiary-level and holdco-level controls over process to feed supplemental information from SIS to Hyperion, including control testing scope | 2015-05-22 | Assess staffing levels to support process at SIS | 2015-05-22 | High | High | Yes | Additional internal and consulting resource. Delivery Risk: Sufficient entity ability to support.
Finance Transformation | Accounting, Tax, & Reporting | Enhance current and historical consolidation of existing SHUSA entities and all IHC entities supported by a consolidation tool with automated general ledger feeds and a robust contributor process for supplemental data with adequate distributed and centralized controls | Implement Hyperion Consolidation (IHC-Other) | Nancy Reinhard | 2015-11-06 | Yes | Establish CoA and map IHC-Other to CoA | 2015-05-22 | Identify, Prioritize, & Remediate Gaps in IHC-Other GL mapping | 2015-05-22 | Identify and develop process for feeding supplemental information from IHC-Other to Hyperion | 2015-05-22 | Develop both subsidiary-level and holdco-level controls over process to feed supplemental information from IHC-Other to Hyperion, including control testing scope | 2015-05-22 | Assess staffing levels to support process at IHC-Other | 2015-05-22 | High | High | Yes | Additional internal and consulting resource. Delivery Risk: Sufficient entity ability to support.
Finance Transformation | Accounting, Tax, & Reporting | Establish effective governance and controls over Chart of Accounts for all IHC entities | Implement Data Relationship Governance (DRG) | John Moore | 2015-11-12 | Yes | DRG: Complete Assess Phase | 2015-06-24 | DRG: Complete Design Phase | 2015-07-23 | DRG: Complete Construct Phase | 2015-08-28 | DRG: Complete Implement Phase | 2015-09-24 | DRG: Complete Operate & Review Phase | 2015-11-12 | High | High | Yes | May need additional resources. Delivery Risk: Willingness to comply with new change management process & controls
Finance Transformation | Accounting, Tax, & Reporting | Establish effective governance and controls over Chart of Accounts for all IHC entities | Implement Data Relationship Manager (DRM) | John Moore | 2015-11-12 | Yes | DRM: Complete Assess Phase | 2015-05-08 | DRM: Complete Design Phase | 2015-06-24 | DRM: Complete Construct Phase | 2015-08-11 | DRM: Complete Implement Phase | 2015-10-02 | DRM: Complete Operate & Review Phase | 2015-11-12 | High | High | Yes | May need additional resources. Delivery Risk: Willingness to comply with new change management process & controls
Finance Transformation | Accounting, Tax, & Reporting | Establish effective governance and controls over Chart of Accounts for all IHC entities | Establish Formal Governance over CoA/Hierarchies | John Moore | 2015-12-31 | Yes | Define roles/responsibilities for managing CoA | 2015-06-24 | Obtain acknowledgement from entities of understanding of Governance process | 2015-06-24 | Implement formal governance | 2015-12-31 |  |  |  |  | High | Medium | No | Delivery Risk: Willingness to comply with new change management process & controls
Finance Transformation | Accounting, Tax, & Reporting | Leverage existing reporting tools (FRS and Workiva) and new tools (Moody’s) to pull directly from HFM consolidation tool where applicable | Establish FRS feed from HFM | Sean Mulcahy | 2015-12-31 | Yes | Map expected HFM capability to FRS reporting requirements | 2015-12-31 | Identify gaps in HFM/FRS mapping | 2015-12-31 | Develop plan for remediation of HFM/FRS mapping gaps | 2015-12-31 | Remediate HFM/FRS mapping gaps | 2015-12-31 | Design HFM/FRS integration | 2015-12-31 | High | High | Yes | IT may need additional resources. Delivery Risk: Challenge to complete parallel activities and meet deliverables on time within current organizational structure
Finance Transformation | Accounting, Tax, & Reporting | Leverage existing reporting tools (FRS and Workiva) and new tools (Moody’s) to pull directly from HFM consolidation tool where applicable | Establish Moody's feed from HFM | Eric Ratican | 2015-12-31 | Yes | Map expected HFM capability to Moody's reporting requirements | 2015-12-31 | Identify gaps in HFM/Moody's mapping | 2015-12-31 | Develop plan for remediation of HFM/Moody's mapping gaps | 2015-12-31 | Remediate HFM/Moody's mapping gaps | 2015-12-31 | Design HFM/Moody's integration | 2015-12-31 | High | High | Yes | IT may need additional resources. Delivery Risk: Challenge to complete parallel activities and meet deliverables on time within current organizational structure
Finance Transformation | Accounting, Tax, & Reporting | Leverage existing reporting tools (FRS and Workiva) and new tools (Moody’s) to pull directly from HFM consolidation tool where applicable | Establish Workiva feed from HFM | Kerry Marshall | 2016-02-29 | Yes | Map expected HFM capability to Workiva reporting requirements | 2016-02-29 | Identify gaps in HFM/Workiva mapping | 2016-02-29 | Develop plan for remediation of HFM/Workiva mapping gaps | 2016-02-29 | Remediate HFM/Workiva mapping gaps | 2016-02-29 | Design HFM/Workiva integration | 2016-02-29 | High | High | Yes | IT may need additional resources. Delivery Risk: Challenge to complete parallel activities and meet deliverables on time within current organizational structure
Finance Transformation | Accounting, Tax, & Reporting | Reconciliation across appropriate sources of financial data for financial/regulatory reports (Y-9C, Y-14’s, SEC, and other regulatory reporting). | Establish fully functional CoA with hierarchy dimensionality | Nancy Reinhard | 2015-09-30 | Yes | Complete HFM implementation (dependency placeholder) | 2015-11-06 | [8 empty] | High | High | Yes | Same resources as above to deliver HFM.Delivery Risk: Clear data definitions / overarching data governance, and data quality / data sourcing to complete accurate/timely reconciliation
Finance Transformation | Accounting, Tax, & Reporting | Reconciliation across appropriate sources of financial data for financial/regulatory reports (Y-9C, Y-14’s, SEC, and other regulatory reporting). | Establish reconciliation process between entity GLs and Hyperion | Nancy Reinhard | 2015-09-30 | Yes | Establish reconciliation process for SHUSA | 2015-09-30 | Establish reconciliation process for SBNA | 2015-09-30 | Establish reconciliation process for SCUSA | 2015-09-30 | Establish reconciliation process for BSI | 2015-09-30 | Establish reconciliation process for PR | 2015-09-30 | Medium | Medium | No | Delivery Risk: Clear data definitions / overarching data governance, and data quality / data sourcing to complete accurate/timely reconciliation
Finance Transformation | Accounting, Tax, & Reporting | Reconciliation across appropriate sources of financial data for financial/regulatory reports (Y-9C, Y-14’s, SEC, and other regulatory reporting). | Establish reconciliation process between Hyperion and financial/regulatory reporting tools | Nancy Reinhard | 2015-09-30 | Yes | Establish reconciliation process for FRS | 2015-09-30 | Establish reconciliation process for Moody's | 2015-09-30 | Establish reconciliation process for Workiva | 2015-09-30 |  |  |  |  | High | High | Yes | Need consultants to design process. Delivery Risk: Clear data definitions / overarching data governance, and data quality / data sourcing to complete accurate/timely reconciliation
Finance Transformation | Accounting, Tax, & Reporting | Reconciliation across appropriate sources of financial data for financial/regulatory reports (Y-9C, Y-14’s, SEC, and other regulatory reporting). | Establish reconciliation process between the reporting tools | Nancy Reinhard | 2015-09-30 | Yes | Identify common elements between reporting | 2015-09-30 | Complete 4-way recon between Hyperion-FRS-Moody's-Workiva | 2015-09-30 | [6 empty] | High | High | Yes | Delivery Risk: Clear data definitions / overarching data governance, and data quality / data sourcing to complete accurate/timely reconciliation
Finance Transformation | Accounting, Tax, & Reporting | Comprehensive documentation of controls over reporting process (centralized and distributed components) | Revise existing SOX-level control documentation | Manuel Munoz | 2015-09-30 | No | Revise process for tax reporting | 2015-09-30 | Revise process for parent reporting | 2015-09-30 | Revise process for reg reporting | 2015-09-30 | Revise process for CCAR reg reporting | 2015-09-30 | Revise process for SEC reporting | 2015-09-30 | Medium | Medium | Yes | Need consultants to develop documentation. Delivery Risk: Comprehensive cross-functional participation, expertise in documentation
Finance Transformation | Accounting, Tax, & Reporting | Comprehensive documentation of controls over reporting process (centralized and distributed components) | Develop change management process for maintaining SOX-level control documentation | Manuel Munoz | 2015-09-30 | No | Coordinate with internal controls (dependency) | 2015-09-30 | [8 empty] | Medium | Medium | No | Delivery Risk: Comprehensive cross-functional participation, expertise in documentation
Finance Transformation | Accounting, Tax, & Reporting | Improve efficiency of Regulatory Report production (Incorporate all legacy systems not completed as part of the original FRS implementation). | Enhance FRS | Sean Mulcahy | 2015-12-31 | Yes | Enhance FRS: Complete Analysis | Completed | Enhance FRS: Complete Design | 2015-06-30 | Enhance FRS: Complete Development | 2015-09-30 | Enhance FRS: Complete Testing | 2015-10-31 | Enhance FRS: Complete UAT | 2015-12-31 | High | High | Yes | Need internal or consulting resources. Delivery Risk: IT Execution
Finance Transformation | Accounting, Tax, & Reporting | Implement an industry standard spreadsheet control tool to address critical End User Application gaps at SHUSA and SBNA/SCUSA subsidiaries | Complete inventory of all SHUSA (SBNA/SCUSA) critical EUAs | John Moore | 2015-06-30 | Yes | [10 empty] | High | High | No | Delivery Risk: Bandwidth for completing large breadth of work
Finance Transformation | Accounting, Tax, & Reporting | Implement an industry standard spreadsheet control tool to address critical End User Application gaps at SHUSA and SBNA/SCUSA subsidiaries | Risk-rate inventory and establish prioritized plan for compliance | John Moore | 2015-07-31 | Yes | [10 empty] | High | High | No | Delivery Risk: Bandwidth for completing large breadth of work
Finance Transformation | Accounting, Tax, & Reporting | Implement an industry standard spreadsheet control tool to address critical End User Application gaps at SHUSA and SBNA/SCUSA subsidiaries | Remediate all critical EUAs | John Moore | 2015-12-31 | Yes | [10 empty] | High | High | No | Delivery Risk: Bandwidth for completing large breadth of work
Finance Transformation | Accounting, Tax, & Reporting | Report Group Results on Business Day 4 | Current State Assessment | Mike Boyle | Completed | No | Develop Data Flows (of pain points) from source to report | Completed | [8 empty] | Medium | Medium | No | completed
Finance Transformation | Accounting, Tax, & Reporting | Report Group Results on Business Day 4 | Conduct Quality Gap Assessment | Mike Boyle | Completed | No | Document areas of deficiency | Completed | [8 empty] | Medium | Medium | No | completed
Finance Transformation | Accounting, Tax, & Reporting | Report Group Results on Business Day 4 | Develop Recommendations | Mike Boyle | Completed | No | Develop recommendations to address areas of deficiency | Completed | [8 empty] | Medium | Medium | No | completed
Finance Transformation | Accounting, Tax, & Reporting | Report Group Results on Business Day 4 | Prioritize Data Areas | Mike Boyle | Completed | No | Prioritize remediation of deficiencies | Completed | [8 empty] | Medium | Medium | No | completed
Finance Transformation | Accounting, Tax, & Reporting | Report Group Results on Business Day 4 | Develop Roadmap for Remediation | Mike Boyle | 2015-05-31 | No | Develop schedule for remediation | 2015-05-31 | [8 empty] | Medium | Medium | Yes | Need risk resources
Finance Transformation | Accounting, Tax, & Reporting | Report Group Results on Business Day 4 | Change Approach to source data | Mike Boyle | 2015-12-31 | Yes | Revised approach to data sourcing | 2015-12-31 | [8 empty] | Medium | Medium | Yes | Need IT and risk resources
Finance Transformation | Accounting, Tax, & Reporting | Improve the quality of information in the general ledger needed to complete the chart of accounts and execute reporting | Hyperion Implementation | Nancy Reinhard | 2015-11-06 | Yes
Finance Transformation | Accounting, Tax, & Reporting | Improve the amount of general ledger information available from direct system feeds rather than manual processes | RDA | Ignacio Garijo Garde | TBD | Yes | Inventory Manual Processes (SBNA) | TBD | Prioritize Processes Changes | TBD | Develop Schedule to Remediate | 2015-05-31 | Develop System Feeds | 2015-12-31
Finance Transformation | Accounting, Tax, & Reporting | Deployment of a uniform reconciliation tool (SHUSA and subsidiaries) | Efficient accumulation of reconcilement information with an automated tool. | John Moore | 2015-12-31 | Yes | Evaluate and select the appropriate reconciliation tool | 2015-08-31 | Develop schedule and plan for SBNA deployment | 2015-08-31 | Install tool for SBNA | 2015-12-31 | Develop schedule and plan for other entity deployments | 2015-12-31
Finance Transformation | Accounting, Tax, & Reporting | Finalize the implementation of Target Operating Model | Target Operating Model | Ken Goldman | 2015-12-31 | No | Complete Definition of Target Operating Model | 2015-12-31 | [8 empty] | Low | Low | No
Finance Transformation | Accounting, Tax, & Reporting | Uniform application of accounting policies across subsidiaries (was part of IHC plan) | Apply accounting policies to SHUSA | Jessie Velazquez | 2015-12-31 | No | Procedures revised at SHUSA | 2015-10-01 | Approved by appropriate governance | 2015-10-31 | Staff trained in revised procedures at SHUSA | 2015-11-30 |  |  |  |  | Medium | Medium | Yes | May need resources to review and revise policies.
Finance Transformation | Accounting, Tax, & Reporting | Uniform application of accounting policies across subsidiaries (was part of IHC plan) | Apply accounting policies to SBNA | M Ballenger | 2015-12-31 | No | Procedures revised at SBNA | 2015-10-01 | Approved by appropriate governance | 2015-10-31 | Staff trained in revised procedures at SBNA | 2015-11-30 |  |  |  |  | Medium | Medium | Yes | May need resources to review and revise policies.
Finance Transformation | Accounting, Tax, & Reporting | Uniform application of accounting policies across subsidiaries (was part of IHC plan) | Apply accounting policies to SCUSA | J Kulas | 2015-12-31 | No | Procedures revised at SCUSA | 2015-10-01 | Approved by appropriate governance | 2015-10-31 | Staff trained in revised procedures at SCUSA | 2015-11-30 |  |  |  |  | Medium | Medium | Yes | May need resources to review and revise policies.
Finance Transformation | Accounting, Tax, & Reporting | Uniform application of accounting policies across subsidiaries (was part of IHC plan) | Apply accounting policies to BSI | E Franco Espinosa | 2015-12-31 | No | Procedures revised at BSOI | 2015-10-01 | Approved by appropriate governance | 2015-10-31 | Staff trained in revised procedures at BSI | 2015-11-30 |  |  |  |  | Medium | Medium | Yes | May need resources to review and revise policies.
Finance Transformation | Accounting, Tax, & Reporting | Uniform application of accounting policies across subsidiaries (was part of IHC plan) | Apply accounting policies to PR | A. Guzman | 2015-12-31 | No | Procedures revised at PR | 2015-10-01 | Approved by appropriate governance | 2015-10-31 | Staff trained in revised procedures at PR | 2015-11-30 |  |  |  |  | Medium | Medium | Yes | May need resources to review and revise policies.
Finance Transformation | Accounting, Tax, & Reporting | Uniform application of accounting policies across subsidiaries (was part of IHC plan) | Apply accounting policies to SIS | F. Sempre | 2015-12-31 | No | Procedures revised at SIS | 2015-10-01 | Approved by appropriate governance | 2015-10-31 | Staff trained in revised procedures at SIS | 2015-11-30 |  |  |  |  | Medium | Medium | Yes | May need resources to review and revise policies.
Finance Transformation | Accounting, Tax, & Reporting | Uniform application of accounting policies across subsidiaries (was part of IHC plan) | Apply accounting policies to Other Entities | Jessie Velazquez | 2015-12-31 | No | Procedures revised at Other Entities | 2015-10-01 | Approved by appropriate governance | 2015-10-31 | Staff trained in revised procedures at Other Entities | 2015-11-30 |  |  |  |  | Medium | Medium | Yes | May need resources to review and revise policies.
Finance Transformation | Capital Management | Enhance capital policy and capital contingency policy to address FRS and IA feedback, satisfying ROPE and CCAR capital goals requirement | Enhance SHUSA Capital policy | Bart Simon | 2015-12-30 | No | Capital goals and targets methodology document - At sub level ID and quant critical stakeholder requirements in stress - Enhance study of experience in stress - Determine capital goals at each sub & analysis impact of changes at subs on SHUSA - Risk Inventory from Risk ID w/ quant source - Roles & Responsibilities | 2015-09-15 | Capital assessment methodology document - Enhance doc of process & responsibilities & deliverables - ID specific analysis (ratios, changes in biz profile, strategic initiatives, risk tolerance metrics, etc.) required for assessment - Develop draft of capital assessment report (companion to current deck) | 2015-09-05 | Dividend and capital action methodology document - ID all metrics and analysis required to develop 'capital triggers' - Compile data required for analysis of indicators that could drive changes to capital actions - Determine roles & responsibilities for analysis - Determine governance/communication expectations | TBD | Incorporate all new methodology / enhancements into Policy Admin reviewed Capital Policy | 2015-12-30 |  |  | Medium | Low | No
Finance Transformation | Capital Management | Enhance capital policy and capital contingency policy to address FRS and IA feedback, satisfying ROPE and CCAR capital goals requirement | Enhance SHUSA Capital contingency policy | Bart Simon | 2015-12-05 | No | Incorporate FRS and IA feedback into existing draft policy - Align capital contingency process with updated capital policy methodology documents - Include 'capital triggers' analysis | 2015-11-30 | Develop appropriate governance over capital contingency process across entities. | 2015-12-02 | Deliver contingency policy to policy admin | 2015-11-30 | Complete policy and approval governance process | 2015-12-05 |  |  | Medium | Low | No
Finance Transformation | Capital Management | Enhance capital policy and capital contingency policy to address FRS and IA feedback, satisfying ROPE and CCAR capital goals requirement | Capital Policies for subs (SBNA, SCUSA and IHCs) commensurate with size / complexity | Bart Simon | 2015-12-31 | No | Establish capital management governance structure at each entity | TBD | Capital goals and targets methodology document - ID and quant critical stakeholder requirements in stress - Enhance study of experience in stress - Risk Inventory from Risk ID w/ quant source - Roles & Responsibilities | 2015-09-05 | Dividend and capital action methodology document - ID all metrics and analysis required to develop 'capital triggers' - Compile data required for analysis of indicators that could drive changes to capital actions - Determine roles & responsibilities for analysis - Determine governance/communication expectations | TBD | Develop early warning indicators | 2015-05-15 | Define individual entity roles & responsibilities | TBD | Medium | Medium | Yes
Finance Transformation | Capital Management | Operationalize processes for escalation to board, potential suspension of capital actions, and implementation of contingency plans (improve analysis and documentation of contingency actions) | Enhance/Update Contingent Capital Plan | Bart Simon | 2016-04-05 | No | Re-define process for which contingent actions are identified, quantified and assessed | 2015-10-15 | Update inventory of potential contingent capital actions | 2015-10-30 | Align potential contingent capital actions with liquidity, strategic planning, & resolution planning (dependencies…) | 2015-10-15 | Quantify potential contingent capital actions | 2016-03-20 | Board Approval of contingent capital plan | 2016-04-05 | Medium | Low | No
Finance Transformation | Capital Management | Enhance capital adequacy and capital planning governance | Improved quality of information presented | Simon / Watson | TBD | No | Establish team for template creation and population | TBD | Create common templates | TBD | Develop process for review of content prior to presentation | TBD |  |  |  |  | High | High | Yes
Finance Transformation | Capital Management | Enhance capital adequacy and capital planning governance | Improve completeness of info presented | Simon / Watson | TBD | No | Review final structures to determine 'new' reporting expectations and locations | TBD | Develop full inventory of models and processes for review | TBD | Develop full inventory of results for review | TBD | Schedule and track review of inventories at appropriate level of governance body | TBD |  |  | Low | Medium | No
Finance Transformation | Capital Management | Enhance capital adequacy and capital planning governance | Add clarity to material provided for consideration of dividend | Bart Simon | TBD | No | See SHUSA Capital Policy for details | TBD
Finance Transformation | Capital Management | Enhance capital adequacy and capital planning governance | Enhance Board and Snr. Management Training | Simon / Watson | TBD | No | Outline required training at Board and Senior Management | TBD | Schedule training | TBD | Determine training provider (internal / external) | TBD |  |  |  |  | Low | Low | Yes
Finance Transformation | Capital Management | Enhance capital adequacy and capital planning governance | Detailed Procedures for E2E processes | Bart Simon | TBD | No | Determine review governance / review process for E2E procedures | TBD | Confirm E2E process map owners and responsibilities for procedures | TBD | First draft of procedures for all E2E process steps | TBD | Central review of draft procedures | TBD |  |  | High | Medium | Yes
Finance Transformation | Capital Management | Enhance capital adequacy and capital planning governance | Accountability | TBD | TBD | No | This needs to be part of the 'bigger' Governance discussion. | TBD
Finance Transformation | Capital Management | Establish staffing and conduct adequate training across the end-to-end CCAR review cycle | Establish Staffing & Conduct Training - TBD | TBD | TBD | No
Finance Transformation | Capital Management | Develop clear linkage between Risk ID and scenario generation and develop BHC specific scenarios | Risk ID output that satisfies requirements for the scenario-design and scenario-selection processes in CCAR/DFAST. | Risk ID | 2015-10-31 | No | First Line of Defense creates Business Segment Inventories | 2015-06-30 | Second Line of Defense Aggregates Business Entity Inventories | 2015-07-31 | Aggregation of SHUSA-level Inventory with Top-Down Analysis | 2015-10-31
Finance Transformation | Capital Management | Develop clear linkage between Risk ID and scenario generation and develop BHC specific scenarios | Presentation of a suite of scenarios to Management and Board Capital Committees for formal selection and approval of the scenarios to be used in CCAR/DFAST | John Barris | 2015-12-31 | No | Receive SHUSA-level Risk ID Inventory & Assessment | 2015-10-31 | Receive SHUSA-level Risk ID Inventory & Assessment | 2015-11-13 | Capital Management recommends Idiosyncratic Narratives to Management CC | 2015-11-18 | Capital Management recommends Idiosyncratic Narratives to Board CC | 2015-12-01 | Capital Management works with BU and Risk stakeholder to parameterize suite of multiple scenarios | 2015-12-18 | Medium | Medium | No
Finance Transformation | Capital Management | Develop clear linkage between Risk ID and scenario generation and develop BHC specific scenarios | Stand-alone policies and procedures that govern the scenario-design and scenario-selection processes, with each formally approved at the Management and Board Capital Committees. | John Barris | 2016-03-31 | No | First Draft of Policy & Procedure Documentation reviewed by CCAR Director | 2015-10-31 | Policy & Procedure Documentation reviewed by Ex&Agg | 2015-11-06 | Policy & Procedure Documentation reviewed by Management CC | 2015-11-11 | Policy & Procedure Documentation reviewed by Board CC | 2015-12-01 | Policy & Procedure Documentation updated to reflect actual CCAR 2016 process | 2016-01-31 | Low | Low | No
Finance Transformation | Capital Management | Develop clear linkage between Risk ID and scenario generation and develop BHC specific scenarios | BHC scenarios will have Actual macroeconomic data aligned across all scenarios. | John Barris | 2016-01-31 | No | Presentation of a suite of scenarios to Management and Board Capital Committees for formal selection and approval of the scenarios to be used in CCAR/DFAST | 2015-12-31 | Receive FRB Scenarios from FRB | 2015-01-22 | Align BHC Scenario Actuals with FRB Scenarios | 2015-01-31 |  |  |  |  | Low | Low | No
Finance Transformation | Capital Management | Develop granular forecast of baseline and stress scenarios to test capital adequacy, incorporating IHC entities | Establish set of reconciled as-of and clean historical data | IT/IMAD | TBD | Yes | Complete gap assessment against data quality | TBD | Develop remediation plan to close prioritized gaps | TBD | Execute remediation plan to close prioritized gaps | TBD | Operationalize source system(s) for 2016 CCAR Run | TBD
Finance Transformation | Capital Management | Develop granular forecast of baseline and stress scenarios to test capital adequacy, incorporating IHC entities | Develop end-to-end stress-testing platform | TBD | TBD | Yes | Develop BHC specific Scenarios that are clearly linked to the RISK ID process and that are BHC specific | TBD | Develop model execution platform (for PPNR, Credit Loss, etc.) | TBD | Develop SAS balance-walk engine | TBD | Develop integration of IHC data | TBD | Develop ability to consolidate SHUSA IHC information | TBD
Finance Transformation | Capital Management | Develop granular forecast of baseline and stress scenarios to test capital adequacy, incorporating IHC entities | Base and stress forecasts for each IHC entity | TBD | TBD | No | Communicate modeling strategy | TBD | Develop forecasting processes for non-modeled line-items (PPNR) | TBD | Develop forecasting processes for non-modeled line-items (Credit) | TBD | Develop supporting documentation | TBD | Internal Control review of process (IC, IA, MRM, etc.) | TBD
Finance Transformation | Capital Management | Enhance the structure, transparency, and control of the process that produces capital forecasts, including validated models and assumptions, to ensure capital levels meet policy thresholds/ limits under normal and stressful conditions (where stressed conditions are specific to the BHC) | Detailed E2E processes maps | Bart Simon | TBD | No | Build team for compilation of E2E process maps | TBD | Process owners deliver individual maps | TBD | Aggregation and review of full process maps | TBD | Approval of full process maps / full process | TBD |  |  | High | Medium | Yes
Finance Transformation | Capital Management | Enhance the structure, transparency, and control of the process that produces capital forecasts, including validated models and assumptions, to ensure capital levels meet policy thresholds/ limits under normal and stressful conditions (where stressed conditions are specific to the BHC) | Comprehensive Assessment from Internal Audit | Vik Soni | TBD | No
Finance Transformation | Capital Management | Enhance the structure, transparency, and control of the process that produces capital forecasts, including validated models and assumptions, to ensure capital levels meet policy thresholds/ limits under normal and stressful conditions (where stressed conditions are specific to the BHC) | Comprehensive Assessment from Internal Controls | M. Munoz | TBD | No
Finance Transformation | Capital Management | Enhance the structure, transparency, and control of the process that produces capital forecasts, including validated models and assumptions, to ensure capital levels meet policy thresholds/ limits under normal and stressful conditions (where stressed conditions are specific to the BHC) | Model Validation / MRM | TBD | TBD | No
Finance Transformation | Capital Management | Define and approve process for calculating RWA with appropriate governance, controls, and supporting documentation of RWA calculations, process and methodologies | Increase the granularity of forecasting of on and off balance sheet product level information. This process will be extended to include all material IHCs for CCAR 2016 inclusion | John Barris | 2016-04-04 | No | Management Control/Strategic Planning build out SAS forecasting models | 2015-09-30 | SAS Models validated | 2015-12-31 | GAP level of forecasts with RWA needed levels | 2015-10-30 | Develop any methodologies or assumptions for gaps and obtain governance approvals | 2015-12-31 |  |  | Medium | Low | No
Finance Transformation | Capital Management | Define and approve process for calculating RWA with appropriate governance, controls, and supporting documentation of RWA calculations, process and methodologies | Finalization of the Basel III methodology that is approved and fully documented and Forecasting methodology that is consistent with the final approved SHUSA Basel III methodology | John Barris | 2015-07-06 | No | RCRD/Accounting to produce final Basel III methodology for numerator and denominator | 2015-04-01 | CPG to incorporate final Basel III methodology into forecasting | 2015-07-06 | Update forecasting documentation obtain final approval | 2015-07-06 |  |  |  |  | Medium | Medium | No | completed,
Finance Transformation | Capital Management | Define and approve process for calculating RWA with appropriate governance, controls, and supporting documentation of RWA calculations, process and methodologies | Internal Audit to review the RWA methodology for both actuals and forecasts for CCAR 2016 | John Barris | 2015-12-31 | No | Review of Actual methodology for RWA | 2015-06-01 | Review of forecasting methodology for Forecasting | 2015-12-31 | [6 empty] | Low | Low | No
Finance Transformation | Capital Management | Define and approve process for calculating RWA with appropriate governance, controls, and supporting documentation of RWA calculations, process and methodologies | RWA methodology will be well documented and all assumptions will be approved by the appropriate governance committees prior to use, including validated SSFA methodology developed and run by 3rd party external vendor | John Barris | 2015-12-31 | No | Obtain approval for SSFA 3rd Party Vendor | 2015-07-31 | Vendor to develop methodology with CPG | 2015-09-30 | MRM to validate SSFA models | 2015-12-31 | Provide Cusips and produce results | 2016-03-01 |  |  | High | High | Yes
Finance Transformation | Capital Management | Define and approve process for calculating RWA with appropriate governance, controls, and supporting documentation of RWA calculations, process and methodologies | Implement a framework for RWA sensitivity analysis and back testing for CCAR 2016 that is well documented | John Barris | 2016-04-04 | No | Develop necessary analysis and back testing needs | 2015-09-30 | Gap needs to abilities | 2015-10-30 | Develop plan for analysis and back testing for CCAR 2016 | 2015-12-31 | Document results of analysis and back testing | 2015-04-04 |  |  | High | High | No
Finance Transformation | Capital Management | Define and approve process for calculating RWA with appropriate governance, controls, and supporting documentation of RWA calculations, process and methodologies | RWA process will be reviewed and tested by internal controls for CCAR 2016 | John Barris | 2015-12-31 | No | Work with IC to produce necessary RWA control framework | 2015-07-30 | Add controls into the RWA process as outlined | 2015-12-31 | Produce RWA for CCAR 2016 | 2016-04-04 | IC to conduct control test | 2016-05-30 |  |  | Low | Low | No
Finance Transformation | Capital Management | Improve financial analysis at consolidated and legal entity view | Review of Previous Capital Plan with comments on areas for improvement | Bart Simon | TBD | No | Comments delivered to Capital Plan contributors | TBD | [8 empty] | Low | Low | No
Finance Transformation | Capital Management | Improve financial analysis at consolidated and legal entity view | Consolidated and legal entity historical results in Planning Tree delivered | TBD | TBD | Yes
Finance Transformation | Capital Management | Improve financial analysis at consolidated and legal entity view | Strategic plan at consolidated and legal entity in Planning Tree | D. Budington | TBD | Yes
Finance Transformation | Capital Management | Improve financial analysis at consolidated and legal entity view | Baseline and Stress at consolidated and legal entity in Planning Tree | John Barris | TBD | Yes | [10 empty] | High | High | Yes
Finance Transformation | Capital Management | Improve financial analysis at consolidated and legal entity view | Financial analysis in Capital Plan | John Barris | TBD | Yes | Determine roles and review expectations | TBD | Establish "team" for review | TBD | Preplan all charts graphs | TBD | Reviewed analysis in Capital Plan | TBD |  |  | Medium | Medium | Yes
Finance Transformation | Capital Management | Establish enhanced monthly capital reporting / tracking | Develop / Enhance Monthly Report | John Barris | TBD | No | Gap Current Report to Management Needs | TBD | Develop remediation plan for executions | TBD | Develop draft report for approval | TBD
Finance Transformation | Capital Management | Establish enhanced monthly capital reporting / tracking | Align to GL and RCRD | John Barris | TBD | Yes | Integrate Proforma forecast for monthly cycle | 2015-04-01 | Align to GL through Essbase | TBD | [9 empty] | completed
Finance Transformation | Capital Management | Establish enhanced monthly capital reporting / tracking | Enhance with Current Capital LOB Allocations | John Barris | TBD | No | Integrate LOB allocations into report | TBD
Finance Transformation | Capital Management | Establish enhanced monthly capital reporting / tracking | Develop forecasting ability with Stress overlays | John Barris | TBD | No | Develop process to use monthly actuals to true up forecast | TBD | Develop methodology to overlay CCAR/Mid Cycle stress impacts | TBD | Finalize Reporting format and governance approval | TBD
Finance Transformation | Capital Management | Fully operationalize quarterly capital adequacy assessment with senior-level decision-making rooted in credit considerations, market expectations, and regulatory requirements | Quarterly Decks for MCC | Bart Simon | 2016-04-06 | No | Q1 Deck | 2015-06-25 | Q2 Deck | 2015-09-25 | Q3 Deck | 2015-12-25 | Q4 Deck = 2016 Capital Plan | 2016-04-06 |  |  | Low | Low | No
Finance Transformation | Capital Management | Fully operationalize quarterly capital adequacy assessment with senior-level decision-making rooted in credit considerations, market expectations, and regulatory requirements | Quarterly Report for Board | Bart Simon | TBD | No | Define report structure, details and delivery mechanism | TBD | Define roles and responsibilities for compilation | TBD | Report included in quarterly Board Package | TBD |  |  |  |  | Medium | High | No
Finance Transformation | Capital Management | Enhance Capital Plan for 2016 | Review 2014 Capital Plan | Bart Simon | 2015-06-01 | No | CMG Review of Previous Capital Plan | 2015-06-01 | Incorporate FRS Feedback of Previous Capital Plan | 2015-06-01 | [6 empty] | High | Low | No
Finance Transformation | Capital Management | Enhance Capital Plan for 2016 | Align results & methodology presentation with 'new' segmentation | Bart Simon | 2015-09-30 | Yes | Define revised presentation tables | 2015-09-30 | [8 empty] | High | High | No
Finance Transformation | Capital Management | Enhance Capital Plan for 2016 | IHC Capital Plan | Bart Simon | 2015-07-31 | No | Create Project Plan for each entity: SBNA, SCUSA, Miami, NY, Puerto Rico | 2015-07-31 | [8 empty] | High | High | Yes
Finance Transformation | Capital Management | Enhance Capital Plan for 2016 | Methodology Appendix for Capital Plan | Contributors | 2015-12-31 | No | Contributors Draft/Revise Methodology Sections | 2015-08-01 | Improve existing summary documentation in Capital Plan in workiva per ROPE | 2015-08-01 | Review Team - Capital Management, Working Groups, Peer Review | 2015-12-31 |  |  |  |  | High | Low | No
Finance Transformation | Capital Management | Enhance Capital Plan for 2016 | Results for CCAR Run | Contributors | 2016-03-20 | No | Contributors Draft/Update Results for CCAR Run | 2016-03-10 | Improve existing summary documentation in Capital Plan in workiva per ROPE | 2016-03-10 | Review Team - Capital Management, Working Groups, Peer Review | 2016-03-30 |  |  |  |  | High | Medium | Yes
Finance Transformation | Capital Management | Enhance Capital Plan for 2016 | Enhance Capital Plan Documentation | Bart Simon | 2016-03-20 | No | Improve automation / linkage to wDesk | 2016-03-20 | Improve summary documentation in Capital Plan in workiva per ROPE | 2016-03-20 | [6 empty] | High | Medium | Yes
Finance Transformation | Capital Management | Develop and assess future-focused alternative capital actions, ensuring full transparency of capital ratios relative to binding limits, to present to Board | Procedures for developing and review of alternative capital actions | Bart Simon | TBD | No | Determine Roles & Responsibilities | TBD | Determine Governance | TBD | [6 empty] | Low | Low | No
Finance Transformation | Capital Management | Develop and assess future-focused alternative capital actions, ensuring full transparency of capital ratios relative to binding limits, to present to Board | Alternative Capital Actions | Bart Simon | TBD | No | Execute process to develop alternative capital actions | TBD | Review alternative actions w/ appropriate governance bodies | TBD | Include alternative actions in 2016 Capital Plan | TBD |  |  |  |  | Low | Low | No
Risk Transformation |  | Re-design RAS for SHUSA enterprise | SHUSA Board-level Risk Appetite Statement −Risk appetite statements for most material risks (considering most recent enterprise strategy) −List of metrics and calibrated limits that define quantifiable RA statements -Draft the SHUSA RAS reporting process, breach escalation process and breach penalty mechanism | Edward Smith | 2015-08-10 | Yes | Draft RAS |  | Final RAS |  | Draft process |  | Final process |  |  |  | High | Low | Yes
Risk Transformation |  | Re-design RAS for SHUSA enterprise | Delivery of RAS training to Board (materials drafted in Board Risk Committee training project), includes: - Overview of new RAS structure and metrics - Board roles and responsibilities with respect to RAS | Edward Smith | 2015-08-31 | No | Delivery of training | [9 empty] | Medium | Low | Yes
Risk Transformation |  | Re-design RAS for SHUSA enterprise | Board-approved SHUSA RAS and reporting process | Edward Smith | 2015-09-07 | No | Board approval | [9 empty] | Low | Low | Yes
Risk Transformation |  | Re-design RAS for SHUSA enterprise | Delivery of Board-level RAS communication and socialization materials to the Enterprise e.g. emails, townhalls | Edward Smith | 2015-09-29 | No | Draft of materials |  | Final materials and delivery of communication | [7 empty] | Medium | Low | Yes
Risk Transformation |  | Re-design RAS for SHUSA enterprise | Defined RAS business and data requirements, communicated to T&O | Edward Smith | 2015-09-29 | Yes | Draft BRD |  | Final BRD and communication to T&O | [7 empty] | Low | Low | No
Risk Transformation |  | Cascade RAS to priority subsidiaries | Define approach to cascading SHUSA level Risk Appetite Statement to subsidiaries and levels below | Edward Smith | 2015-08-24 | No | Draft approach |  | Final approach | [7 empty] | Medium | Low | Yes
Risk Transformation |  | Cascade RAS to priority subsidiaries | Risk Appetite Statements for priority subsidiaries i.e. SBNA and SCUSA (aligned with overall SHUSA RAS) −Risk appetite statements for most material risks −List of metrics and calibrated limits | Edward Smith | 2015-10-05 | Yes | Draft RAS for priority subs and list of metrics |  | Input from subs |  | Final RAS for priority subs and list of metrics | [5 empty] | High | Low | Yes
Risk Transformation |  | Cascade RAS to priority subsidiaries | RAS escalation and reporting process (cascaded version), including definition of consequences for RAS limit breaches and more detailed RAS limits | Edward Smith | 2015-09-21 | No | Draft process |  | Final process | [7 empty] | Medium | Low | Yes
Risk Transformation |  | Cascade RAS to priority subsidiaries | Board-approved RAS for priority subsidiaries | Edward Smith | 2015-10-05 | No | Board approval | [9 empty] | Low | Low | Yes
Risk Transformation |  | Board Risk Committee Training | Development of risk training curriculum and schedule for the Board Risk committee: −Training materials [for first 2 sessions, including RAS training] −Detailed risk training objectives | John Hennessey | 2015-07-27 | No | Draft of training materials, including training schedule |  | Final training materials, including training schedule |  | Delivery of two training sessions | [5 empty] | Medium | Low | Yes
Risk Transformation |  | Formalize engagement model between SHUSA and Parent Group | Established governance and coordination mechanisms within Group (i.e. engagement model in terms of linkage between SHUSA and Parent Group committees, etc.) | John Hennessey | 2015-07-27 | No | Key stakeholder engagement |  | Draft governance and coordination mechanisms |  | Final governance and coordination mechanisms | [5 empty] | High | Medium | Yes
Risk Transformation |  | Formalize engagement model between SHUSA and Parent Group | Board-approved governance and coordination mechanisms | John Hennessey | 2015-08-10 | No | Board approval | [9 empty] | Low | Low | Yes
Risk Transformation |  | Formalize engagement model between SHUSA and Parent Group | Group-approved governance and coordination mechanisms | John Hennessey | TBD | No | Group approval | [9 empty] | Medium | Medium | Yes
Risk Transformation |  | Strengthen SHUSA Board and Management Committee guidance | Diagnostic of Risk Management Committee oversight effectiveness over SHUSA subsidiaries | John Hennessey | 2015-06-29 | No | Draft of diagnostic materials |  | Final materials and delivery of diagnostic | [7 empty] | Medium | Low | Yes
Risk Transformation |  | Strengthen SHUSA Board and Management Committee guidance | Updated committee composition, mandates, and charters for priority committees (Board level and Management Committees [Level 1]): −Review enterprise committee suite/structure −Identify and execute necessary changes to high priority committee composition, mandates, processes, charters | John Hennessey | 2015-07-27 | No | Draft of committee composition, mandates, and charters |  | Final committee composition, mandates, and charters | [7 empty] | High | Medium | Yes
Risk Transformation |  | Strengthen SHUSA Board and Management Committee guidance | Board-approved committee compositions, mandates and charters (Board level and Management Committees (Level 1)) | John Hennessey | 2015-08-10 | No | Board approval | [9 empty] | Low | Low | Yes
Risk Transformation |  | Strengthen SHUSA Board and Management Committee guidance | Updated committee composition, mandates, and charters for remaining committees (Management Committees [Level 2], Sub-Committees) | John Hennessey | 2015-09-07 | No | Draft of committee composition, mandates, and charters |  | Final committee composition, mandates, and charters | [7 empty] | High | Medium | Yes
Risk Transformation |  | Strengthen SHUSA Board and Management Committee guidance | Board-approved committee compositions, mandates and charters (Management Committees (Level 2), Sub-Committees) | John Hennessey | 2015-10-05 | No | Board approval | [9 empty] | Low | Low | Yes
Risk Transformation |  | Recruit priority staff | Recruitment of senior Risk leadership staff where gaps exist | Kerrie Maitland | 2015-08-24 | No | Identification of open positions |  | Engagement with HR |  | Recruitment rounds |  | Hiring of positions |  |  |  | High | High | No
Risk Transformation |  | Recruit priority staff | Recruitment of other priority staff where gaps exist e.g. model validators | Kerrie Maitland | 2015-08-24 | No | Identification of open positions |  | Engagement with HR |  | Recruitment rounds |  | Hiring of positions |  |  |  | High | High | No
Risk Transformation |  | Design risk management organizational structure in accordance with 3LoD principles | Articulation and formalization of 3LOD principles | John Hennessy | 2015-06-15 | No | Draft 3LoD principles |  | Final 3LoD principles | [7 empty] | Low | Low | Yes
Risk Transformation |  | Design risk management organizational structure in accordance with 3LoD principles | Definition and formalization of reporting lines at the C-Suite: - Articulation of reporting lines and implications e.g. centralized risk function, 'double-hatting' of roles | John Hennessy | 2015-07-13 | No | Draft reporting lines |  | Key stakeholder engagement |  | Final (formalization of) reporting lines | [5 empty] | Low | Low | Yes
Risk Transformation |  | Design risk management organizational structure in accordance with 3LoD principles | Board-approved C-Suite reporting lines | John Hennessy | 2015-08-10 | No | Board approval | [9 empty] | Medium | Low | Yes
Risk Transformation |  | Design risk management organizational structure in accordance with 3LoD principles | Detailed operating model design aligned with 3LoD principles: -Future risk operating model design for SHUSA / subsidiaries -Design of organizational structure for each Risk type in each subsidiary (aligned with 3LoD) -Designation of roles and responsibilities and senior job descriptions | John Hennessy | 2015-07-27 | No | Draft of operating model |  | Final operating model | [7 empty] | High | Medium | Yes
Risk Transformation |  | Design risk management organizational structure in accordance with 3LoD principles | Headcount analysis aligned with updated operating model design: -Includes determination of FTE at all levels of the enterprise (across all 3 LoD) -Skills / staffing assessment to identify additional staffing needs or changes | John Hennessy | 2015-09-21 | No | Draft headcount |  | Delivery of skills / staffing assessment |  | Hiring / redeployment strategy | [5 empty] | High | Medium | Yes
Risk Transformation |  | Implementation of risk management organizational structure in accordance with 3LoD principles | Roll-out of new operating model, in terms of: -Communications -Development and delivery of materials to convey organizational changes to enterprise -Enterprise-wide training and development of job descriptions (link to execution of Talent Management Strategy) with explicit focus on 3LOD -Embedded structure with all roles and responsibilities filled | John Hennessy | TBD | No | Draft of communication and training materials for enterprise-wide communication |  | Delivery of final communication and training materials for enterprise-wide communication |  | Development of job descriptions |  | Delivery of enterprise-wide training |  |  |  | High | Medium | Yes
Risk Transformation |  | Improve effectiveness of policies and procedures | Frameworks designed and approved across all risk types (continuation of in-flight project for following frameworks: ERM, Credit Risk, Market / Liquidity Risk, Operational Risk) | John Hennessy | 2015-06-29 | No | Validation of updated frameworks | [9 empty] | Low | Low | No
Risk Transformation |  | Improve effectiveness of policies and procedures | Board-approved frameworks | John Hennessy | 2015-07-13 | No | Board approval | [9 empty] | Low | Low | No
Risk Transformation |  | Improve effectiveness of policies and procedures | Assessment of existing enterprise-wide policies and procedures, and prioritization of improvement actions, including: -Ongoing work regarding policy templates, administration and standards -Coordination with other Management Committees to determine ownership of and “hand-off” points for enhancements -Review of policy attestation process and linkage to Senior Management incentives -Ensure standardization across all policies/procedures | John Hennessy | TBD | No | Draft of assessment |  | Delivery of assessment |  | Prioritization of enhancements |  | Final plan for enhancements, given stakeholder input |  | Standardization of all policies / procedures |  | Medium | Low | No
Risk Transformation |  | Enhance risk identification and assessment process | Completed definition of the risk ID and assessment process and execution: −Process maps −Tools/templates | Edward Smith / Diane Allaire | 2015-06-15 | Yes | Draft definition of risk ID/assessment process and plan for execution |  | Final definition of risk ID/assessment process and plan for execution |  | Communication to key stakeholders | [5 empty] | Low | Medium | No
Risk Transformation |  | Enhance risk identification and assessment process | Board-approved risk ID and assessment program | Edward Smith / Diane Allaire | 2015-07-13 | No | Board approval | [9 empty] | Low | Low | No
Risk Transformation |  | Enhance risk identification and assessment process | Register of risks, encompassing both modeled and non-modeled risks across all relevant legal entities / BUs: −Informed by existing Operational Risk, Compliance, and Audit frameworks as possible | Edward Smith / Diane Allaire | 2015-08-10 | Yes | Conduct bottom-up risk identification |  | Aggregate, review & challenge |  | Conduct top-down risk identification |  | Draft of risk register |  | Final risk register |  | High | High | Yes
Risk Transformation |  | Enhance risk identification and assessment process | Policy/procedure for Risk Identification and Assessment cycle (specifying frequency, stakeholders, duration, approvals, management / mitigation actions, updates to RAS, etc.) | Edward Smith / Diane Allaire | 2015-07-27 | No | Draft policy and procedures for risk ID and assessment cycle |  | Final policy and procedures for risk ID and assessment cycle |  | Communication of policies/procedures to key stakeholders | [5 empty] | Medium | Low | No
Risk Transformation |  | Enhance risk identification and assessment process | Defined business and data requirements for enhanced risk identification and assessment process | Edward Smith / Diane Allaire | 2015-09-07 | Yes | Draft BRD |  | Final BRD and communication to T&O | [7 empty] | Low | Medium | No
Risk Transformation |  | Conduct high level credit risk review and deliver quick wins | High level review and revision of wholesale credit process limits / controls and delegation of authority (potential quick win) at SHUSA and SBNA | TBD | 2015-10-05 | No | Proposed recommendations |  | Approved recommendations |  | Updated Credit Policy | [5 empty] | Medium | Medium | Yes
Risk Transformation |  | Create IRR and Liquidity Risk framework | High level review of key IRR and liquidity risk assumptions and parameters, including: governance, metrics and reporting to manage liquidity and IRR risk | TBD | 2015-09-21 | No | Draft framework |  | Final framework | [7 empty] | Medium | Medium | Yes
Risk Transformation |  | Conduct liquidity risk gap analysis | Definition of liquidity risk capabilities across Treasury, Risk, including areas identified in “tasks” and evaluation of current state against capabilities and remediation plan | TBD | 2015-10-05 | No | Definition of liquidity risk capabilities |  | Current state vs. capabilities |  | Remediation plan | [5 empty] | Medium | Medium | Yes
Risk Transformation |  | Conduct Reputational / Strategic Risk Management Framework Review | Review of the Reputational/Strategic Risk Management Framework: −Review existing reputational and strategic risk lists, determine link with other major risk types (liquidity risk, op risk, etc.) −Conduct structured workshops to narrow down top risks −Translate top risk triggers into scenarios and leverage expert opinion to assess impacts −Evaluate mitigating actions and implement necessary controls -Define business and data requirements and communicate to T&O | John Hennessey | 2015-09-12 | No | Initial review of risks |  | Scenario and impact analysis |  | Remediation plan |  | Business and data requirements |  |  |  | TBD | TBD | Yes
Risk Transformation |  | Conduct new Product / New Business process Review | Review of the New Product / New Business Framework (with Risk participation) - Review roles and responsibilities -Design tools to make process systematic (e.g. risk assessment templates) −Define decision authority mechanism -Define business and data requirements and communicate to T&O | TBD | 2015-09-12 | No | Initial review of framework |  | Process and associated tools |  | Documented decision authority |  | Business and data requirements |  |  |  | TBD | TBD | Yes
Risk Transformation |  | Enhance internal reporting | Risk reporting landscape, by audience and risk type −Determine different audiences of risk reporting −For each audience outline essential content and frequency of reporting | Edward Smith | 2015-07-27 | No | Risk reporting landscape outline | [9 empty] | Low | Low | Yes
Risk Transformation |  | Enhance internal reporting | Prototype reports and socialization of high priority reports to: −Board −Senior management (Management Committee Level 1) | Edward Smith | 2015-09-07 | No | Board prototype reports |  | Senior management prototype reports | [7 empty] | Low | Medium | Yes
Risk Transformation |  | Enhance internal reporting | Risk data requirements for reporting: −Based on desired reporting contents and frequency, define business requirements incl. both type and frequency of data −Prioritize business requirements based on report and metric materiality -Identify risk aggregation needs to support reporting | Edward Smith | 2015-09-21 | Yes | Risk reporting data requirements - Board |  | Risk reporting data requirements - Senior Management | [7 empty] | Medium | High | Yes
Risk Transformation |  | Enhance internal reporting | Reporting resourcing: −Identify reporting groups within SHUSA and subsidiaries −Define target organizational structure for reporting groups (e.g., central aggregation team at SHUSA level) −Define resource needs to support desired reporting, both in current and future state −Train and onboard resources for reporting | Edward Smith | 2015-09-21 | No | Target org structure for reporting groups |  | Definition of reporting resource requirements |  | Training for reporting resources | [5 empty] | Low | Medium | Yes
Risk Transformation |  | Update internal monitoring process | Risk IT, RDA and IT service performance dashboard | Edward Smith | 2016-05-10 | Yes | Outlined target performance dashboard |  | Business and data requirements |  | Roadmap / plan for implementation |  | Prototype performance dashboard |  | Implemented performance dashboard |  | High | High | Yes
Risk Transformation |  | Define initial business and data requirements | Coordination and aggregation of all business and data requirements, defined for key data-related risk measurement, management, and reporting activities, including: −Information needed and business purpose −Level of aggregation / granularity −Expected provisioning frequency −Expected turn-around times for data (e.g. provided within 10 days after month-end close) -Links to individual workstream initiatives to define business and data requirements | T&O | 2015-10-19 | Yes | Stakeholder engagement |  | Draft data requirements |  | Final data requirements | [5 empty] | High | High | No
Risk Transformation |  | Define initial business and data requirements | Prioritization of data requirements, both within and across individual business requirement documents −In line with overall risk-related CART prioritization | T&O | 2015-11-23 | Yes | Data prioritization criteria |  | List of prioritized data | [7 empty] | Medium | Medium | No
Risk Transformation |  | Review current systems architecture and identify improvements | Definition of target risk data management IT architecture | T&O | 2015-08-31 | Yes | Draft target state |  | Final target state | [7 empty] | Low |  | No
Risk Transformation |  | Review current systems architecture and identify improvements | Assessment of current systems architecture and identification of required enhancements to support data needs, incorporating: −Above business requirements −BCBS 239 compliance needs −Technology solutions consistent with defined architecture | T&O | 2015-10-27 | Yes | Current systems architecture |  | Remediation plan | [7 empty] | High | Medium | No
Operational Risk | Risk Appetite | Simplify SHUSA Operational Risk Tolerance Statement Limits | Enhanced SHUSA operational risk limits implemented, monitored and reported | Sean O'Malley |  | No | A documented set of recommended enhanced operational risk limits with clear rationale, definitions and thresholds |  | SHUSA Board-approved enhanced operational risk limits and thresholds. |  | Implemented processes to effectively monitor and report on enhanced operational risk limits. | [5 empty] | High | Medium | No
Operational Risk | Risk Appetite | Align with Capital Measures described in the Basel Consultative document (Total Potential OR Losses as a % of Gross Income, Single OR Loss Event > $10MM) | Enhanced SHUSA operational risk limits implemented, monitored and reported | Sean O'Malley |  | No | A documented set of recommended enhanced operational risk limits with clear rationale, definitions and thresholds |  | SHUSA Board-approved enhanced operational risk limits and thresholds. |  | Implemented processes to effectively monitor and report on enhanced operational risk limits. | [5 empty] | High | Medium | No
Operational Risk | Governance & Organization | Determine OR organizational structure between SHUSA and Subsidiaries | Approved short term (year 1) operational risk management operating model for SHUSA and it subsidiaries | Steve Bhatti |  | No | A documented, recommended short term (year 1) operational risk management operating model for SHUSA and it subsidiaries including roles and responsibilities clearly defined using the RACI method | [9 empty] | High | Low | No
Operational Risk | Governance & Organization | Determine OR organizational structure between SHUSA and Subsidiaries | Approved medium term (years 2/3) operational risk management operating model for SHUSA and its subsidiaries | Steve Bhatti |  | No | A documented, recommended medium term (years2/3) operational risk management operating model for SHUSA and its subsidiaries including roles and responsibilities clearly defined using the RACI method | [9 empty] | High | Low | No
Operational Risk | Governance & Organization | Determine and select short-term / medium-term resource requirements (internal and external) to deliver Year 1/2/3 priorities | Approved operational risk management staffing assessment for both the short term (year 1) and medium term (years 2/3) operating models | Steve Bhatti |  | No | Documented results from an operational risk management staffing assessment for both the short term (year 1) and medium term (years 2/3) operating models | [9 empty] | High | Low | No
Operational Risk | Governance & Organization | Recruit and onboard necessary talent | Active recruitment of SHUSA ORM staff for short term (year 1) operating model | Steve Bhatti |  | No | Initial recruitment for SHUSA ORM based on the short term (year 1) operating model | [9 empty] | High | Low | No
Operational Risk | Governance & Organization | Recruit and onboard necessary talent | Active recruitment of SHUSA subsidiaries ORM staff for both 1st and 2nd lines of defense for short term (year 1) operating model | Steve Bhatti |  | No | Initial recruitment for all SHUSA subsidiares ORM 1st and 2nd lines of defense based on the short term (year 1) operating model | [9 empty] | High | Low | No
Operational Risk | Governance & Organization | Establish a SHUSA Operational Risk Management Framework (Develop ORM principles, 3 LoD roles and responsibilities, SHUSA ORM organizational structure, ORM ERM methodology) | SHUSA Operational Risk Framework approved by SHUSA BERC | Brian McVane |  | No | A draft SHUSA Operational Risk Management Framework |  | Socialized Framework with obtained acknowledgement by CRO's and 1st line of defense with acknowledgement of roles and responsibilities |  | Obtained approval from SHUSA BERC | [5 empty] | High | Low | No
Operational Risk | Governance & Organization | Perform gap analysis of policy inventory in line with regulatory guidance supporting SHUSA policy requirements | Completed mapping of all operational risk management enterprise policies and regulatory requirements in a tool | Brian McVane |  | Yes | Tool selected |  | Tool implemented |  | Obtained authoritative sources for regulatory requirements |  | Uploaded regulatory and policy requirements into tool |  |  |  | High | Medium | No
Operational Risk | Governance & Organization | Update SHUSA enterprise Ops Risk policies as required | SHUSA Board approved SHUSA Enterprise Operational Risk Management Policy | Brian McVane |  | No | Updated operational risk management enterprise policies considering regulatory requirements and SHUSA internal policy standards |  | Obtained SHUSA Board approval for operational risk management enterprise policies and communication strategies | [7 empty] | High | Medium | No
Operational Risk | Governance & Organization | Update SHUSA enterprise Ops Risk policies as required | SHUSA Board approved SHUSA Enterprise Information Risk Management Policy | Brian McVane |  | No | Updated information risk management enterprise policies considering regulatory requirements and SHUSA internal policy standards |  | Obtained SHUSA Board approval for Information Risk management enterprise policies and communication strategies | [7 empty] | High | Medium | No
Operational Risk | Governance & Organization | Update SHUSA enterprise Ops Risk policies as required | SHUSA Board approved SHUSA Enterprise Third Party Risk Managment Policy | Brian McVane |  | No | Updated Third Party risk management enterprise policies considering regulatory requirements and SHUSA internal policy standards |  | Obtained SHUSA Board approval for Third Party Risk management enterprise policies and communication strategies | [7 empty] | High | Medium | No
Operational Risk | Governance & Organization | Update SHUSA enterprise Ops Risk policies as required | SHUSA Board approved SHUSA Enterprise Business Continuity & Disaster Recovery Policy | Brian McVane |  | No | Updated Business Continuity & Disaster Recovery risk management enterprise policies considering regulatory requirements and SHUSA internal policy standards |  | Obtained SHUSA Board approval for Business Continuity & Disaster Recovery enterprise policies and communication strategies | [7 empty] | High | Medium | No
Operational Risk | Governance & Organization | Gap analysis to identify training needs for staff of SHUSA and Subsidiaries with respect to SHUSA enterprise Ops Risk policies and standards | Documented operational risk management knowledge/skill assessment to inform initial training requirements | Brian McVane |  | No | Developed centralized, criterion based operational risk management knowledge/skill assessment for SHUSA and its subsidiary 2nd LoD |  | Completed operational risk management knowledge/skill assessment | [7 empty] | Medium | High | Yes
Operational Risk | Governance & Organization | Establish essential standards in line with the SHUSA Enterprise Operational Risk Management Policy | SHUSA CORO approved operational risk management standards and communication strategy | Brian McVane |  | No | Creation of operational risk management Standards Inventory |  | Drafted operational risk management standards aligned with Standards Inventory |  | Documented communication strategy | [5 empty] | High | Medium | Yes
Operational Risk | Governance & Organization | Establish essential standards in line with the SHUSA Enterprise Operational Risk Management Policy | SHUSA CORO approved information risk management standards and communication strategy | Brian McVane |  | No | Creation of information risk management Standards Inventory |  | Drafted information risk management standards aligned with Standards Inventory |  | Documented communication strategy | [5 empty] | High | Medium | Yes
Operational Risk | Governance & Organization | Establish essential standards in line with the SHUSA Enterprise Operational Risk Management Policy | SHUSA CORO approved third party risk management standards and communication strategy | Brian McVane |  | No | Creation of third party risk management Standards Inventory |  | Drafted third party risk management standards aligned with Standards Inventory |  | Documented communication strategy | [5 empty] | High | Medium | Yes
Operational Risk | Governance & Organization | Establish essential standards in line with the SHUSA Enterprise Operational Risk Management Policy | SHUSA CORO approved business continuity and disaster recovery standards and communication strategy | Brian McVane |  | No | Creation of business continuity & disaster recovery Standards Inventory |  | Drafted business continuity & disaster recovery standards aligned with Standards Inventory |  | Documented communication strategy | [5 empty] | High | Medium | Yes
Operational Risk | Risk Identification & Measurement | Establish the process to enforce and improve the identification and management of open issue and remediation efforts | SHUSA known issues are reflected in an issues management tool enhancing issue governance and management. | Sean O'Malley |  | No | Enterprise issue management process ownership and oversight centralized within SHUSA Operational Risk |  | A documented process/standard to improve the centralization of issue management. | [7 empty] | High | High | Yes | 3rd Party
Operational Risk | Risk Identification & Measurement | Implement the issue management tool for the identification, capture and management of issues | SHUSA known issues are reflected in an issues management tool enhancing issue governance and management. | Sean O'Malley |  | Yes | Issue management tool selected |  | Issue management tool implemented |  | Completed data migration of all known issues into an issue management tool | [5 empty] | High | High | Yes | 3rd Party
Operational Risk | Risk Identification & Measurement | Review the Material/Significant Event thresholds in line with peer institutions | Documented analysis of material event thresholds for peer institutions (primarily SBNA peers) | Sean O'Malley |  | No | Completed peer review of event escalation thresholds with results and recommendations for threshold modifications (if applicable) documented | [9 empty] | Low | Low | Yes | 3rd Party
Operational Risk | Risk Identification & Measurement | Review the Material/Significant Event thresholds in line with peer institutions | Document of strategic mitigation program to be completed in collaboration with 1st Line of Defense | Sean O'Malley |  | No | Documented strategic mitigation program designed to address material operational risk event root causes | [9 empty] | Low | Low | Yes | 3rd Party
Operational Risk | Risk Identification & Measurement | Review the Material/Significant Event thresholds in line with peer institutions | Documented analysis of material event back-testing | Sean O'Malley |  | No | A documented plan for back testing related to material operational risk events to ensure data is complete, accurate and timely. | [9 empty] | Low | Low | Yes | 3rd Party
Operational Risk | Risk Identification & Measurement | Review, evaluate and select RCSA methodology based on industry standards | RCSA Methodology document | Sean O'Malley |  | No | Develop an RCSA methodology |  | Approved RCSA methodology (through appropriate governance) | [7 empty] | Medium | Medium | Yes | Internal
Operational Risk | Risk Identification & Measurement | Review, evaluate and select RCSA methodology based on industry standards | Documented approval (ORC meeting minutes) for RCSA methodology | Sean O'Malley |  | No | Develop an RCSA methodology |  | Approved RCSA methodology (through appropriate governance) | [7 empty] | Medium | Medium | Yes | Internal
Operational Risk | Risk Identification & Measurement | Evaluate Scenario Analysis Tools and Processes | Documentation of discussion points raised in Scenario Analysis workshops and loss estimates based on subjective results (SHUSA and Subsidiaries) | Sean O'Malley |  | No | Complete documented results from the execution of the scenario analysis program for SHUSA and Subsidiaries | [9 empty] | Medium | Medium | Yes | Internal
Operational Risk | Risk Identification & Measurement | Evaluate Scenario Analysis Tools and Processes | Scenario analysis Methodology document | Sean O'Malley |  | No | Complete documented results from the execution of the scenario analysis program for SHUSA and Subsidiaries | [9 empty] | Medium | Medium | Yes | Internal
Operational Risk | Risk Identification & Measurement | Complete scenario analysis program for SHUSA and Subsidiaries | Scenario analysis Methodology document | Sean O'Malley |  | No | Complete documented results from the execution of the scenario analysis program for SHUSA and Subsidiaries |  | Provide documented methodology of scenario analysis in line with regulatory standards | [7 empty] | Medium | Medium | Yes | Internal
Operational Risk | Risk Identification & Measurement | Complete CCAR OR Loss Estimates | ORM Loss Estimation Methodology document | Sean O'Malley |  | Yes | Provide documented methodology of ORM Loss Forecasting in line with regulatory standards | [9 empty] | High | High | Yes | 3rd Party & Internal
Operational Risk | Risk Identification & Measurement | Refine operational risk loss forecasting model - Internal/External Loss Data Tools and Processes | Complete Y14A submission for CCAR 2016 | Sean O'Malley |  | Yes | A completed submission of operational risk loss estimates for CCAR (Y14A) | [9 empty] | High | High | Yes | 3rd Party & Internal
Operational Risk | Risk Identification & Measurement | Improve manual processes for OR Loss Event/Incident identification and collection | Documentation for OR Loss Event/Incident identification and capture across SHUSA and Subsidiaries (working with 1st Line of Defense) | Sean O'Malley |  | Yes | Produce documented changes to OR Loss Event/Incident identification and collection process that increase the level of automation | [9 empty] | High | High | Yes | 3rd Party & Internal
Operational Risk | Risk Identification & Measurement | Refine methodology to focus on emerging threats and vulnerabilities | IRM Gap analysis | Geoffrey Hauge |  | No | Created IRM Risk Assessment cross entity working group |  | Kickoff IRM Risk Assessment gap analysis across regulatory guidance and industry standards |  | Completed Analysis for the IRM Risk Assessment | [5 empty] | High | High | Yes | 3rd Party
Operational Risk | Risk Identification & Measurement | Refine Third Party Inherent Risk Classification methodology to determine scope and frequency of third party reviews | Documented methodology for third party inherent risk classification | Gregory Hamilton |  | Yes | A documented Third Party Inherent Risk Classification methodology |  | Rollout for the Third Party Inherent Risk Classification methodology completed for SHUSA entities | [7 empty] | High | High | Yes | 3rd Party
Operational Risk | Risk Identification & Measurement | Complete the new Inherent Risk Classification questionnaire for critical third party services | Updated inherent risk classifications for all critical third party services | Gregory Hamilton |  | Yes | Inherent risk classifications completed for all critical third party services of SHUSA entities | [9 empty] | High | High | Yes | 3rd Party
Operational Risk | Risk Identification & Measurement | Perform onsite reviews for all critical third parties (scope/frequency will be driven by inherent risk questionnaire) | Onsite schedule for critical third parties. Critical third party assessment final reports. | Gregory Hamilton |  | Yes | Completed onsite reviews for a selection of critical third parties based on results of inherent risk classifications | [9 empty] | High | High | Yes | 3rd Party
Operational Risk | Risk Identification & Measurement | Review for program changes as a result of regulatory and SHUSA Policy changes | Business Continuity Management Policy -- review and enhance existing policy; Working individually with each subsidiary: | Danny Phillips |  | No | Finalized BCM policy for submission through approval process and distribute to all subsidiaries (see Enhance Ops Risk Policies for governance); | [9 empty] | High | High | Yes | 3rd party & internal
Operational Risk | Risk Identification & Measurement | Review and refine existing Business Impact Analysis (BIA) of SBNA and SCUSA | Complete review of existing SBNA and SCUSA BIAs supporting SHUSA and subsidiary teammates: -- identify critical processes; -- to investigate and update in existing BIAs where applicable; | Danny Phillips |  | Yes | Completed review of existing BIAs and current dependencies for SBNA and SCUSA entities | [9 empty] | High | High | Yes | 3rd party & internal
Operational Risk | Risk Identification & Measurement | Identify gaps from current BIAs for SBNA and SCUSA critical processes, applications and testing | - Review 2014 - 2015 SBNA and SCUSA BCM (BR and DR) testing reports: -- identify issues and remediations completed and pending: -- identify responsible teams for issues and remediations; | Danny Phillips |  | Yes | Conducted BCM (BR and DR) of testing reports from 2014 to 2015 to identify all existing/pending, closed issues and remediation for SBNA and SCUSA | [9 empty] | High | High | Yes | 3rd party & internal
Operational Risk | Risk Identification & Measurement | Review existing exercise results for each SBNA and SCUSA | Consolidate gap analysis report for SBNA and SCUSA of critical processes, -- critical applications, and testing for all subsidiaries: -- identify potential Risks; | Danny Phillips |  | Yes | Completed and consolidated a gap analysis against critical processes, critical applications and testing results for SBNA and SCUSA | [9 empty] | High | High | Yes | 3rd party & internal
Operational Risk | Risk Management | Strengthen aggregated operational risk reporting to allow the SAN US/SHUSA Operational Risk Committee to better fulfill its obligation to oversee and manage the identification and monitoring of operational risks as well as to escalate risks/issues that need ERMC/BERC/Board transparency. (Establish baseline operational risk management reporting and dashboards for SHUSA and its subsidiaries including (1) a standard set up summary risk data such as RTS limits, risk profile, top risks, emerging risks, material events and program updates, (2) a standard set of risk data specific to operational risk, information risk, third party risk and business continuity) | Established operational risk dashboards, including risk data for ORM, IRM, TPRM and BCM, for SHUSA and its subsidiaries are included in monthly governance reporting. | Brian McVane |  | No | SHUSA operational risk management reporting framework is communicated to all subsidiaries |  | SHUSA defined processes and tools are utilized to support monthly operational risk reporting |  | SHUSA subsidiaries are producing operational risk reporting in line with SHUSA operational risk management requirements | [5 empty] | Medium | Medium | Yes
Operational Risk | Risk Monitoring | Develop timely reporting mechanisms and processes to satisfy OR Y-14Q reporting requirements | Completed automation of data collection for initial phase | Sean O'Malley |  | Yes | "Golden Source" repository populated with data for initial phase | [9 empty] | High | High | Yes | 3rd party & internal
Model Risk Management |  | Inform Board and Sen. Mgt on MRM regulatory requirements and industry practices (Board, BERC, ERMC, EMC) | Presentation Material | Pete W. | 2015-08-31 | No | Presentation material drafted | 2015-08-31 | Presentation material reviewed and approved | 2015-08-31 | [6 empty] | High | Low | Yes
Model Risk Management |  | Inform Board and Sen. Mgt on MRM regulatory requirements and industry practices (Board, BERC, ERMC, EMC) | Presentation Schedule (if beyond SHUSA) | Pete W. | 2015-08-31 | No | Presentation schedule drafted | 2015-08-31 | Presentation schedule reviewed | 2015-08-31 | Presentation Schedule published | 2015-08-31 |  |  |  |  | Low | Low | No
Model Risk Management |  | Inform Board and Sen. Mgt on MRM regulatory requirements and industry practices (Board, BERC, ERMC, EMC) | Presentation Confirmation (Board Minute) | Pete W. | 2015-09-30 | No | Conduct Initial SHUSA Board Presentation | 2015-09-30 | [8 empty] | Low | Low | No
Model Risk Management |  | Inform Board and Sen. Mgt on MRM regulatory requirements and industry practices (Board, BERC, ERMC, EMC) | Board Presentation Plan | Pete W. | 2015-09-30 | No | Build long term Board Presentation Plan (including Entities) | 2015-09-30 | [8 empty] | Low | Low | No
Model Risk Management |  | Clarify the roles of BERC, ERMC, EMC, MRMC in MRM. Revise committee charters and mandates to strengthen MRM o/s role | Updated charters for BERC, ERMC, EMC and MRMC | Pete W. | 2015-08-31 | No | Updates to charters drafted | 2015-08-31 | Reviewed and finalized BERC, ERMC, EMC and MRMC committee charters with updates to strengthen MRM oversight and roles and responsibilities | 2015-08-31 | [6 empty] | High | High | Yes
Model Risk Management |  | Clarify the roles of BERC, ERMC, EMC, MRMC in MRM. Revise committee charters and mandates to strengthen MRM o/s role | Charter Approval (Board Minute) | Pete W. | 2015-09-30 | No | Revised charters approved | 2015-09-30 | [8 empty] | Low | Low | No
Model Risk Management |  | Develop model risk workstream (CART) reporting, governance, controls | Requirements for model risk workstream (CART) reporting, governance, controls | Greg T. | 2015-07-31 | No | Requirements for enhanced model risk remediation reporting, governance and control drafted | 2015-06-30 | Requirements for enhanced model risk remediation reporting, governance and control reviewed and approved | 2015-07-31 | [6 empty] | Medium | Medium | No
Model Risk Management |  | Develop model risk workstream (CART) reporting, governance, controls | Reporting templates, communication plan and calendar(cadence) | Greg T. | 2015-07-31 | No | Reporting templates, communication plan and calendar(cadence) drafted | 2015-07-31 | [8 empty] | Medium | Low | No
Model Risk Management |  | Enhance model risk BAU reporting standards. Deliver enhanced reporting (including Sen Leadership & Board) | Requirements for enhanced model risk BAU reporting | Pete W. | 2015-08-31 | No | Requirements for enhanced model risk BAU reporting drafted (MRMC, Model Risk to BERC/ERMC, etc.) | 2015-07-31 | Requirements for enhanced model risk BAU reporting approved | 2015-08-31 | [6 empty] | Medium | Medium | No
Model Risk Management |  | Enhance model risk BAU reporting standards. Deliver enhanced reporting (including Sen Leadership & Board) | BAU Reporting templates, Frequency(Cadence) , Communication Plan (Who gets what level of detail) | Pete W. | 2015-08-31 | No | Reporting templates, communication plan and calendar(cadence) drafted | 2015-08-31 | Reporting templates, communication plan and calendar(cadence) approved | 2015-08-31 | [6 empty] | Medium | Medium | Yes
Model Risk Management |  | Enhance model risk BAU reporting standards. Deliver enhanced reporting (including Sen Leadership & Board) | MRMC Committee deck, BERC/ERMC submission | Pete W. | 2015-09-30 | No | Implemented Enhanced reporting | 2015-09-30 | [8 empty] | Medium | Medium | Yes
Model Risk Management |  | Define requirements for long term Model Inventory and Reporting system. Conduct vendor selection | Long term Model inventory and reporting system requirement | Pete W. | 2015-09-30 | Yes | Requirements for long term Model inventory and reporting system drafted | 2015-09-30 | Requirements for long term Model inventory and reporting system approved | 2015-09-30 | [6 empty] | High | High | Yes
Model Risk Management |  | Define requirements for long term Model Inventory and Reporting system. Conduct vendor selection | Vendor selection criteria and approach | Pete W. | 2015-10-31 | No | Vendor selection criteria and process drafted/approved | 2015-10-31 | [8 empty] | Low | Low | No
Model Risk Management |  | Define requirements for long term Model Inventory and Reporting system. Conduct vendor selection | Vendor SOW; documented Minutes of decision (per VRM committee) | Pete W. | 2015-11-30 | No | Vendor selection complete | 2015-11-30 | [8 empty] | Low | Low | No
Model Risk Management |  | Hire for known staffing requirements based on volume of validation req'd | Staffing Report | Rafic F. | 2015-12-31 | No | Approval for supplemental FTE headcount | 2015-06-30 | Approval for supplemental consultant/advisory headcount | 2015-06-30 | Onboarding of consulting resources | 2015-07-31 | Hiring of approved incremental FTEs and existing gaps | 2015-12-31 |  |  | Medium | Medium | No
Model Risk Management |  | Define Target Operating model (including org structure) | Operating Model | Edward S. | 2015-07-31 | No | Articulation of 3LoD principles (May) | 2015-05-29 | Formalization of Risk reporting lines at the C-Suite (May) | 2015-05-29 | Risk roles and responsibilities of SHUSA vs. subsidiaries (across each line of defense) | 2015-07-31 | Design of org. structure for each risk type / entity / line of defense | 2015-07-31 | Operating model approved | 2015-07-31 | Medium | Medium | Yes
Model Risk Management |  | Conduct talent and staffing assessment for MRMG | Talent and staffing assessment result/report | Rafic F. | 2015-09-30 | No | Assessment of FTE needs (activity based analysis) | 2015-09-30 | Definition of capabilities needed | 2015-09-30 | Assessment of capabilities of existing staff | 2015-09-30 | Identification of training / upskilling / hiring needs | 2015-09-30 | Talent and staffing assessment complete | 2015-09-30 | Medium | Medium | Yes
Model Risk Management |  | Conduct First Line and auxiliary functions (IT, etc.) staffing assessment (Dependency on Model Development) | Talent and staffing assessment result/report | TBD | 2015-09-30 | No | Assessment of FTE needs (activity based analysis) | 2015-09-30 | Definition of capabilities needed | 2015-09-30 | Assessment of capabilities of existing staff | 2015-09-30 | Identification of training / upskilling / hiring needs | 2015-09-30 | First line and auxiliary functions staffing assessment complete | 2015-09-30 | Medium | Medium | Yes
Model Risk Management |  | Develop staffing/hiring strategy (including external resources) and plan based on assessment, backlogs, and workloads | Staffing/Hiring Strategy | TBD | 2015-09-30 | No | All relevant inputs to define staffing/hiring strategy is in place | 2015-09-30 | Staffing/Hiring strategy drafted | 2015-09-30 | Staffing/Hiring strategy approved | 2015-09-30 |  |  |  | 2015-12-31 | Medium | Medium | Yes
Model Risk Management |  | Commence hiring strategy/plan in partnership with the First Line/Model Development | Hiring execution touchpoint cadence | TBD | 2015-12-31 | No | Regular checkpoint on hiring strategy execution drafted | 2015-12-31 | Regular checkpoint on hiring strategy execution reviewed and published | 2015-12-31 | [6 empty] | Low | High | Yes
Model Risk Management |  | Include MRMG specialist in SCUSA pricing governance | Updated SCUSA pricing governance charter | TBD | 2015-07-31 | No | MRMG specialist designated to participate in SCUSA pricing governance | 2015-07-31 | SCUSA pricing governance charter updated to include MRMG specialist | 2015-07-31 | [6 empty] | High | Medium |  | Actual status of this item is pending. May be closed
Model Risk Management |  | Strengthen oversight of the pricing of SCUSA retail financial products including committee charter updates | SCUSA retail finance product oversight requirements | TBD | 2015-07-31 | No | Requirements for oversight drafted | 2015-07-31 | Requirements for oversight approved | 2015-07-31 | [6 empty] | High | Medium |  | Actual status of this item is pending. May be closed
Model Risk Management |  | Strengthen oversight of the pricing of SCUSA retail financial products including committee charter updates | Updated relevant charters | TBD | 2015-07-31 | No | List of charters to be updated defined | 2015-07-31 | Relevant charters updates drafted | 2015-07-31 | Relevant charters updates approved | 2015-07-31 |  |  |  |  | High | Medium |  | Actual status of this item is pending. May be closed
Model Risk Management |  | Enhance SCUSA pricing policies and procedures | Updated SCUSA pricing policy | TBD | 2015-07-31 | No | SCUSA pricing policy updates drafted | 2015-07-31 | SCUSA pricing policy updates approved | 2015-07-31 | [6 empty] | High | Medium |  | Actual status of this item is pending. May be closed
Model Risk Management |  | Enhance SCUSA pricing policies and procedures | Updated SCUSA pricing procedures | TBD | 2015-07-31 | No | SCUSA pricing procedures updates drafted | 2015-07-31 | SCUSA pricing procedures updates approved | 2015-07-31 | [6 empty] | High | Medium |  | Actual status of this item is pending. May be closed
Model Risk Management |  | Develop Framework - enhance decision making authority & roles and responsibilities for approving models and model changes (including model retirement) | MRM Framework | Pete W. | 2015-08-31 | No | Framework Drafted | 2015-07-31 | Framework Approved | 2015-08-31 | [6 empty] | High | High | Yes
Model Risk Management |  | Enhance Provisional Approval (PA) process, clarify roles and responsibilities | PA process enhancement requirements | Pete W. | 2015-07-31 | No | Requirements for enhancement for PA process drafted | 2015-07-31 | Requirements for enhancement for PA process approved | 2015-07-31 | [6 empty] | High | Low | No
Model Risk Management |  | Enhance Provisional Approval (PA) process, clarify roles and responsibilities | Updated PA process | Pete W. | 2015-08-31 | No | PA process updates drafted | 2015-08-31 | PA process updates approved | 2015-08-31 | [6 empty] | Medium | Low | No
Model Risk Management |  | Redesign Risk Rating Methodology with a focus on repeatability, transparency, and methodology | Model Risk rating methodology enhancement requirements | Pete W. | 2015-08-31 | No | Requirements for Model risk rating methodology drafted | 2015-08-31 | Requirements for Model risk rating methodology approved | 2015-08-31 | [6 empty] | High | Low | No
Model Risk Management |  | Redesign Risk Rating Methodology with a focus on repeatability, transparency, and methodology | Updated model risk rating methodology | Pete W. | 2015-08-31 | No | Enhancement of Model risk rating methodology drafted | 2015-08-31 | Enhancement of Model risk rating methodology approved | 2015-08-31 | [6 empty] | High | Low | No
Model Risk Management |  | Redesign modelling tiering Methodology with a focus on repeatability, transparency, and methodology | Model tiering methodology enhancement requirements | Pete W. | 2015-07-31 | No | Requirements for Model tiering methodology drafted | 2015-07-31 | Requirements for Model tiering methodology approved | 2015-07-31 | [6 empty] | High | Low | No
Model Risk Management |  | Redesign modelling tiering Methodology with a focus on repeatability, transparency, and methodology | Updated model tiering methodology | Pete W. | 2015-07-31 | No | Enhancement of Model tiering methodology drafted | 2015-07-31 | Enhancement of Model tiering methodology approved | 2015-07-31 | [6 empty] | High | Low | No
Model Risk Management |  | Update policy and procedure based on SR 11-7 guidance (gap analysis) including detailed model validation testing procedures | SR 11-7 gap analysis | Pete W. | 2015-07-31 | No | SR 11-7 Gap analysis complete | 2015-07-31 | [8 empty] | High | Medium | Yes
Model Risk Management |  | Update policy and procedure based on SR 11-7 guidance (gap analysis) including detailed model validation testing procedures | Updated MRM Policy | Pete W. | 2015-08-31 | No | Policy update based on SR 11-7 gap analysis drafted | 2015-08-31 | [8 empty] | High | Medium | Yes
Model Risk Management |  | Update policy and procedure based on SR 11-7 guidance (gap analysis) including detailed model validation testing procedures | Minutes from MRMC / BERC/ERMC | Pete W. | 2015-09-30 | No | Obtain approval on MRM policy | 2015-09-30 | [8 empty] | High | Medium | No
Model Risk Management |  | Update policy and procedure based on SR 11-7 guidance (gap analysis) including detailed model validation testing procedures | MRM Procedure inventory | Pete W. | 2015-08-31 | No | Updated inventory of procedures based on SR11-7 | 2015-08-31 | [8 empty] | Low | High | Yes
Model Risk Management |  | Update policy and procedure based on SR 11-7 guidance (gap analysis) including detailed model validation testing procedures | Updated MRM procedures | Pete W. | 2015-09-30 | No | Obtained MRMC approval of procedures | 2015-09-30 | [8 empty] | High | High | Yes
Model Risk Management |  | Train MRMG staff on the new validation procedures | Training materials approved by CMRO | Pete W. | 2015-09-30 | No | Prepare MRMG materials | 2015-09-30 | [8 empty] | High | Low | No
Model Risk Management |  | Train MRMG staff on the new validation procedures | Record of attendees / signatures | Pete W. | 2015-09-30 | No | Deliver MRMG training | 2015-09-30 | [8 empty] | Low | Low | No
Model Risk Management |  | Enhance training based on updated Policy, Procedures, and Development Standards | Updated training materials | Pete W. | 2015-12-31 | No | Training material for all stakeholders drafted | 2015-12-31 | Training material for all stakeholders approved by CMRO | 2015-12-31 | [6 empty] | High | Medium | Yes
Model Risk Management |  | Enhance training based on updated Policy, Procedures, and Development Standards | Training schedule/cadence | Pete W. | 2015-12-31 | No | Training schedule/cadence drafted | 2015-12-31 | Training schedule/cadence reviewed and published | 2015-12-31 | [6 empty] | Low | Low | No
Model Risk Management |  | Implement Policy and Procedures/Standards | TBD | Pete W. | TBD | No | Collection of compliance report complete | TBD | [8 empty] | High | High | Yes
Model Risk Management |  | Address Legacy Model Validation Backlog | Prioritized list of Legacy models | Paul M. | 2015-07-31 | No | Legacy models prioritized for validation | 2015-07-31 | [8 empty] | High | Medium | Yes
Model Risk Management |  | Address Legacy Model Validation Backlog | Gap assessment result | Paul M. | 2015-10-31 | No | Tier 1 Models gap assessment complete | 2015-10-31 | [8 empty] | High | Medium | Yes
Model Risk Management |  | Address Legacy Model Validation Backlog | Remediation plan | Paul M. | 2015-10-31 | No | Tier 1 Models remediation plan complete | 2015-10-31 | [8 empty] | High | Medium | Yes
Model Risk Management |  | Address Legacy Model Validation Backlog | Validation results | Paul M. | 2015-10-31 | No | Initial validation findings – including interim compensating controls and other risk mitigants | 2015-10-31 | [8 empty] | High | High | Yes
Model Risk Management |  | Address Legacy Model Validation Backlog | List of validation ready models | Paul M. | 2015-12-31 | No | Commence work on models identified as being ready for validation | 2015-12-31 | [8 empty] | High | Medium | Yes
Model Risk Management |  | CCAR model validation | Validation Schedule | Paul M. | 2015-06-30 | No | Definition of validation schedule with Model Development complete | 2015-06-30 | [8 empty] | High | Medium | Yes
Model Risk Management |  | CCAR model validation | CCAR Model Validation Result | Paul M. | 2015-12-31 | No | CCAR models validated | 2015-12-31 | [8 empty] | High | High | Yes
Model Risk Management |  | Define model data validation data and reporting requirements aligned to model risk management framework and validation standards | Model data validation data requirements | TBD | TBD | Yes | Requirements for Model Data validation data drafted | TBD | Requirements for Model Data validation data approved | TBD | [6 empty] | High | Low | No
Model Risk Management |  | Define model data validation data and reporting requirements aligned to model risk management framework and validation standards | Model data validation reporting requirements | TBD | TBD | Yes | Requirements for Model Data validation Report drafted | TBD | Requirements for Model Data validation Report approved | TBD | [6 empty] | High | Medium | No
Data & IT |  | IT Risk Assessment and Risk Reporting (CCAR, RCSA, ERM, MRP, OCC, HS, etc.) | SHUSA Aggregrated IT Risk Assessment Document (Phase 1 - partial completion expected) | Frank Cignarella | December 31 2015 | Yes | IT Risk Assessment Methodology Document Published | June 1 2015 | IT Risk Aggregregation Model Developed and Approved by IT, ORM and ERM | July 1 2015 | iGRC SHUSA Instance with Business Hierarchy loaded | Aug 1 2015 | iGRC Data populated for SHUSA and related entitied (SBNA, SCUSA, other (SIS) | December 15 2015 | SHUSA Risk Aggregration report from iGRC Data generated for management | December 31 2015 | Medium | High | Yes | SHUSA iGRC Instance and SBNA methodology and groundwork available today to leverage; contract in place with vendor to support
Data & IT |  | IT Risk Assessment and Risk Reporting (CCAR, RCSA, ERM, MRP, OCC, HS, etc.) | SBNA IT Risk Assessment Document (Phase 1 - partial completion expected) (Data to be fed into SHUSA iGRC instance for risk aggregation) | Frank Cignarella | Nov 10 2015 | Yes | SBNA IT Risk Register | May 25 2015 | SBNA IT Applicability Matrix | June 1 2015 | SBNA IT Control Plans and Controls Modeled inside iGRC | June 15 2015 | SBNA IT Process, IT Function, IT Facility Control Plans Documented and Risk Assessed | Sept 1 2015 | SBNA Application and Infrastructure Control Plans Documented and Risk Assessed | Nov 1 2015 | High | High | Yes | SBNA iGRC Instance already in place; groundwork in place to leverace and contract in place with vendor to support
Data & IT |  | IT Risk Assessment and Risk Reporting (CCAR, RCSA, ERM, MRP, OCC, HS, etc.) | SCUSA IT Risk Assessment Document (Phase 1 - partial completion expected) (Data to be fed into SHUSA iGRC instance for risk aggregation) | Frank Cignarella | Nov 15 2015 | Yes | SCUSA IT Risk Register | May 25 2015 | SCUSA IT Applicability Matrix | June 15 2015 | SCUSA IT Control Plans and Controls Modeled inside iGRC | June 20 2015 | SCUSA IT Process, IT Function, IT Facility Control Plans Documented and Risk Assessed | Sept 1 2015 | SCUSA Application and Infrastructure Control Plans Documented and Risk Assessed | Nov 1 2015 | High | High | Yes | SCUSA iGRC Instance already in place; groundwork in place to leverace and contract in place with vendor to support
Data & IT |  | IT Risk Assessment and Risk Reporting (CCAR, RCSA, ERM, MRP, OCC, HS, etc.) | Other SHUSA Entity IT Risk Assessment Document (e.g., SIS, etc.) (Phase 1 - partial completion expected) (Data to be fed into SHUSA iGRC instance for risk aggregation) | Frank Cignarella | Nov 20 2015 | Yes | Other IT Risk Register | May 25 2015 | Other IT Applicability Matrix | June 20 2015 | Other IT Control Plans and Controls Modeled inside iGRC | June 25 2015 | "Other" IT Process, IT Function, IT Facility Control Plans Documented and Risk Assessed | Sept 1 2015 | "Other" Application and Infrastructure Control Plans Documented and Risk Assessed | Nov 1 2015 | High | High | Yes | "Other" iGRC Instance already in place; groundwork in place to leverace and contract in place with vendor to support
Data & IT |  | Finding and Remediation Management Capability and Governance (including 2014 IT SOX Finding Remediations) | Monthly report of Technology Findings and Remediation Plans, assigned to owners with business alignment (T&O, Retail, Auto, etc.) generated and delivered to EMC members | Frank Cignarella | December 1 2015 | Yes | Business Owners for Applications (SOX Covered) Identified | June 1 2015 | Findings for Business Applications assigned to Business Owners (e.g., T&O, Retail, Auto, etc.) | June 15 2015 | Findings and Remediation Plan Governance Model Documented (expected behavior and timing) | July 1 2015 | SHUSA and related entities Findings to be loaded into iGRC SHUSA Instance and related iGRC instances for entities (SBNA, SCUSA, etc.) with minimum necessary fields populated | Oct 1 2015 | "Governance" Report generated from iGRC and communicated to EMC members and the finding and remediation plan owners for ongoing management and maintenance | Nov 20 2015 | High | High | Yes | IGRC instances and SBNA OpRisk Issue Management documentation available to leverage; heavy lifting will be getting ownership, fields populated and active management of the findings and remediations in place and under governance whereby violations (non participation) are escalated and remedied.
Data & IT |  | Governance: Policy, Standards, Roles and Responsibilities Development (EPAP, RTS) | IT Governance document in EPAP Compliant format for SHUSA the holding company approved and published | Frank Cignarella | December 31 2015 | Yes | IT Policies Drafted | Nov 1 2015 | IT Policies Approved | Dec 1 2015 | IT Standards Drafted | Dec 1 2015 | IT Standards Approved | Dec 15 2015 | IT Guidelines, Acceptable form, and select IT Processes Drafted | Dec 31 2015 | High | Medium | Yes | Contracted for delivery of the draft documents with vendor in place, leveraging same vendor we had success developing SBNA governance documents with and will 'uplifting' SBNA documents to the extent practical.
Data & IT |  | Identity and Access Management Solution (SailPoint for Attestation, Access Request) | SHUSA Access Attestation & Certification Solution - Production Phase 1 | Frank Cignarella | December 31 2015 | Yes | SHUSA IAM Program Defined and Documented for Access Attestation and Certification | Oct 1 2015 | Define SHUSA Access Attestation and Certification - Standard Operating Procedures (SOP) (Document) | Nov 1 2015 | Development Environment for SHUSA Access Attestation & Certification Solution in place | Nov 15 2015 | UAT / Pre-production Environment and User Acceptance Testing Performed and Signed off for SHUSA Access Attestation and Certification Solution | Dec 15 2015 | Production Release -SHUSA Access Attestation & Certification Solutoin Phase 1 Capabilities (Phase 2 Capabilities to be delivered in 2016) and initial campaign initiated | Dec 31 2015 | High | High | Yes | Contracted for delivery of the Attestation and Certification with same vendor that successfully supported SBNA in 2014/2015; blueprints and accelerators available from SBNA to leverage as practical. Solution is Gartner Magic Quandrant leader and well known within the financial services industry (SailPoint).
Data & IT |  | Identity and Access Management Solution (SailPoint for Attestation, Access Request) | SHUSA User Access Request Portal - Production Phase 1 | Frank Cignarella | December 31 2015 | Yes | SHUSA IAM Program Defined and Documented for User Access Request Portal | Oct 1 2015 | Define SHUSA User Access Request Portal - Standard Operating Procedures (SOP) (Document) | Nov 1 2015 | Development Environment for SHUSA User Access Request Portal Solution in place | Nov 15 2015 | UAT / Pre-production Environment and User Acceptance Testing Performed and Signed off for SHUSA User Access Request Portal Solution | Dec 15 2015 | Production Release - SHUSA User Access Request Portal - Phase 1 Capabilities (Phase 2 Capabilities to be delivered in 2016) (3-5 Applications and related roles can be requested and workflow for management pre-approval and then sent to human provisioners) | Dec 31 2015 | High | High | Yes | Contracted for delivery of the User Access Request Portal with same vendor that successfully supported SBNA in 2014/2015; blueprints and accelerators available from SBNA to leverage as practical. Solution is Gartner Magic Quandrant leader and well known within the financial services industry (SailPoint).
Data & IT |  | Identity and Access Management Solution (SailPoint for Attestation, Access Request) | SHUSA Access Termination Workflow - Production Phase 1 | Frank Cignarella | December 31 2015 | Yes | SHUSA IAM Program Defined and Documented for Access Termination Workflow | Oct 1 2015 | Define SHUSA Access Termination Workflow - Standard Operating Procedures (SOP) (Document) | Nov 1 2015 | Development Environment for SHUSA Access Termination Workflow Solution in place | Nov 15 2015 | UAT / Pre-production Environment and User Acceptance Testing Performed and Signed off for SHUSA Access Termination Workflow Solution | Dec 15 2015 | Production Release - SHUSA Access Termination Workflow - Phase 1 Capabilities (Phase 2 Capabilities to be delivered in 2016) | Dec 31 2015 | High | High | Yes | Contracted for delivery of the Access Termination Workflow Solution with same vendor that successfully supported SBNA in 2014/2015; blueprints and accelerators available from SBNA to leverage as practical. Solution is Gartner Magic Quandrant leader and well known within the financial services industry (SailPoint).
Data & IT |  | Data Flow Control from Upstream Feeders into Golden Sources and from Golden Sources to Downstream Reporting Systems | Data Flow Control Document detailing the data flows and specific controls (e.g., accuracy and completeness) in place for the data elements | Frank Cignarella | December 31 2015 | Yes | Data Elements identified and documented | July 1 2015 | Data Sources (Upstream feeders, golden sources, downstream reporting systems) identified and documented (including owners) | Aug 1 2015 | Data flow modeled (flow chart) from source to source (upstream, golden, downstream) | Oct 1 2015 | Control Points and Control Techniques documented | Nov 1 2015 | Potential gaps in control points and control techniques documented in SHUSA iGRC as Findings with corresponding remediation plans | Dec 31 2015 | High | High | Yes | This is a core deliverable and requires support from the Architecture, RDA and CDO teams
Data & IT |  | Establish Key Data Elements (KDEs) for prioritized CCAR data (including models and schedules), including documenting data dictionary and lineage, measuring and remediating data quality, deploying data controls. | KDEs defined for each domain in SHUSA, with lineage information, data quality rules, and initial metrics (KPIs) | Peter Flanagan | 2015-12-31 | Yes
Data & IT |  | Implement a Data Quality Center of Excellence to improve the quality of the company’s data (SHUSA and all the related US entities) by centralizing the collection of data defects, analyzing and assigning the issues causing the defects, and ensuring remediation activities are completed. | DQ COE staffed and operational | Peter Flanagan | 2015-12-21 | Yes
Data & IT |  | Conduct a data industry maturity model assessment for SBNA, SCUSA and SHUSA to identify capability gaps that require further remediation. | Data Maturity Model (DMM) assessment for each of SHUSA, SBNA and SCUSA | Peter Flanagan | 2015-08-30 | No
Data & IT |  | Establish strict governance on KDEs to assess, ensure and report on compliance with data policies and standards. | Establishment of working group including business data stewards | Peter Flanagan | 2015-12-31 | No
Data & IT |  | Create the structure and organization of the CDO for SHUSA | Staffed CDO Target Operating Model | Peter Flanagan | 2015-12-21 | No
Data & IT |  | Clearly define roles, responsibilities and ownership for data collection, quality, maintenance (Data Manager, Data Owner, Data Steward, DQ Admin, Tech Data Owner,……) as well as a list of Data Domains. | Agreed list of Data Domain definition documents, with assignment of key roles | Peter Flanagan | 2015-07-31 | No
Data & IT |  | Organize data management roles along the three lines of defense model (Business, Chief Data Officer and Independent Audit) | Approval of data management roles definitions | Peter Flanagan | 2015-07-15 | No
Data & IT |  | Socialize data management program and implementation plan with key stakeholders. | Education and communication plan for SHUSA CDO | Peter Flanagan | 2015-07-15 | No
Data & IT |  | Define domain scope and boundaries | Data Domain definition documents | Peter Flanagan | 2015-11-30 | No
Data & IT |  | Launch a SHUSA Data Governance Council attended by Data Manager, Data Owners, Data Stewards and CDO. | Data Governance council charter approved by first meeting of DG Council members | Peter Flanagan | 2015-06-30 | No
Data & IT |  | Assess and ensure compliance of SHSUA, SBNA and SCUSA practices against the Data Management Policy and Standards | Compliance review worksheet completed for each CDO team within SHUSA, SBNA and SCUSA | Peter Flanagan | 2015-12-31 | No
Data & IT |  | Define a comprehensive data control framework, and apply it for critical CCAR and EPS / ELS related processes | Data Dictionary, Lineage, Data Quality Dashboard Reports | Peter Flanagan | 2015-12-31 | Yes
Data & IT |  | Conduct data industry maturity model assessment for SHUSA, SBNA and SCUSA on an annual basis | Completed Maturity Model | Peter Flanagan | 2015-11-30 | No
CCAR | Scenario generation | Improve linkages between scenario generation and upstream / downstream processes | Capital Management team included in the Risk ID process to ensure appropriate collaboration between teams and support the identification of quantitative and qualitative risks | John Barris | 2015-10-31 | No | Identify Capital Management-Risk ID liaison | 2015-06-30 | Define roles, responsibilities governing involvement and collaboration (if any) | 2015-07-31 | Review ed aggregation of SHUSA-level Inventory with Top-Down Analysis | 2015-10-31 |  |  |  |  | Medium | Medium | No | Heavy reliance on Risk ID to meet their deadlines, which are reflected here as Milestones.
CCAR | Scenario generation | Development of multiple, robust scenarios for selection and testing | Enhanced set of scenarios aligned to the refreshed scenario design methodology | John Barris | 2015-12-18 | No | Receive SHUSA-level Risk ID Inventory & Assessment | 2015-10-31 | Capital Management presents and recommends initial set of Idiosyncratic Narratives to Ex&Agg | 2015-11-13 | Capital Management recommends Idiosyncratic Narratives to Management CC | 2015-12-18 | Capital Management recommends Idiosyncratic Narratives to Board CC | 2015-12-01 | Capital Management works with BU and Risk stakeholder to paramterize suite of multiple scenarios | 2015-12-18 | High | Medium | No
CCAR | Scenario generation | Development of multiple, robust scenarios for selection and testing | Updated policies and procedures that govern the scenario-design and scenario-selection processes | John Barris | 2015-10-31 | No | First Draft of Policy & Procedure Documentation reviewed by CCAR Director | 2015-08-30 | Policy & Procedure Documentation reviewed by Ex&Agg | 2015-08-15 | Policy & Procedure Documentation reviewed by Management CC | 2015-09-15 | Policy & Procedure Documentation reviewed by Board CC | 2015-10-31 | Policy & Procedure Documentation updated to reflect actual CCAR 2016 process | 2016-01-31 | Medium | Low | No
CCAR | Scenario generation | Development of multiple, robust scenarios for selection and testing | BHC scenarios actual macroeconomic data aligned across all scenarios | John Barris | 2016-01-31 | No | Presentation of a suite of scenarios to Management and Board Capital Committees for formal selection and approval of the scenarios to be used in CCAR/DFAST | 2015-12-31 | Receive FRB Scenarios from FRB | 2015-01-22 | Align BHC Scenario Actuals with FRB Scenarios | 2015-01-31 |  |  |  |  | Low | Low | No
CCAR | Capital assessment | Credible, transparent, repeatable process to measure uncertainty resulting from capital planning and process weaknesses | Defined quantification approach and methodology | Imad Kordab | TBD | No | Drafted quantification approach and methodology |  | Syndicated with relevant experts and stakeholders |  | Approved by [X] committee
CCAR | Capital assessment | Credible, transparent, repeatable process to measure uncertainty resulting from capital planning and process weaknesses | Developed model to translate uncertainty to a capital buffer | Imad Kordab | TBD | Yes | Staffed modeling team |  | Developed multiple model options for governance committee consideration |  | Finalized modeling approach
CCAR | Capital assessment | Credible, transparent, repeatable process to measure uncertainty resulting from capital planning and process weaknesses | Quantification/estimate of uncertainty resulting from capital planning and process weaknesses at a process or model level | Imad Kordab | TBD | Yes | Assessed current and past process weakness to develop estimate of uncertainty |  | Developed estimates related to assumptions, limitations and weaknesses |  | Quantification approved by [X] committee
CCAR | Capital assessment | Measure and account for inherent uncertainty due to model limitations | Developed quantification approach and standards | Imad Kordab | TBD | No | Drafted quantification approach and standards |  | Approved by [X] committee
CCAR | Capital assessment | Measure and account for inherent uncertainty due to model limitations | Disseminated the approach to stakeholders to syndicate | Imad Kordab | TBD | No | Developed approach to stakeholders |  | Implemented approach
CCAR | Capital assessment | Measure and account for inherent uncertainty due to model limitations | Quantified inherent model uncertainty and incorporated results into stressed capital buffer | Imad Kordab | TBD | No | Develop intial quantification of model uncertainty |  | Syndicated results of uncertainty measurement with model risk management and model validation |  | Approved by [X] committee
CCAR | Capital assessment | Developed economic capital model to evaluate impact on capital of stressful scenarios | Rigorous process developed beyond enterprise-wide scenario analysis, to assess the aggregate impact on capital from stressful conditions | Imad Kordab | TBD | Yes | Brainstormed and determined necessary actions to constititute process steps |  | Mapped process based on determined steps
CCAR | Capital assessment | Formalized management overlays process | Developed overlay standards and templates | Imad Kordab | TBD | No | Determined and consulted with correct stakeholders |  | Determined correct standards/templates based on stakeholder interactions |  | Incorporated feedback and expert opinions
CCAR | Capital assessment | Formalized management overlays process | Disseminated model overlay approach to governance committees and model owners | Imad Kordab | TBD | No | Disseminated approach to stakeholders |  | Implemented approach |  | Implemented standards of documentation for overlays
CCAR | Capital assessment | Formalized management overlays process | Aggregated of overlays across CCAR process steps | Imad Kordab | TBD | No | Developed and implemented process for centralzing collection of overlay documentation |  | Aggregated overlay results across CCAR process steps
CCAR | Governance and effective challenge | Improved weakness indentification and management process | Updated weakness indentification policy and procedures | Jon Watson | TBD | No | Draft updated policy and procedures |  | Draft sent to committee #1 |  | Draft sent to committee #2 | [5 empty] | Medium | Low
CCAR | Governance and effective challenge | Improved weakness indentification and management process | Finalized weakness inventory with owners and action items | Jon Watson | TBD | No | Weakness inventory structure updated to comply with new weakness ID procedures |  | Weakness ID process communicated to CCAR participants |  | Completed inventory | [5 empty] | Medium | High
CCAR | Governance and effective challenge | Refreshed and implemented review and challenge framework | Review and enhance current review and challenge framework | Jon Watson | TBD | No | Assessment and update of current framework completed |  | Draft sent to committee #1 |  | Draft sent to committee #2 |  | New review and challenge communicated to all relevant governance committees |  |  |  | Medium | Low
CCAR | Governance and effective challenge | Refreshed and implemented review and challenge framework | Review and challenge calendar aligned to framework | Jon Watson | TBD | No | Calendars and high-level drafted |  | Calendar approved by committee #1 |  | Detailed calendar based on revamped end-to-end process | [5 empty] | Medium | Low
CCAR | Governance and effective challenge | Updated CCAR governance structure | Re-designed CCAR governance structure and landscape | Jon Watson | TBD | No | Current state governance structure and flows assessed |  | New CCAR governance structure determined (e.g., charters, membership) |  |  |  | Approval of governance structure by committee #1 |  |  |  | Medium | Low
CCAR | Governance and effective challenge | Updated CCAR governance structure | Governance landscape implemented | Jon Watson | TBD | No | Governance structure approved |  | Initial meeting of committee with new membership/composition held | [7 empty] | High | High
CCAR | Governance and effective challenge | Extensive board engagement and input into CCAR process | Board training materials and schedule | Jon Watson | TBD | No | Developed overall board training schedule and agenda |  | Delivered training #1 |  | Delivered training #2 | [5 empty] | High | Medium
CCAR | Governance and effective challenge | Extensive board engagement and input into CCAR process | Board key capital planning decision calendar and schedule | Jon Watson | TBD | No | Deveoped overall board interaction schedule and model |  | Approved by [X] committee | [7 empty] | Medium | Medium
CCAR | Documentation | Develop common documentation standards and templates | Developed document landscape consisting of key document categories | Jon Watson | TBD | No | Identified the universe of document categories (e.g., capital planning and policy) |  | Collaborated with process/category owners to define the document types per category |  | Syndicated completeness of document landscape (across processes and within process steps / events) with process owners and overarching CCAR central team | [5 empty] | Medium | Low
CCAR | Documentation | Develop common documentation standards and templates | Documentation standards, procedures and templates across the documentation landscape | Jon Watson | TBD | No | For each document in the landscape, defined level of document granularity, type of descriptions required ((e.g., actions, processes, events), and type of explanation (e.g., analysis, decision-making / rationale) |  | Syndicate documentation standards with CCAR central team to ensure documentation standards are aligned with FRB expectations |  | Syndicated / disseminated document standards with process owners witin workstreams |  | Adapted models and processes to ensure capture of documents to the established standards (e.g., altered granularity of models to ensure documentation granularity) |  |  |  | Medium | Low
CCAR | Documentation | Develop common documentation standards and templates | Developed a centralized inventory for documents, with clear organization scheme and owners attached | Jon Watson | TBD | Yes | Identified central storage warehouse for documents |  | Defined organization scheme for documents (e.g., by Y 14A line item, v. legal entity) |  | Defined ownership for each document in each category |  | Defined owner roles and responsibilities |  | Trained owners on orgnization scheme and inventory access |  | Medium | Medium
CCAR | Documentation | Create centralized documentation aggregation and review process | Detailed documentation hand-off process including calendar of hand-offs and dates | Jon Watson | TBD | No | Developed calendar of review and challenge sessions in line with |  | Defined steps in review process for incorporating feedback, correctionsm and controls to ensure evidence of review is incorporated |  | Mapped out detailed documentation hand-off process, including calendar of hand-offs and R&C session, with dates for submission | [5 empty] | Medium | Low
CCAR | Documentation | Create centralized documentation aggregation and review process | Established central oversight to own document aggregation | Jon Watson | TBD | No | Defined ownership of and accountability for dcoumentation process |  | Assigned central team documentation liaisons in each core documentation area | [7 empty] | Medium | Medium
CCAR | E2E process and controls | Redesign and centralization of the CCAR end-to-end process | Developed spreadsheet inventory and standardized controls | Jon Watson | TBD | No | Compiled list of all spreadsheets used in each CCAR process |  | Defined organization scheme for spreadsheets (e.g., by Y 14A line item, v. legal entity) |  | Assessed criticality of each spreadsheet for classification and prioritization |  | Identified, implemented and documented all required control points |  | Defined a minimum set of spreadsheet controls (e.g., password protection) and applied to all spreadsheets |  | High | High
CCAR | E2E process and controls | Restructure CCAR organization and improve staffing | Centralized oversight and execution of CCAR cycle run process within CCAR workstream | Jon Watson | TBD | No | Established oversight governance, i.e., CCAR leadership / oversight, decision-making, reporting lines, and escalation process |  | Defined responsibilities of oversight team (e.g., process design, change management and issue tracking) | [7 empty] | High | High
CCAR | E2E process and controls | Restructure CCAR organization and improve staffing | Implemented change management process led by dedicated team | Jon Watson | TBD | No | Defined change management team responsibilities: identification and documentation of changes and required controls |  | Defined process for managing changes and internal controls |  | Established ownership / leadership of change management process | [5 empty] | High | High
CCAR | E2E process and controls | Develop new internal controls framework and testing procedures | Developed an enhanced internal controls framework and testing plan | Jon Watson | TBD | No | Defined CCAR requirements for internal controls |  | Defined critical control points across CCAR cycle run process |  | Developed materiality assessment for internal control points |  | Created a governance mechanism to ensure that all control points used in the capital planning process are graded for materiality |  | Ensured robust design and testing of controls within material spreadsheets |  | Medium | Low
CCAR | E2E process and controls | Develop new internal controls framework and testing procedures | Implemented internal controls across critical control points | Jon Watson | TBD | Yes | All material controls implemented |  | All remaining controls implemented | [5 empty] | Engaged external advisors to supplement internal teams in oversight and execution |  | High | High
CCAR | E2E process and controls | Develop new internal controls framework and testing procedures | Designed and enforced governance structure to ensure consistent implementation of controls mechanisms | Jon Watson | TBD | No | Defined clear ownership of controls and review and challenge processes |  | Developed hand-off calendar with sign-off for audit and review tasks | [7 empty] | Medium | High
CCAR | E2E process and controls | Effective process for aggreagating estimates of loss revenue | Updated IT infrastructure for generation and aggregation of loss estimates | Jon Watson | TBD | Yes | Developed customized SAS aggreation tool for loss and PPNR forecasts |  | Reconciled as of data set |  | Partially implemented Moody's Scenario Analyzer |  | Increased granularily of forecasts (e.g., by business line / unit) in SAS |  |  |  | High | High
Model Development |  | In partnership with MRMG, promulgate an Enterprise Model Policy that includes standards for: Data, Model development, Documentation, Testing and implementation, Validations, Monitoring, Approvals, Provisional approvals, Operating controls, Model changes, and Third party products and services | Develop an Enterprise Model Policy | Alex Silloway and Rafic Fahs | Thu 7/2/2015 | No | Enterprise Model Policy COMPLETE and APPROVED at CART Leadership (to include Standards, Roles & Responsibilities, and a gap analysis against SR Letter 11-7) | Thu 7/16/2015 | Communication of the Enterprise Model Policy DISTRIBUTED company wide and train Model Owners, Model Developers, Model Validators and Model User | Thu 9/3/2015 | Draft procedures re: Enterprise Model Policy COMPLETE and APPROVED at Working Group (to reinforce the application of the Enterprise Model Policy for Model Developers) | Thu 9/3/2015 |  |  |  |  | Low | Low | Yes | Resources required: consulting company to do benchmark analysis and gap assessment versus SR Letter 11-7
Model Development |  | Review, and modify if needed, working group charters | Working group charters | Alex Silloway | Thu 7/2/2015 | No | Existing governance MAPPED and APPROVED (to include the following topics: Alignment on Data for Model Development, Documentation, Testing and implementation, Validations, Monitoring, Model Approvals, Provisional approvals, Operating controls, Model changes, and Third party products and services) | Fri 6/19/2015 | Charters UPDATED and COMPLETE and APPROVED at CART Leadership | Thu 7/2/2015 | Implement new charters within all working groups | Thu 7/2/2015 |  |  |  |  | Low | Low | No | 0
Model Development |  | Ensure model performance monitoring reports are being regularly generated for all tier 1 models | Model Performance Monitoring report for all tier 1 models | Alex Silloway | Thu 7/2/2015 | No | Receive from MRM final inventory of all tier 1 models | Mon 6/1/2015 | All tier 1 models not included on the model performance monitoring report prioritized & ADDED | Fri 6/19/2015 | Procedures COMPLETE establishing routines to ensure model performance monitoring reports are being regularly generated for all tier 1 models | Thu 7/2/2015 |  |  |  |  | Medium | Medium | No | 0
Model Development |  | Define a Model Development organizational structure that establishes clear lines of control between SHUSA and LOBs | Model Development Organizational Structure | Alex Silloway | Thu 7/2/2015 | No | Scope and roles & responsibilities for SHUSA Model Development group (with detailed lines of control btwn SHUSA & LOBs) COMPLETE | Thu 7/2/2015 | Model Dev Organizational Structure COMPLETE and APPROVED at CART Leadership | Thu 7/2/2015 | [6 empty] | Low | Low | Yes | Model Development resources pending Organizational Structure design
Model Development |  | Standardized skills assessments for senior analysts and managers | Standardized job descriptions across SHUSA | Alex Silloway | Thu 7/2/2015 | No | Existing job descriptions for Model Development across SHUSA MAPPED | Mon 6/8/2015 | Organization and HR job descriptions for Model Development across SHUSA reviewed with HR and APPROVED | Thu 7/2/2015 | New job descriptions for existing Model Development employess COMMUNICATED / SOCIALIZED across SHUSA | Thu 7/2/2015 |  |  |  |  | Low | Low | Yes | Resouces: Pending revised grade and comp for new Job Descriptions
Model Development |  | Assess recruiting needs and begin recruiting of qualified FTEs | New and existing resource requirement and recruitment plan | Alex Silloway | Fri 7/31/2015 | No | Comprehensive staffing assessment conducted and COMPLETE (determines skills, capabilities and areas of expertise) | Fri 6/19/2015 | Gap analysis between staffing assessment and model landscape COMPLETE | Thu 6/25/2015 | New hiring plan defined and APPROVED at CART Leadership | Thu 6/25/2015 |  |  |  |  | Low | Low | Yes | Resouces: Pending idetification of resource needs outside of Model Development group (resource of Model Development group already identified together with the definition of the new Organization Structure)
Model Development |  | Introduce Professional Qualification Standards (PQS) at the SHUSA level | Professional Qualification Standards (PQS) at the SHUSA level | Alex Silloway | Thu 10/29/2015 | No | PQS at SHUSA COMPLETE and APPROVED | Thu 10/29/2015 | Training and Implementation plan COMPLETE and APPROVED | Thu 10/29/2015 | [6 empty] | Medium | Medium | Yes | May need assistance with systems support
Model Development |  | Model Reference Library: - Establish a Model Reference Library of modeling procedures, standardized reporting templates, best practices, and other support materials to assist in the management of mathematical models - Populate the Model Reference Library with at least one “Gold Standard” document | Model Reference Library | Alex Silloway | Thu 10/29/2015 | No | Model Reference Library DEFINED (to include modeling procedures, standardized reporting templates, best practices, and other support materials to assist in the management of models) | Thu 10/29/2015 | Model Reference Library POPULATED (includes X "Gold Standard” documents) | Thu 10/29/2015 | Model Reference Library SHARED company-wide | Thu 10/29/2015 | Training Plan COMPLETE, APPROVED and IMPLEMENTED | Thu 10/29/2015 |  |  | Low | Low | Yes | Vendor may be needed to develop training plan and assist with inventory
Model Development |  | Model Landascape: - Confirm Model inventory - Assign model risk tiers (in alignment with new tiering system) - Assess model performance - Identify non-existent BAU models - Prioritize - Validate or redevelop as necessary | 2015 & 2016 Model Landascape | Alex Silloway and Rafic Fahs | Fri 7/31/2015 | Yes | Model Inventory CONFIRMED | Mon 6/8/2015 | Model Risk Tiers ASSIGNED / COMPLETE | Mon 6/15/2015 | Model development Prioritization COMPLETE | Mon 6/15/2015 | Go-forward Model Development Strategy COMPLETE (outlining the Development, validation or redevelopment of models wherever necessary) | Fri 6/26/2015 | Model Development procedures COMPLETE and APPROVED (procedures will allow MD to continue this process moving forward) | Fri 7/31/2015 | High | High | Yes | 0
Model Development |  | CCAR Models: - Strong coordination between PPNR and CCAR Credit Losses, with unified project plan - Follow approved approach, including unified decision making, to prioritize and execute CCAR Model Landscape for 2016 - Ensure alignment and appropriateness of segmentation and selection of Risk Factors - Create procedures for 70% of all CCAR modeling processes | CCAR Model Landascape for 2016 CCAR Submission | Alex Silloway | Tue 9/1/2015 | Yes | Unified project plan for PPNR and CCAR Credit Loss model development COMPLETE | Thu 7/2/2015 | Approach to prioritize the CCAR Model Development landscape for 2016 DEFINED | Mon 8/3/2015 | Procedures COMPLETE implementing recurring model performance monitoring | Tue 9/1/2015 | Procedures for 70% of all CCAR modeling processes COMPLETE and APPROVED | Tue 9/1/2015 |  |  | High | High | Yes | 0
CART- Master Program Level Deliverable Inventory

## Data Sheet
Workstream | Element | Topic | Year 1 Requirement | Column1
Data & IT | Data Quality | Data Quality | Establish Key Data Elements (KDEs) for prioritized CCAR data (including models and schedules), including documenting data dictionary and lineage, measuring and remediating data quality, deploying data controls. | Finance Transformation
Data & IT | Data Quality | Data Quality | Implement a Data Quality Center of Excellence to improve the quality of the company’s data (SHUSA and all the related US entities) by centralizing the collection of data defects, analyzing and assigning the issues causing the defects, and ensuring remediation activities are completed. | Model Development
Data & IT | Data Governance | Data Governance | Conduct a data industry maturity model assessment for SBNA, SCUSA and SHUSA to identify capability gaps that require further remediation. | Model Risk Management
Data & IT | Data Governance | Data Governance | Establish strict governance on KDEs to assess, ensure and report on compliance with data policies and standards. | Operational Risk
Data & IT | Data Governance | Data Governance | Define a comprehensive data control framework, and apply it for critical CCAR and EPS / ELS related processes | Non CART Workstream
Data & IT | Data Governance | Data Governance | Create the structure and organization of the CDO for SHUSA
Data & IT | Data Governance | Data Governance | Conduct data industry maturity model assessment for SHUSA, SBNA and SCUSA on an annual basis
Data & IT | Data Governance | Data Governance | Clearly define roles, responsibilities and ownership for data collection, quality, maintenance (Data Manager, Data Owner, Data Steward, DQ Admin, Tech Data Owner,……) as well as a list of Data Domains.
Data & IT | Data Governance | Data Governance | Organize data management roles along the three lines of defense model (Business, Chief Data Officer and Independent Audit)
Data & IT | Data Governance | Data Governance | Socialize data management program and implementation plan with key stakeholders.
Data & IT | Data Governance | Data Governance | Define domain scope and boundaries
Data & IT | Data Governance | Data Governance | Launch a SHUSA Data Governance Council attended by Data Manager, Data Owners, Data Stewards and CDO.
Data & IT | Data Governance | Data Governance | Assess and ensure compliance of SHSUA, SBNA and SCUSA practices against the Data Management Policy and Standards
Data & IT | Infosecurity | Infosecurity | IT Risk Assessment and Risk Reporting (CCAR, RCSA, ERM, MRP, OCC, HS, etc.)
Data & IT | Infosecurity | Infosecurity | Finding and Remediation Management Capability and Governance (including 2014 IT SOX Finding Remediations)
Data & IT | Infosecurity | Infosecurity | Governance: Policy, Standards, Roles and Responsibilities Development (EPAP, RTS)
Data & IT | Infosecurity | Infosecurity | Identity and Access Management Solution (SailPoint for Attestation, Access Request)
Data & IT | Infosecurity | Infosecurity | Data Flow Control from Upstream Feeders into Golden Sources and from Golden Sources to Downstream Reporting Systems
Model Development | Governance Tools | Governance Tools | In partnership with MRMG, promulgate an Enterprise Model Policy that includes standards for: Data, Model development, Documentation, Testing and implementation, Validations, Monitoring, Approvals, Provisional approvals, Operating controls, Model changes, and Third party products and services
Model Development | Governance Tools | Governance Tools | Review, and modify if needed, working group charters
Model Development | Governance Tools | Governance Tools | Best Practices Library
Model Development | Governance Tools | Governance Tools | Ensure model performance monitoring reports are being regularly generated for all tier 1 models
Model Development | Governance Tools | Governance Tools | Define a Model Development organizational structure that establishes clear lines of control between SHUSA and LOBs
Model Development | Governance Tools | Governance Tools | LOB Modeling Frameworks and Procedures
Model Development | Governance Tools | Governance Tools | Templates, checklists, and other standardized (but adaptable) controls
Model Development | Professional Development | Professional Development | Develop standardized job descriptions across SHUSA (e.g. Analyst Level I, Analyst Level II, etc.)
Model Development | Professional Development | Professional Development | Assess recruiting needs and begin recruiting of qualified FTEs
Model Development | Professional Development | Professional Development | Standardized skills assessments for senior analysts and managers
Model Development | Professional Development | Professional Development | Introduce Professional Qualification Standards (PQS) at the SHUSA level
Model Development | Professional Development | Professional Development | Classroom and online training
Model Development | Professional Development | Professional Development | Establish Model Forum
Model Development | CCAR | CCAR | FRB letter gap analysis
Model Development | CCAR | CCAR | Inventory of models needed for CCAR 2016
Model Development | CCAR | CCAR | Construct at least one set of models with dual CCAR and business purposes
Model Development | CCAR | CCAR | Demonstrate substantial improvement on Model Development
Operational Risk | Risk Appetite | SHUSA Operational Risk Tolerance Statement | Simplify SHUSA Operational Risk Tolerance Statement Limits
Operational Risk | Risk Appetite | SHUSA Operational Risk Tolerance Statement | Align with Capital Measures described in the Basel Consultative document (Total Potential OR Losses as a % of Gross Income, Single OR Loss Event > $10MM)
Operational Risk | Governance & Organization | Establish a SHUSA Operational Risk Management Framework | Establish a SHUSA Operational Risk Management Framework (Develop ORM principles, 3 LoD roles and responsibilities, SHUSA ORM organizational structure, ORM ERM methodology)
Operational Risk | Governance & Organization | Enhance Ops Risk Policies | Perform gap analysis of policy inventory in line with regulatory guidance supporting SHUSA policy requirements
Operational Risk | Governance & Organization | Enhance Ops Risk Policies | Update SHUSA enterprise Ops Risk policies as required
Operational Risk | Governance & Organization | Training & Awareness | Gap analysis to identify training needs for staff of SHUSA and Subsidiaries with respect to SHUSA enterprise Ops Risk policies and standards
Operational Risk | Governance & Organization | Establish Ops Risk Operating Model | Establish essential standards in line with the SHUSA Enterprise Operational Risk Management Policy
Operational Risk | Governance & Organization | Establish Ops Risk Operating Model | Determine OR organizational structure between SHUSA and Subsidiaries
Operational Risk | Governance & Organization | Establish Ops Risk Operating Model | Determine and select short-term / medium-term resource requirements (internal and external) to deliver Year 1/2/3 priorities
Operational Risk | Governance & Organization | Establish Ops Risk Operating Model | Recruit and onboard necessary talent
Operational Risk | Risk Measurement | Risk Identification and Assessment Design & Implementation | Establish the process to enforce and improve the identification and management of open issue and remediation efforts
Operational Risk | Risk Measurement | Risk Identification and Assessment Design & Implementation | Implement the issue management tool for the identification, capture and management of issues
Operational Risk | Risk Measurement | Material Event Escalation Process | Review the Material/Significant Event thresholds in line with peer institutions
Operational Risk | Risk Measurement | Enhance/Refine ORM Risk Identification and Assessment Tools and Processes | Review, evaluate and select RCSA methodology based on industry standards
Operational Risk | Risk Measurement | Enhance/Refine ORM Risk Identification and Assessment Tools and Processes | Review, evaluate and select RCSA methodology based on industry standards
Operational Risk | Risk Measurement | Scenario Analysis Tool | Evaluate Scenario Analysis Tools and Processes
Operational Risk | Risk Measurement | Scenario Analysis Tool | Complete scenario analysis program for SHUSA and Subsidiaries
Operational Risk | Risk Measurement | ORM Modeling Tool | Complete CCAR OR Loss Estimates
Operational Risk | Risk Measurement | ORM Modeling Tool | Refine operational risk loss forecasting model - Internal/External Loss Data Tools and Processes
Operational Risk | Risk Measurement | ORM Modeling Tool | Improve manual processes for OR Loss Event/Incident identification and collection
Operational Risk | Risk Measurement | Enhance IRM Assessment Tools and Processes | Refine methodology to focus on emerging threats and vulnerabilities
Operational Risk | Risk Measurement | Enhance IRM Assessment Tools and Processes | Evaluate threats and changes across regulatory landscape and industry standards
Operational Risk | Risk Measurement | Enhance IRM Assessment Tools and Processes | Develop and automate assessment processes
Operational Risk | Risk Measurement | Enhance/Refine VRM Assessment Tools and Processes | Refine methodology to focus on emerging threats and vulnerabilities
Operational Risk | Risk Measurement | Enhance/Refine VRM Assessment Tools and Processes | Evaluate threats and changes across regulatory landscape and industry standards
Operational Risk | Risk Measurement | Enhance/Refine VRM Assessment Tools and Processes | Refine Third Party Inherent Risk Classification methodology to determine scope and frequency of third party reviews
Operational Risk | Risk Measurement | Enhance/Refine VRM Assessment Tools and Processes | Complete the new Inherent Risk Classification questionnaire for critical third party services
Operational Risk | Risk Measurement | Enhance/Refine VRM Assessment Tools and Processes | Perform onsite reviews for all critical third parties (scope/frequency will be driven by inherent risk questionnaire)
Operational Risk | Risk Measurement | Enhance/Refine VRM Assessment Tools and Processes | Develop and automate assessment processes
Operational Risk | Risk Measurement | Enhance/Refine BCM Assessment Tools and Processes | Review for program changes as a result of regulatory and SHUSA Policy changes
Operational Risk | Risk Measurement | Enhance/Refine BCM Assessment Tools and Processes | Review and refine existing Business Impact Analysis (BIA) of SBNA and SCUSA
Operational Risk | Risk Measurement | Enhance/Refine BCM Assessment Tools and Processes | Identify gaps from current BIAs for SBNA and SCUSA critical processes, applications and testing
Operational Risk | Risk Measurement | Enhance/Refine BCM Assessment Tools and Processes | Review existing exercise results for each SBNA and SCUSA
Operational Risk | Risk Management | Update Internal Reporting | Continue to complete the baseline Ops Risk dashboard reporting for all Subsidiaries
Operational Risk | Risk Monitoring | Refine External Reporting | Develop timely reporting mechanisms and processes to satisfy OR Y-14Q reporting requirements
Operational Risk | Risk Monitoring | Refine External Reporting | Define automated system requirements for Ops Risk
Operational Risk | Risk Monitoring | Refine External Reporting | Hiperos roll-out in SBNA, begin implementation for New York branch
Operational Risk | Risk Monitoring | Refine External Reporting | Everbridge Crisis Management System roll-out to SHUSA and Subsidiaries
Operational Risk | Data & Systems | Data & Systems | Continue roll-out of iGRC within SBNA
Operational Risk | Data & Systems | Data & Systems | Select BCM tool across all SHUSA subsidiaries
Finance Transformation | Finance Planning and Analysis | Strategic Planning and Forecasting | Establish and execute foundational Planning and Forecasting framework including process governance, process timelines, clear roles and responsibilities and controlled approval processes
Finance Transformation | Finance Planning and Analysis | Strategic Planning and Forecasting | Execute 2015 P-18 process ensuring consistency between Strategic and Capital planning processes to create Strategic and Capital planning outputs (ownership shared with Capital Management)
Finance Transformation | Finance Planning and Analysis | Business Performance | Incorporate cost of contingent liquidity across all IHC entities
Finance Transformation | Finance Planning and Analysis | Business Performance | Create high-level cost allocation model to support organizational and product group profitability to improve accuracy of contribution and ROE reporting
Finance Transformation | Finance Planning and Analysis | SHUSA Reporting & Analysis | Finalize build out of team dedicated to define and produce SHUSA and board management reporting
Finance Transformation | Finance Planning and Analysis | SHUSA Reporting & Analysis | Definition of requirement to supporting effective management decision making at SHUSA
Finance Transformation | Finance Planning and Analysis | Target Operating Model | Define FP&A Target Operating Model (clear roles and responsibilities, ownership and governance between holdco and entities)
Finance Transformation | Finance Planning and Analysis | Target Operating Model | Define requirements to support interim and target state business, data and reporting requirements to support planning and forecasting, management reporting and multi-dimensional profitability
Finance Transformation | Finance Planning and Analysis | Target Operating Model | Technology design and rationalization based on methodology and system decisions for planning, forecasting and reporting
Finance Transformation | Finance Planning and Analysis | Target Operating Model | Develop a detailed project plan with T&O based on release schedule for target state implementation
Finance Transformation | Capital Management | Strengthen Capital planning governance and policy, and contingent capital planning and policy | Enhance capital policy and capital contingency policy to address FRS and IA feedback, satisfying ROPE and CCAR capital goals requirement
Finance Transformation | Capital Management | Strengthen Capital planning governance and policy, and contingent capital planning and policy | Enhance capital adequacy and capital planning governance
Finance Transformation | Capital Management | Strengthen Capital planning governance and policy, and contingent capital planning and policy | Establish staffing and conduct adequate training across the end-to-end CCAR review cycle
Finance Transformation | Capital Management | Strengthen Capital planning governance and policy, and contingent capital planning and policy | Develop capital expectations for IHC entities commensurate with size / complexity
Finance Transformation | Capital Management | Strengthen Capital planning governance and policy, and contingent capital planning and policy | Establish hand-off process from businesses to aggregation team, with a clearly defined operating model of sub-functions and activities to be centralized at SHUSA vs performed at each entity (specifically, NY, MIA, PR)
Finance Transformation | Capital Management | Strengthen Capital planning governance and policy, and contingent capital planning and policy | Operationalize processes for escalation to board, potential suspension of capital actions, and implementation of contingency plans (improve analysis and documentation of contingency actions)
Finance Transformation | Capital Management |  | Develop clear linkage between Risk ID and scenario generation and develop BHC specific scenarios
Finance Transformation | Capital Management | Capital policy and planning | Develop granular forecast of baseline and stress scenarios to test capital adequacy, incorporating IHC entities
Finance Transformation | Capital Management | Capital policy and planning | Enhance the structure, transparency, and control of the process that produces capital forecasts, including validated models and assumptions, to ensure capital levels meet policy thresholds/ limits under normal and stressful conditions (where stressed conditions are specific to the BHC)
Finance Transformation | Capital Management | Capital policy and planning | Fully operationalize quarterly capital adequacy assessment with senior-level decision-making rooted in credit considerations, market expectations, and regulatory requirements
Finance Transformation | Capital Management | Capital policy and planning | Develop and assess future-focused alternative capital actions, ensuring full transparency of capital ratios relative to binding limits, to present to Board
Finance Transformation | Capital Management | Capital policy and planning | Enhance Capital Plan for 2016
Finance Transformation | Capital Management | Enhance Capital management aggregation, tracking, and reporting | Develop clear linkage of Risk, Capital, liquidity, and strategic planning across reporting and Risk Tolerances
Finance Transformation | Capital Management | Enhance Capital management aggregation, tracking, and reporting | Establish enhanced monthly capital reporting / tracking
Finance Transformation | Capital Management | Enhance Capital management aggregation, tracking, and reporting | Improve financial analysis at consolidated and legal entity view
Finance Transformation | Capital Management | Enhance Capital management aggregation, tracking, and reporting | Conduct training sessions to prepare reviewers of aggregated results
Finance Transformation | Capital Management | RWA modeling and calculation methodology | Define and approve process for calculating RWA with appropriate governance, controls, and supporting documentation of RWA calculations, process and methodologies
Finance Transformation | Treasury | Operating Model | Complete execution of Target Operating Model (T.O.M.) with a focus on ALM and LRM functions
Finance Transformation | Treasury | Intraday Cash and Collateral Management | Establish local intraday cash and collateral management at each entity, and establish process for SHUSA to consolidate information and coordinate
Finance Transformation | Treasury | Intraday Cash and Collateral Management | Incorporate intraday procedures in SHUSA’s Cash Management and Funding policy and procedures
Finance Transformation | Treasury | Asset/Liability Management | Develop first version of Board-approved Enterprise and Operating policies, procedure and charter for Interest Rate Risk
Finance Transformation | Treasury | Asset/Liability Management | Enhance QRM operating environment including prudent mix of Chart of Accounts and dimensions, access controls and optimization of processes
Finance Transformation | Treasury | Stress Testing/Cash Flow Projections | Complete first round of stress testing, and re-iterate with additional scenarios once the framework is enhanced
Finance Transformation | Treasury | Stress Testing/Cash Flow Projections | Enhance stress testing assumptions, and update liquidity buffer based on results of the stress tests
Finance Transformation | Treasury | Regulatory Reporting (Treasury) | Develop capability to submit 2052a reports by 1/1/16
Finance Transformation | Treasury | Regulatory Reporting (Treasury) | U.S. LCR reporting (though not currently required, is expected to be produced as a result of the granularity of 2052a reporting)
Finance Transformation | Accounting, Tax & Reporting | SHUSA / IHC Data Consolidation | Establish a set of reconciled and clean current and historical financial data (internal sources where possible) to use for reporting and to support forecasting capabilities (CCAR and Strategic Planning)
Finance Transformation | Accounting, Tax & Reporting | SHUSA / IHC Data Consolidation | Enhance current and historical consolidation of existing SHUSA entities and all IHC entities supported by a consolidation tool with automated general ledger feeds and a robust contributor process for supplemental data with adequate distributed and centralized controls
Finance Transformation | Accounting, Tax & Reporting | SHUSA / IHC Data Consolidation | Establish effective governance and controls over Chart of Accounts for all IHC entities
Finance Transformation | Accounting, Tax & Reporting | SHUSA / IHC Data Consolidation | Improve the quality of information in the general ledger needed to complete the chart of accounts and execute reporting
Finance Transformation | Accounting, Tax & Reporting | SHUSA / IHC Data Consolidation | Improve the amount of general ledger information available from direct system feeds rather than manual processes
Finance Transformation | Accounting, Tax & Reporting | SHUSA / IHC Data Consolidation | Deployment of a uniform reconciliation tool (SHUSA and subsidiaries)
Finance Transformation | Accounting, Tax & Reporting | Data Reconciliation & Reporting Capabilities at SHUSA Level | Leverage existing reporting tools (FRS and Workiva) and new tools (Moody’s) to pull directly from HFM consolidation tool where applicable
Finance Transformation | Accounting, Tax & Reporting | Data Reconciliation & Reporting Capabilities at SHUSA Level | Reconciliation across appropriate sources of financial data for financial/regulatory reports (Y-9C, Y-14’s, SEC, and other regulatory reporting).
Finance Transformation | Accounting, Tax & Reporting | Data Reconciliation & Reporting Capabilities at SHUSA Level | Comprehensive documentation of controls over reporting process (centralized and distributed components)
Finance Transformation | Accounting, Tax & Reporting | End User Application Controls | Implement an industry standard spreadsheet control tool to address critical End User Application gaps at SHUSA and SBNA/SCUSA subsidiaries
Finance Transformation | Accounting, Tax & Reporting | Data Reconciliation & Reporting Capabilities at SHUSA Level | Report Group Results on Business Day 4
Finance Transformation | Accounting, Tax & Reporting | Operating Model | Finalize the implementation of Target Operating Model
Finance Transformation | Accounting, Tax & Reporting | Operating Model | Uniform application of accounting policies across subsidiaries (was part of IHC plan)
Finance Transformation | Accounting, Tax & Reporting | Data Reconciliation & Reporting Capabilities at SHUSA Level | Improve efficiency of Regulatory Report production (Incorporate all legacy systems not completed as part of the original FRS implementation).
Finance Transformation | Internal Controls | Operating Model | Finalize implementation of target operating model
Finance Transformation | Internal Controls | Operating Model | Development and/or enhancement of framework and methodology governing SOX, CCAR and EUA for SHUSA
Finance Transformation | Internal Controls | Implement programs to roll-out internal controls operating model | Implement SOX, CCAR, and EUA programs to manage the internal controls contruct and environment at SHUSA and all subsidiaries
Finance Transformation | Internal Controls | Reporting & Tools | Implementation of common software tools such as Cluster7 and Archer to manage the documentation, monitoring, evaluation, governance and reporting of internal control across all IHC entities
Risk Transformation | Re-design and embed Risk Appetite Statement | Re-design RAS for SHUSA enterprise | Re-design RAS for SHUSA enterprise
Risk Transformation | Re-design and embed Risk Appetite Statement | Re-design RAS for SHUSA enterprise | RAS reporting, breach escalation and breach penalty mechanism
Risk Transformation | Re-design and embed Risk Appetite Statement | Re-design RAS for SHUSA enterprise | Preliminary RAS communication and socialization materials
Risk Transformation | Re-design and embed Risk Appetite Statement | Cascaded RAS at subsidiary, BU levels and individual risk types | Cascade RAS to priority subsidiaries
Risk Transformation | Re-design and embed Risk Appetite Statement | Cascaded RAS at subsidiary, BU levels and individual risk types | RAS for all subsidiaries/BUs (aligned with overall SHUSA RAS)
Risk Transformation | Re-design and embed Risk Appetite Statement | Cascaded RAS at subsidiary, BU levels and individual risk types | RAS reporting, breach escalation and breach penalty mechanism (cascaded version)
Risk Transformation | Re-design and embed Risk Appetite Statement | Embed RAS in material processes | Board Risk Committee Training
Risk Transformation | Strengthen Board and Management oversight | Strengthen SHUSA Committee guidance | Strengthen SHUSA Board and Management Committee guidance
Risk Transformation | Strengthen Board and Management oversight | Strengthen SHUSA Committee guidance | Formalize engagement model between SHUSA and Parent Group
Risk Transformation | Strengthen Board and Management oversight | Strengthen SHUSA Committee guidance | Board Risk Committee reporting
Risk Transformation | Strengthen Board and Management oversight | Strengthen SHUSA Committee guidance | Updated committee composition, mandates, charters and compensation structure for high priority committees
Risk Transformation | Strengthen Board and Management oversight | Set a strong ‘Tone at the top | Revised and consistent risk-related messaging (link to articulation of ‘risk culture’):
Risk Transformation | Strengthen Board and Management oversight | Develop link between risk mgt. and performance assessment and compensation | Risk based / risk aware performance assessments and compensation framework and principles:
Risk Transformation | Strengthen Board and Management oversight | Continue and enhance Risk training for the Board Risk Committee | Risk training curriculum and schedule for Board Risk Committee including: (Training Materials, Detailed risk training objectives, Assessment and improvement process, Delivery)
Risk Transformation | Enhance Limits and Controls Framework | Review and update credit process controls and limits for underwriting and origination | High level review of credit process limits / controls
Risk Transformation | Enhance Limits and Controls Framework | Define risk oversight framework for IRR / liq. risk | Framework for risk oversight of key IRR and liquidity risk assumptions and parameters
Risk Transformation | Re-design operating model and talent management | Rationalize risk org structure | Future risk organizational model for SHUSA / subsidiaries
Risk Transformation | Re-design operating model and talent management | Rationalize risk org structure | Design risk management organizational structure in accordance with 3LoD principles
Risk Transformation | Re-design operating model and talent management | Rationalize risk org structure | Recruit priority staff
Risk Transformation | Re-design operating model and talent management | Rationalize risk org structure | Communication materials to convey org. changes to enterprise
Risk Transformation | Re-design operating model and talent management | Articulate and embed 3LoD principles | Updated articulation of risk management roles and responsibilities across the three lines
Risk Transformation | Re-design operating model and talent management | Articulate and embed 3LoD principles | Training materials to explain model and key changes
Risk Transformation | Re-design operating model and talent management | Articulate and embed 3LoD principles | Implementation of risk management organizational structure in accordance with 3LoD principles
Risk Transformation | Re-design operating model and talent management | Design risk staff recruitment / retention strategy and onboard talent | Development and execution of Phase 1 Talent Management Strategy,
Risk Transformation | Re-design operating model and talent management | Improve risk culture | Risk culture assessment across the organization
Risk Transformation | Create/update policies and procedures | Improve effectiveness of policies and procedures | Improve effectiveness of policies and procedures
Risk Transformation | Create/update policies and procedures | Improve effectiveness of policies and procedures | Frameworks defined and approved across all risk types
Risk Transformation | Create/update policies and procedures | Improve effectiveness of policies and procedures | Policy attestation process
Risk Transformation | Create effective risk identification and assessment process | Enhance risk identification and assessment process | Enhance risk identification and assessment process
Risk Transformation | Create effective risk identification and assessment process | Enhance risk identification and assessment process | Defined risk ID and assessment process, integrated into the end-to-end CCAR process:
Risk Transformation | Create effective risk identification and assessment process | Enhance risk identification and assessment process | Initial register of risks, encompassing both modeled and non-modeled risks across all relevant legal entities / BUs
Risk Transformation | Create effective risk identification and assessment process | Enhance risk identification and assessment process | Policy/procedure for Risk Identification and Assessment cycle (specifying frequency, stakeholders, duration, approvals, etc.)
Risk Transformation | Create effective risk identification and assessment process | Enhance risk identification and assessment process | Demonstrated linkage of risk ID process to capital planning (CCAR) process
Risk Transformation | Create effective risk identification and assessment process | Enhance risk identification and assessment process | Demonstrated linkage of risk ID process to risk mitigation, management and reporting
Risk Transformation | Design & Operationalize Financial Risk Management | Align credit risk mgt. activities alignment with 3LOD roles | Conduct high level credit risk review and deliver quick wins
Risk Transformation | Design & Operationalize Financial Risk Management | Align credit risk mgt. activities alignment with 3LOD roles | Definition of credit-related roles and responsibilities and lines of control across 3LoD
Risk Transformation | Design & Operationalize Financial Risk Management | Align credit risk mgt. activities alignment with 3LOD roles | Initial roll-out of 3LOD across credit risk management
Risk Transformation | Design & Operationalize Financial Risk Management | Define expected liquidity risk capabilities and conduct gap analysis | Create IRR and Liquidity Risk framework
Risk Transformation | Design & Operationalize Financial Risk Management | Define expected liquidity risk capabilities and conduct gap analysis | Conduct liquidity risk gap analysis
Risk Transformation | Design & Operationalize Financial Risk Management | Define expected liquidity risk capabilities and conduct gap analysis | Improvement of liquidity stress-testing
Risk Transformation | Design & Operationalize other non- Financial Risk Management | Design & Operationalize other non- Financial Risk Management | Conduct Compliance Risk Management Framework Review
Risk Transformation | Design & Operationalize other non- Financial Risk Management | Design & Operationalize other non- Financial Risk Management | Conduct Reputational / Strategic Risk Management Framework Review
Risk Transformation | Design & Operationalize other non- Financial Risk Management | Design & Operationalize other non- Financial Risk Management | Conduct new Product / New Business process Review
Risk Transformation | Design & Operationalize other non- Financial Risk Management | Design & Operationalize other non- Financial Risk Management | Execute Compliance Risk Mgt. Remediation Plan
Risk Transformation | Design & Operationalize other non- Financial Risk Management | Design & Operationalize other non- Financial Risk Management | Execute New Product / New Business Remediation Plan
Risk Transformation | Update internal monitoring and reporting | Define risk reporting landscape | Enhance internal reporting
Risk Transformation | Update internal monitoring and reporting | Define risk reporting landscape | Update internal monitoring process
Risk Transformation | Update internal monitoring and reporting | Define risk reporting landscape | Risk reporting landscape, by audience and risk type
Risk Transformation | Update internal monitoring and reporting | Develop and socialize prototype reports | Prototype reports and socialization of high priority reports to Board & Senior Management
Risk Transformation | Update internal monitoring and reporting | Develop business requirements | Define initial business and data requirements
Risk Transformation | Update internal monitoring and reporting | Develop business requirements | Identification of risk aggregation needs to support reporting
Risk Transformation | Update internal monitoring and reporting | Determine resourcing needs to produce reports | Reporting resourcing
Risk Transformation | Improve data quality and aggregation and strengthen systems infrastructure | Create business and data requirements | Requirements defined for all data-related risk measurement, management, and reporting activities
Risk Transformation | Improve data quality and aggregation and strengthen systems infrastructure | Create business and data requirements | Prioritization of data requirements, both within and across individual business requirement documents
Risk Transformation | Improve data quality and aggregation and strengthen systems infrastructure | Define systems architecture to support data needs | Review current systems architecture and identify improvements
Model Risk Management | Governance Oversight and Reporting | Strengthen oversight of the MRM framework by the Board and senior management | Provide training on MRM regulatory requirements and industry practices (Board, BERC, EMC)
Model Risk Management | Governance Oversight and Reporting | Strengthen oversight of the MRM framework by the Board and senior management | Inform Board and Sen. Mgt on MRM regulatory requirements and industry practices (Board, BERC, ERMC, EMC)
Model Risk Management | Governance Oversight and Reporting | Strengthen oversight of the MRM framework by the Board and senior management | Clarify the roles of BERC, ERMC, EMC, MRMC in MRM. Revise committee charters and mandates to strengthen MRM o/s role
Model Risk Management | Governance Oversight and Reporting | Enhance Model Risk Reporting | Enhance model risk remediation reporting, governance, controls
Model Risk Management | Governance Oversight and Reporting | Enhance Model Risk Reporting | Enhance model risk BAU reporting standards. Deliver enhanced reporting (including Sen Leadership & Board)
Model Risk Management | Governance Oversight and Reporting | Enhance Model Risk Reporting | Develop model risk workstream (CART) reporting, governance, controls
Model Risk Management | Governance Oversight and Reporting | Enhance Model Risk Reporting | Define requirements for long term Model Inventory and Reporting system. Conduct vendor selection
Model Risk Management | Talent and Staffing | Talent and Staffing | Hire for known staffing requirements based on volume of validation req'd
Model Risk Management | Talent and Staffing | Talent and Staffing | Conduct talent and staffing assessment for MRMG
Model Risk Management | Talent and Staffing | Talent and Staffing | Conduct First Line and auxiliary functions (IT, etc.) staffing assessment (Dependency on Model Development)
Model Risk Management | Talent and Staffing | Talent and Staffing | Develop staffing/hiring strategy (including external resources) and plan based on assessment, backlogs, and workloads
Model Risk Management | Talent and Staffing | Talent and Staffing | Implement hiring strategy/plan in partnership with the First Line/Model Development
Model Risk Management | Governance Oversight and Reporting | Governance Oversight and Reporting | Define Target Operating model (including org structure)
Model Risk Management | Talent and Staffing | Talent and Staffing | Commence hiring strategy/plan in partnership with the First Line/Model Development
Model Risk Management | SCUSA Pricing Governance and Oversight | SCUSA Pricing Governance and Oversight | Include MRMG specialist in SCUSA pricing governance
Model Risk Management | SCUSA Pricing Governance and Oversight | SCUSA Pricing Governance and Oversight | Strengthen oversight of the pricing of SCUSA retail financial products including committee charter updates
Model Risk Management | SCUSA Pricing Governance and Oversight | SCUSA Pricing Governance and Oversight | Enhance SCUSA pricing policies and procedures
Model Risk Management | MRM Policy, Procedures / Standards, Controls, and Training | Enhance MRM Policy/Procedures/Standards/Templates: | Update policy and procedure based on SR 11-7 guidance (gap analysis) including detailed model validation testing procedures
Model Risk Management | MRM Policy, Procedures / Standards, Controls, and Training | Enhance MRM Policy/Procedures/Standards/Templates: | Enhance Provisional Approval (PA) process, clarify roles and responsibilities
Model Risk Management | MRM Policy, Procedures / Standards, Controls, and Training | Enhance MRM Policy/Procedures/Standards/Templates: | Develop Framework - enhance decision making authority & roles and responsibilities for approving models and model changes (including model retirement)
Model Risk Management | MRM Policy, Procedures / Standards, Controls, and Training | Enhance MRM Policy/Procedures/Standards/Templates: | Redesign Risk Rating Methodology with a focus on repeatability, transparency, and methodology
Model Risk Management | MRM Policy, Procedures / Standards, Controls, and Training | Enhance MRM Policy/Procedures/Standards/Templates: | Redesign modelling tiering Methodology with a focus on repeatability, transparency, and methodology
Model Risk Management | MRM Policy, Procedures / Standards, Controls, and Training | Develop and deliver Training on updated Policy and Procedures | Enhance training based on updated Policy, Procedures, and Development Standards
Model Risk Management | MRM Policy, Procedures / Standards, Controls, and Training | Develop and deliver Training on updated Policy and Procedures | Train MRMG staff on the new validation procedures
Model Risk Management | MRM Policy, Procedures / Standards, Controls, and Training | Develop and deliver Training on updated Policy and Procedures | Begin targeted training on enhanced MRM Policy and Model Development Standards including training on SR 11-7 Standards and expectations (as a precursor to the Policy/Procedure rollout)
Model Risk Management | MRM Policy, Procedures / Standards, Controls, and Training | MRM Policy, Procedures / Standards, Controls, and Training | Implement Policy and Procedures/Standards
Model Risk Management | Model Validation | Address Legacy Models Validation Backlog: | Address Legacy Model Validation Backlog
Model Risk Management | Model Validation | Address Legacy Models Validation Backlog: | Conduct gap assessment (e.g. conceptual soundness, etc.)
Model Risk Management | Model Validation | Address Legacy Models Validation Backlog: | Commence Validation not completed in in the initial gap assessment and initial validation for all models. Updates to Findings Log
Model Risk Management | Model Validation | Model Validation | Evaluate internal/external model pipeline management and reporting tools/process
Model Risk Management | Model Validation | Model Validation | CCAR model validation
Model Risk Management | Data | Data | Define model data validation data and reporting requirements aligned to model risk management framework and validation standards
CART Workstream Year 1 Requirements Initiative Mapping