## Original+Required Changes
Original Plan | [7 empty] | Change Required
Outline Level | WBS | Task Name | % Complete | Duration | Start | Finish | Contact | Change type | Change required | Start | Finish | Comment | Notes on required changes
0 | 0 | RT_Risk ID and Measurement 0728 1730 | 36% | 510d? | 2015-02-02 | 2017-01-13
1 | 1 | Risk ID & Measurement | 36% | 510d? | 2015-02-02 | 2017-01-13
2 | 1.1 | Risk Measurement Deliverables | 0% | 445d | 2015-05-01 | 2017-01-13
3 | 1.1.1 | DELIVERABLE: Program Design and Approval (Risk Taxonomy, Tools, Templates, Guidance) | 100% | 0d | 2015-05-01 | 2015-05-01
3 | 1.1.2 | DELIVERABLE: SHUSA Material Risk Program | 0% | 0d | 2016-01-15 | 2016-01-15 | D. Allaire
3 | 1.1.3 | DELIVERABLE: SBNA - Business Entity Material Risk Program | 0% | 0d | 2015-10-02 | 2015-10-02 | D. Allaire | Contact | Allaire -> M. Carbone
3 | 1.1.4 | DELIVERABLE: SCUSA - Business Entity Material Risk Program | 0% | 0d | 2015-10-02 | 2015-10-02 | D. Allaire | Contact | Allaire -> T. Ploetz
3 | 1.1.5 | DELIVERABLE: New York Santander Investment Securities (SIS) - Business Entity Material Risk Program | 0% | 0d | 2015-10-02 | 2015-10-02 | D. Allaire | Contact | Allaire -> J. Bathon
3 | 1.1.6 | DELIVERABLE: Puerto Rico - Business Entity Material Risk Program | 0% | 0d | 2015-10-02 | 2015-10-02 | D. Allaire | Contact | Allaire -> Jurado
3 | 1.1.7 | DELIVERABLE: Miami - Business Entity Material Risk Program | 0% | 0d | 2015-10-02 | 2015-10-02 | D. Allaire | Contact | Allaire -> Prado
3 | 1.1.8 | DELIVERABLE: Assess Foundational Risk Processes and ensure complete Foundational Risk Inventory is in place | 0% | 0d | 2016-02-26 | 2016-02-26 | D. Allaire | Contact | Allaire -> E. Smith
3 | 1.1.9 | DELIVERABLE: Review each Foundational Risk Process; identify deficient processes, and use gap analyses to determine how to optimize processes | 0% | 0d | 2016-03-31 | 2016-03-31 | D. Allaire | Contact | Allaire -> E. Smith
3 | 1.1.10 | DELIVERABLE: Develop Foundational Risk Process remediation plan | 0% | 0d | 2016-04-27 | 2016-04-27 | D. Allaire | Contact | Allaire -> E. Smith
3 | 1.1.11 | DELIVERABLE: Updated risk taxonomy | 0% | 0d | 2016-01-15 | 2016-01-15 | D. Allaire | Contact | Allaire -> E. Smith
3 | 1.1.12 | DELIVERABLE: Updated material risk inventory template and guidance | 0% | 0d | 2016-02-26 | 2016-02-26 | D. Allaire | Contact | Allaire -> E. Smith
3 | 1.1.13 | DELIVERABLE: Identification of technology needs, requirements definition and implementation planning to support risk identification | 0% | 0d | 2016-03-31 | 2016-03-31 | D. Allaire | Contact | Allaire -> E. Smith
3 | 1.1.14 | DELIVERABLE: Training materials, policies and procedures based on updated material risk program process | 0% | 0d | 2016-06-17 | 2016-06-17 | D. Allaire | Contact | Allaire -> E. Smith
3 | 1.1.15 | DELIVERABLE: Development and implementation of planned data and technology solutions (e.g. automated interfaces for risk inventory template, database for foundational inputs and data sources for risk identification, etc) | 0% | 0d | 2016-11-15 | 2016-11-15 | D. Allaire | Delete | remove from plan |  |  |  | In the slide to Fed
3 | 1.1.16 | DELIVERABLE: Training materials, policies and procedures for risk ID database and process | 0% | 0d | 2017-01-13 | 2017-01-13 | D. Allaire
2 | 1.2 | Design and execute the Material Risk Program across SHUSA (leveraging existing data and technology) | 44% | 250d | 2015-02-02 | 2016-01-15 | D. Allaire
3 | 1.2.1 | DELIVERABLE: Design material risk program and obtain approvals (incl. risk taxonomy, tools, templates, guidance) | 100% | 65d | 2015-02-02 | 2015-05-01 | D. Allaire
4 | 1.2.1.1 | MILESTONE: Program Design and Approval (Risk Taxonomy, Tools, Templates, Guidance) | 100% | 65d | 2015-02-02 | 2015-05-01
3 | 1.2.2 | DELIVERABLE: Create risk inventory for the SHUSA, hold workshops for aggregation | 0% | 75d | 2015-10-05 | 2016-01-15 | D. Allaire
4 | 1.2.2.1 | MILESTONE: Preparation for Aggregation to Create SHUSA Material Risk Inventory | 0% | 11d | 2015-10-05 | 2015-10-19 |  | Date Change |  | 2015-09-01 | 2015-09-09 |  | Start/Finish one month early; rationale behind?
5 | 1.2.2.1.1 | ERM Collects Risk Inventories from Entity Risk Managers | 0% | 5d? | 2015-10-05 | 2015-10-09 |  | Delete | Remove detail |  |  | Unnecessary detail complicates the plan | Rationale behind deleting?
5 | 1.2.2.1.2 | ERM Sorts risks and groups by Risk Type | 0% | 5d? | 2015-10-05 | 2015-10-09 |  | Delete | Remove detail |  |  | Unnecessary detail complicates the plan
5 | 1.2.2.1.3 | ERM Creates pre-Workshop, pre-read Materials and instructions for SHUSA Risk Managers | 0% | 5d? | 2015-10-05 | 2015-10-09 |  | Delete | Remove detail |  |  | Unnecessary detail complicates the plan
5 | 1.2.2.1.4 | ERM Distributes Workshop Materials to Responsible parties | 0% | 5d? | 2015-10-05 | 2015-10-09 |  | Delete | Remove detail |  |  | ERM creates and distributes
5 | 1.2.2.1.5 | Aggregation to Create SHUSA Material Risk Inventory Prepared | 0% | 0d | 2015-10-19 | 2015-10-19 | D. Mael | Delete | Remove detail |  |  | Unnecessary detail complicates the plan
4 | 1.2.2.2 | MILESTONE: Hold SHUSA Aggregation Workshops (include 2nd LOD challenge) | 0% | 11d | 2015-10-12 | 2015-10-26 |  | Date Change |  | 2015-09-01 | 2015-09-30 |  | Start/Finish one month early
5 | 1.2.2.2.1 | TASK: Credit Risk Material Risk Aggregation | 0% | 11d? | 2015-10-12 | 2015-10-26 |  | Date Change |  | 2015-09-01 | 2015-09-30 |  | Start/Finish one month early
6 | 1.2.2.2.1.1 | Credit Risk performs pre-Read and analysis | 0% | 4d? | 2015-10-12 | 2015-10-15 |  | Delete | Remove detail |  |  | Red until more info
6 | 1.2.2.2.1.2 | Risk Managers Conduct Credit pre-Workshop Enrichment and Aggregation Activites | 0% | 4d? | 2015-10-12 | 2015-10-15 |  | Delete | Remove detail |  |  | Red until more info
6 | 1.2.2.2.1.3 | ERM facilitates Credit Aggregation and Enrichment Workshop | 0% | 11d? | 2015-10-12 | 2015-10-26 |  | Delete | Remove detail |  |  | Red until more info
6 | 1.2.2.2.1.4 | Present to Level II Subcommittees | 0% | 2d? | 2015-10-12 | 2015-10-13 |  | Delete | Remove detail |  |  | Red until more info
6 | 1.2.2.2.1.5 | Credit Risk Material Risk Aggregation Prepared | 0% | 0d | 2015-10-12 | 2015-10-12 | K. Martelon | Delete | Remove detail |  |  | Red until more info
5 | 1.2.2.2.2 | TASK: Operational Risk Material Risk Aggregation | 0% | 11d? | 2015-10-12 | 2015-10-26 |  | Date Change |  | 2015-09-01 | 2015-09-30 | Red until more info | Start/Finish one month early
6 | 1.2.2.2.2.1 | Operational Risk performs pre-Read and analysis | 0% | 4d? | 2015-10-12 | 2015-10-15 |  | Delete | Remove detail |  |  | Red until more info
6 | 1.2.2.2.2.2 | Risk Managers Conduct Operational Risk pre-Workshop Enrichment and Aggregation Activites | 0% | 4d? | 2015-10-12 | 2015-10-15 |  | Delete | Remove detail |  |  | Red until more info
6 | 1.2.2.2.2.3 | ERM facilitates Operational Risk Aggregation and Enrichment Workshop | 0% | 11d? | 2015-10-12 | 2015-10-26 |  | Delete | Remove detail |  |  | Red until more info
6 | 1.2.2.2.2.4 | Present to Level II Subcommittees | 0% | 2d? | 2015-10-12 | 2015-10-13 |  | Delete | Remove detail |  |  | Red until more info
6 | 1.2.2.2.2.5 | Operational Risk Material Risk Aggregation Prepared | 0% | 0d | 2015-10-12 | 2015-10-12 | J. Christie | Delete | Remove detail |  |  | Red until more info
5 | 1.2.2.2.3 | TASK: Compliance Material Risk Aggregation | 0% | 11d? | 2015-10-12 | 2015-10-26 |  | Date Change |  | 2015-09-01 | 2015-09-30 | Red until more info | Start/Finish one month early
6 | 1.2.2.2.3.1 | Compliance performs pre-Read and analysis | 0% | 4d? | 2015-10-12 | 2015-10-15 |  | Delete | Remove detail |  |  | Red until more info
6 | 1.2.2.2.3.2 | Risk Managers Conduct Compliance pre-Workshop Enrichment and Aggregation Activites | 0% | 4d? | 2015-10-12 | 2015-10-15 |  | Delete | Remove detail |  |  | Red until more info
6 | 1.2.2.2.3.3 | ERM facilitates Compliance Aggregation and Enrichment Workshop | 0% | 11d? | 2015-10-12 | 2015-10-26 |  | Delete | Remove detail |  |  | Red until more info
6 | 1.2.2.2.3.4 | Present to Level II Subcommittees | 0% | 2d? | 2015-10-12 | 2015-10-13 |  | Delete | Remove detail |  |  | Red until more info
6 | 1.2.2.2.3.5 | Compliance Material Risk Aggregation Prepared | 0% | 0d | 2015-10-12 | 2015-10-12 | J. Christie | Delete | Remove detail |  |  | Red until more info
5 | 1.2.2.2.4 | TASK: Model Material Risk Aggregation | 0% | 11d? | 2015-10-12 | 2015-10-26 |  | Date Change |  | 2015-09-01 | 2015-09-30 | Red until more info | Start/Finish one month early
6 | 1.2.2.2.4.1 | Model Risk performs pre-Read and analysis | 0% | 4d? | 2015-10-12 | 2015-10-15 |  | Delete | Remove detail |  |  | Red until more info
6 | 1.2.2.2.4.2 | Risk Managers Conduct Model pre-Workshop Enrichment and Aggregation Activites | 0% | 4d? | 2015-10-12 | 2015-10-15 |  | Delete | Remove detail |  |  | Red until more info
6 | 1.2.2.2.4.3 | ERM facilitates Model Aggregation and Enrichment Workshop | 0% | 11d? | 2015-10-12 | 2015-10-26 |  | Delete | Remove detail |  |  | Red until more info
6 | 1.2.2.2.4.4 | Present to Level II Subcommittees | 0% | 2d? | 2015-10-12 | 2015-10-13 |  | Delete | Remove detail |  |  | Red until more info
6 | 1.2.2.2.4.5 | Model Material Risk Aggregation Prepared | 0% | 0d | 2015-10-12 | 2015-10-12 | D. Mael | Delete | Remove detail |  |  | Red until more info
5 | 1.2.2.2.5 | TASK: Market Material Risk Aggregation2 | 0% | 11d? | 2015-10-12 | 2015-10-26 |  | Date Change |  | 2015-09-01 | 2015-09-30 | Red until more info | Start/Finish one month early
6 | 1.2.2.2.5.1 | Market Risk performs pre-Read and analysis | 0% | 4d? | 2015-10-12 | 2015-10-15 |  | Delete | Remove detail |  |  | Red until more info
6 | 1.2.2.2.5.2 | Risk Managers Conduct Market pre-Workshop Enrichment and Aggregation Activites | 0% | 4d? | 2015-10-12 | 2015-10-15 |  | Delete | Remove detail |  |  | Red until more info
6 | 1.2.2.2.5.3 | ERM facilitates Market Aggregation and Enrichment Workshop | 0% | 11d? | 2015-10-12 | 2015-10-26 |  | Delete | Remove detail |  |  | Red until more info
6 | 1.2.2.2.5.4 | Present to Level II Subcommittees | 0% | 2d? | 2015-10-12 | 2015-10-13 |  | Delete | Remove detail |  |  | Red until more info
6 | 1.2.2.2.5.5 | Market Material Risk Aggregation Prepared | 0% | 0d | 2015-10-12 | 2015-10-12 | R. Ballou | Delete | Remove detail |  |  | Red until more info
5 | 1.2.2.2.6 | TASK: Liquidity Material Risk Aggregation | 0% | 11d? | 2015-10-12 | 2015-10-26 |  | Date Change |  | 2015-09-01 | 2015-09-30 | Red until more info | Start/Finish one month early
6 | 1.2.2.2.6.1 | Liquidity Risk performs pre-Read and analysis | 0% | 4d? | 2015-10-12 | 2015-10-15 |  | Delete | Remove detail |  |  | Red until more info
6 | 1.2.2.2.6.2 | Risk Managers Conduct Liquidity pre-Workshop Enrichment and Aggregation Activites | 0% | 4d? | 2015-10-12 | 2015-10-15 |  | Delete | Remove detail |  |  | Red until more info
6 | 1.2.2.2.6.3 | ERM facilitates Liquidity Aggregation and Enrichment Workshop | 0% | 11d? | 2015-10-12 | 2015-10-26 |  | Delete | Remove detail |  |  | Red until more info
6 | 1.2.2.2.6.4 | Present to Level II Subcommittees | 0% | 2d? | 2015-10-12 | 2015-10-13 |  | Delete | Remove detail |  |  | Red until more info
6 | 1.2.2.2.6.5 | Liquidity Material Risk Aggregation Prepared | 0% | 0d | 2015-10-12 | 2015-10-12 | R. Ballou | Delete | Remove detail |  |  | Red until more info
5 | 1.2.2.2.7 | TASK: Strategic Material Risk Aggregation | 0% | 11d? | 2015-10-12 | 2015-10-26 |  | Date Change |  | 2015-09-01 | 2015-09-30 | Red until more info | Start/Finish one month early
6 | 1.2.2.2.7.1 | Strategic Risk performs pre-Read and analysis | 0% | 4d? | 2015-10-12 | 2015-10-15 |  | Delete | Remove detail |  |  | Red until more info
6 | 1.2.2.2.7.2 | Risk Managers Conduct Strategic pre-Workshop Enrichment and Aggregation Activites | 0% | 4d? | 2015-10-12 | 2015-10-15 |  | Delete | Remove detail |  |  | Red until more info
6 | 1.2.2.2.7.3 | ERM facilitates Strategic Aggregation and Enrichment Workshop | 0% | 11d? | 2015-10-12 | 2015-10-26 |  | Delete | Remove detail |  |  | Red until more info
6 | 1.2.2.2.7.4 | Present to Level II Subcommittees | 0% | 2d? | 2015-10-12 | 2015-10-13 |  | Delete | Remove detail |  |  | Red until more info
6 | 1.2.2.2.7.5 | Strategic Material Risk Aggregation Prepared | 0% | 0d | 2015-10-12 | 2015-10-12 | K. Martelon | Delete | Remove detail |  |  | Red until more info
5 | 1.2.2.2.8 | TASK: Reputational Material Risk Aggregation | 0% | 11d? | 2015-10-12 | 2015-10-26 |  | Date Change |  | 2015-09-01 | 2015-09-30 | Red until more info | Start/Finish one month early
6 | 1.2.2.2.8.1 | Reputational Risk performs pre-Read and analysis | 0% | 4d? | 2015-10-12 | 2015-10-15 |  | Delete | Remove detail |  |  | Red until more info
6 | 1.2.2.2.8.2 | Risk Managers Conduct Reputational pre-Workshop Enrichment and Aggregation Activites | 0% | 4d? | 2015-10-12 | 2015-10-15 |  | Delete | Remove detail |  |  | Red until more info
6 | 1.2.2.2.8.3 | ERM facilitates Reputational Aggregation and Enrichment Workshop | 0% | 11d? | 2015-10-12 | 2015-10-26 |  | Delete | Remove detail |  |  | Red until more info
6 | 1.2.2.2.8.4 | Present to Level II Subcommittees | 0% | 2d? | 2015-10-12 | 2015-10-13 |  | Delete | Remove detail |  |  | Red until more info
6 | 1.2.2.2.8.5 | Reputational Material Risk Aggregation Prepared | 0% | 0d | 2015-10-12 | 2015-10-12 | K. Martelon | Delete | Remove detail |  |  | Red until more info
4 | 1.2.2.3 | MILESTONE:Execute on SHUSA Top Down Aggregation (1st and 2nd LOD executive challenge) | 0% | 11d | 2015-10-26 | 2015-11-09
5 | 1.2.2.3.1 | TASK:SHUSA Top Down Aggregation | 0% | 11d | 2015-10-26 | 2015-11-09 |  | Rename/Date Change | "Synthesis Activities Inventory" | 2015-09-30 | 2015-10-31 |  | Start one month early
6 | 1.2.2.3.1.1 | ERM consolidates risks into SHUSA Inventory | 0% | 1d | 2015-10-26 | 2015-10-26 |  | Delete | Remove detail |  |  | Red until more info
6 | 1.2.2.3.1.2 | ERM distributes inventory to SHUSA Business and Risk executives | 0% | 2d | 2015-10-26 | 2015-10-27 |  | Delete | Remove detail |  |  | Red until more info
6 | 1.2.2.3.1.3 | ERM incorporates final risks into SHUSA Inventory | 0% | 4d | 2015-10-26 | 2015-10-29 |  | Delete | Remove detail |  |  | Red until more info
6 | 1.2.2.3.1.4 | SHUSA Top Down Aggregation Prepared | 0% | 1d | 2015-11-09 | 2015-11-09 |  | Delete | Remove detail |  |  | Red until more info
4 | 1.2.2.4 | MILESTONE:Obtain approvals for Material Risks of SHUSA (final aggregation, Board and Management review and challenge) | 0% | 20d | 2015-11-09 | 2015-12-04
5 | 1.2.2.4.1 | TASK:Establish Clear Linkage of MRP Outputs to Capital Planning Scenario Design Process | 0% | 40d | 2015-10-12 | 2015-12-04 | [5 empty] | Dependencies to CCAR | From David's update 0714
6 | 1.2.2.4.1.1 | Present SHUSA Material Risks to CCAR and Capital Plan | 0% | 40d | 2015-10-12 | 2015-12-04 | [5 empty] | Dependencies to CCAR
6 | 1.2.2.4.1.2 | Deliver SHUSA Material Risks to CCAR and Capital Plan | 0% | 0d | 2015-12-04 | 2015-12-04 | [5 empty] | Dependencies to CCAR
5 | 1.2.2.4.2 | TASK:Material Risk SHUSA Approval | 0% | 20d? | 2015-11-09 | 2015-12-04
6 | 1.2.2.4.2.1 | Present SHUSA Material Risks to BERC | 0% | 20d? | 2015-11-09 | 2015-12-04
6 | 1.2.2.4.2.2 | Present SHUSA Material Risks to ERMC | 0% | 20d? | 2015-11-09 | 2015-12-04
6 | 1.2.2.4.2.3 | Material Risk SHUSA Approval | 0% | 0d | 2015-12-04 | 2015-12-04
4 | 1.2.2.5 | MILESTONE:Draft Risk ID and Assessment Policy and obtain approvals | 0% | 60d | 2015-10-26 | 2016-01-15
5 | 1.2.2.5.1 | TASK:Risk ID and Assessment Policy | 0% | 60d? | 2015-10-26 | 2016-01-15
6 | 1.2.2.5.1.1 | Risk ID and Assessment group drafts policy | 0% | 37d? | 2015-10-26 | 2015-12-15
6 | 1.2.2.5.1.2 | Risk ID and Assessment group presents draft to ERMC for approval | 0% | 26d? | 2015-12-01 | 2016-01-05
6 | 1.2.2.5.1.3 | Risk ID and Assessment group presents to Risk Committee (BERC) | 0% | 34d? | 2015-12-01 | 2016-01-15
6 | 1.2.2.5.1.4 | Risk ID and Assessment Policy | 0% | 0d | 2016-01-15 | 2016-01-15 | K. Martelon
3 | 1.2.3 | DELIVERABLE: Design and execute the Material Risk Program across SBNA | 51% | 92d | 2015-05-28 | 2015-10-02 | D. Allaire | Contact | Allaire -> M. Carbone
4 | 1.2.3.1 | MILESTONE:Preparation for Aggregation to Create Retail Banking Material Risk Inventory | 95% | 24d | 2015-06-29 | 2015-07-31
5 | 1.2.3.1.1 | TASK: Small Business Banking Material Risk Inventory | 100% | 24d | 2015-06-29 | 2015-07-31
6 | 1.2.3.1.1.1 | Deliver Final Inventory to SBNA and SHUSA ERM | 100% | 24d | 2015-06-29 | 2015-07-30
6 | 1.2.3.1.1.2 | Small Business Banking Material Risk Inventory Prepared | 100% | 0d | 2015-07-31 | 2015-07-31 | Alhadeff/Carbone | Contact | Alhadeff/Carbone -> M. Carbone
5 | 1.2.3.1.2 | TASK: Cards Material Risk Inventory | 100% | 24d | 2015-06-29 | 2015-07-31
6 | 1.2.3.1.2.1 | Deliver Final Inventory to SBNA and SHUSA ERM | 100% | 24d | 2015-06-29 | 2015-07-30
6 | 1.2.3.1.2.2 | Cards Material Risk Inventory Prepared | 100% | 0d | 2015-07-31 | 2015-07-31 | Alhadeff/Carbone | Contact | Alhadeff/Carbone -> M. Carbone
5 | 1.2.3.1.3 | TASK: Mortgages Material Risk Inventory | 100% | 24d | 2015-06-29 | 2015-07-31
6 | 1.2.3.1.3.1 | Deliver Final Inventory to SBNA and SHUSA ERM | 100% | 24d | 2015-06-29 | 2015-07-30
6 | 1.2.3.1.3.2 | Mortgages Material Risk Inventory Prepared | 100% | 0d | 2015-07-31 | 2015-07-31 | Alhadeff/Carbone | Contact | Alhadeff/Carbone -> M. Carbone
5 | 1.2.3.1.4 | TASK: Purchased Portfolios (RV/Marine) Material Risk Inventory | N/A | 24d | 2015-06-29 | 2015-07-31 |  | Delete |  |  |  | No longer LOB after re-org
6 | 1.2.3.1.4.1 | Deliver Final Inventory to SBNA and SHUSA ERM | N/A | 24d | 2015-06-29 | 2015-07-30 |  | Delete |  |  |  | No longer LOB after re-org
6 | 1.2.3.1.4.2 | Purchased Portfolios (RV/Marine) Material Risk Inventory Prepared | N/A | 0d | 2015-07-31 | 2015-07-31 | Alhadeff/Carbone | Delete |  |  |  | No longer LOB after re-org
5 | 1.2.3.1.5 | TASK: Individual Material Risk Inventory | N/A | 24d | 2015-06-29 | 2015-07-31 |  | Delete |  |  |  | No longer LOB after re-org
6 | 1.2.3.1.5.1 | Deliver Final Inventory to SBNA and SHUSA ERM | N/A | 24d | 2015-06-29 | 2015-07-30 |  | Delete |  |  |  | No longer LOB after re-org
6 | 1.2.3.1.5.2 | Individual Material Risk Inventory Prepared | N/A | 0d | 2015-07-31 | 2015-07-31 | Alhadeff/Carbone | Delete |  |  |  | No longer LOB after re-org
5 | 1.2.3.1.6 | TASK: Wealth Management Material Risk Inventory | N/A | 24d | 2015-06-29 | 2015-07-31 |  | Delete |  |  |  | No longer LOB after re-org
6 | 1.2.3.1.6.1 | Deliver Final Inventory to SBNA and SHUSA ERM | N/A | 24d | 2015-06-29 | 2015-07-30 |  | Delete |  |  |  | No longer LOB after re-org
6 | 1.2.3.1.6.2 | Wealth Management Material Risk Inventory Prepared | N/A | 0d | 2015-07-31 | 2015-07-31 | Alhadeff/Carbone | Delete |  |  |  | No longer LOB after re-org
4 | 1.2.3.2 | MILESTONE:Retail: Create Retail Banking Material Risk Inventory | 100% | 24d | 2015-06-29 | 2015-07-31
5 | 1.2.3.2.1 | TASK: Retail: Create Retail Banking Material Risk Inventory | 100% | 24d | 2015-06-29 | 2015-07-31
6 | 1.2.3.2.1.1 | Create Segment Material Risk Inventory (Aggregation) | 100% | 24d | 2015-06-29 | 2015-07-30
6 | 1.2.3.2.1.2 | Retail: Create Retail Banking Material Risk Inventory Prepared | 100% | 0d | 2015-07-31 | 2015-07-31 | Alhadeff/Carbone | Contact | Alhadeff/Carbone -> M. Carbone
4 | 1.2.3.3 | MILESTONE:Commercial Banking Material Risk Inventory | 100% | 24d | 2015-06-29 | 2015-07-31
5 | 1.2.3.3.1 | TASK: Commercial and Industrial Material Risk Inventory | 100% | 24d | 2015-06-29 | 2015-07-31
6 | 1.2.3.3.1.1 | Deliver Final Inventory to SBNA and SHUSA ERM | 100% | 24d | 2015-06-29 | 2015-07-30
6 | 1.2.3.3.1.2 | Commercial and Industrial Material Risk Inventory Prepared | 100% | 0d | 2015-07-31 | 2015-07-31 | Alhadeff/Carbone | Contact | Alhadeff/Carbone -> M. Carbone
5 | 1.2.3.3.2 | TASK: Specialties Material Risk Inventory | 100% | 24d | 2015-06-29 | 2015-07-31
6 | 1.2.3.3.2.1 | Deliver Final Inventory to SBNA and SHUSA ERM | 100% | 24d | 2015-06-29 | 2015-07-30
6 | 1.2.3.3.2.2 | Specialties Material Risk Inventory Prepared | 100% | 0d | 2015-07-31 | 2015-07-31 | Alhadeff/Carbone | Contact | Alhadeff/Carbone -> M. Carbone
5 | 1.2.3.3.3 | TASK: Government Banking Material Risk Inventory | 100% | 24d | 2015-06-29 | 2015-07-31
6 | 1.2.3.3.3.1 | Deliver Final Inventory to SBNA and SHUSA ERM | 100% | 24d | 2015-06-29 | 2015-07-30
6 | 1.2.3.3.3.2 | Government Banking Material Risk Inventory Prepared | 100% | 0d | 2015-07-31 | 2015-07-31 | Alhadeff/Carbone
4 | 1.2.3.4 | MILESTONE: Commercial: Create Commercial Banking Material Risk Inventory | 100% | 24d | 2015-06-29 | 2015-07-31
5 | 1.2.3.4.1 | TASK: Commercial: Create Commercial Banking Material Risk Inventory | 100% | 24d | 2015-06-29 | 2015-07-31
6 | 1.2.3.4.1.1 | Create Segment Material Risk Inventory (Aggregation) | 100% | 24d | 2015-06-29 | 2015-07-30
6 | 1.2.3.4.1.2 | Create Commercial Banking Material Risk Inventory Prepared | 100% | 0d | 2015-07-31 | 2015-07-31 | Alhadeff/Carbone | Contact | Alhadeff/Carbone -> M. Carbone
4 | 1.2.3.5 | MILESTONE:Global Banking Material Risk Inventory | 100% | 24d | 2015-06-29 | 2015-07-31
5 | 1.2.3.5.1 | TASK: MRG Material Risk Inventory | 100% | 24d | 2015-06-29 | 2015-07-31
6 | 1.2.3.5.1.1 | Deliver Final Inventory to SBNA and SHUSA ERM | 100% | 24d | 2015-06-29 | 2015-07-30
6 | 1.2.3.5.1.2 | MRG Material Risk Inventory Prepared | 100% | 0d | 2015-07-31 | 2015-07-31 | Alhadeff/Carbone | Contact | Alhadeff/Carbone -> M. Carbone
5 | 1.2.3.5.2 | TASK: Large Corporates Material Risk Inventory | 100% | 24d | 2015-06-29 | 2015-07-31
6 | 1.2.3.5.2.1 | Deliver Final Inventory to SBNA and SHUSA ERM | 100% | 24d | 2015-06-29 | 2015-07-30
6 | 1.2.3.5.2.2 | Large Corporates Material Risk Inventory Prepared | 100% | 0d | 2015-07-31 | 2015-07-31 | Alhadeff/Carbone | Contact | Alhadeff/Carbone -> M. Carbone
4 | 1.2.3.6 | MILESTONE:Global: Create Global Banking Material Risk Inventory | 100% | 24d | 2015-06-29 | 2015-07-31
5 | 1.2.3.6.1 | TASK: Global: Create Global Banking Material Risk Inventory | 100% | 24d | 2015-06-29 | 2015-07-31
6 | 1.2.3.6.1.1 | Create Segment Material Risk Inventory (Aggregation) | 100% | 24d | 2015-06-29 | 2015-07-30
6 | 1.2.3.6.1.2 | Global: Create Global Banking Material Risk Inventory Prepared | 100% | 0d | 2015-07-31 | 2015-07-31 | Alhadeff/Carbone | Contact | Alhadeff/Carbone -> M. Carbone
4 | 1.2.3.7 | MILESTONE:Automotive Finance Material Risk Inventory | 100% | 2d | 2015-06-29 | 2015-06-30
5 | 1.2.3.7.1 | TASK: CEVF Material Risk Inventory | 100% | 2d | 2015-06-29 | 2015-06-30
6 | 1.2.3.7.1.1 | Deliver Final Inventory to SBNA and SHUSA ERM | 100% | 2d | 2015-06-29 | 2015-06-30
6 | 1.2.3.7.1.2 | CEVF Material Risk Inventory Prepared | 100% | 0d | 2015-06-30 | 2015-06-30 | Alhadeff/Carbone | Contact | Alhadeff/Carbone -> M. Carbone
5 | 1.2.3.7.2 | TASK: Leasing Material Risk Inventory | 100% | 2d | 2015-06-29 | 2015-06-30
6 | 1.2.3.7.2.1 | Deliver Final Inventory to SBNA and SHUSA ERM | 100% | 2d | 2015-06-29 | 2015-06-30
6 | 1.2.3.7.2.2 | Leasing Material Risk Inventory Prepared | 100% | 0d | 2015-06-30 | 2015-06-30 | Alhadeff/Carbone | Contact | Alhadeff/Carbone -> M. Carbone
5 | 1.2.3.7.3 | TASK: Dealer Floor Plan Material Risk Inventory | 100% | 2d | 2015-06-29 | 2015-06-30
6 | 1.2.3.7.3.1 | Deliver Final Inventory to SBNA and SHUSA ERM | 100% | 2d | 2015-06-29 | 2015-06-30
6 | 1.2.3.7.3.2 | Dealer Floor Plan Material Risk Inventory Prepared | 100% | 0d | 2015-06-30 | 2015-06-30 | Alhadeff/Carbone | Contact | Alhadeff/Carbone -> M. Carbone
4 | 1.2.3.8 | MILESTONE: Automotive: Create Automotive Finance Material Risk Inventory | 100% | 24d | 2015-05-28 | 2015-06-30
5 | 1.2.3.8.1 | TASK: Automotive: Create Automotive Finance Material Risk Inventory | 100% | 24d | 2015-05-28 | 2015-06-30
6 | 1.2.3.8.1.1 | Create Segment Material Risk Inventory (Aggregation) | 100% | 24d | 2015-05-28 | 2015-06-30
6 | 1.2.3.8.1.2 | Automotive Finance Material Risk Inventory Prepared | 100% | 0d | 2015-06-30 | 2015-06-30 | Alhadeff/Carbone | Contact | Alhadeff/Carbone -> M. Carbone
4 | 1.2.3.9 | MILESTONE: Commerical Real Estate Material Risk Inventory | 100% | 24d | 2015-06-29 | 2015-07-31
5 | 1.2.3.9.1 | TASK: Commerical Real Estate Material Risk Inventory | 100% | 24d | 2015-06-29 | 2015-07-31
6 | 1.2.3.9.1.1 | Deliver Final Inventory to SBNA and SHUSA ERM | 100% | 24d | 2015-06-29 | 2015-07-30
6 | 1.2.3.9.1.2 | Commerical Real Estate Material Risk Inventory Prepared | 100% | 0d | 2015-07-31 | 2015-07-31 | Alhadeff/Carbone | Contact | Alhadeff/Carbone -> M. Carbone
4 | 1.2.3.10 | MILESTONE:Financial Management Material Risk Inventory | N/A | 24d | 2015-06-29 | 2015-07-31 |  | Delete |  |  |  | No longer LOB after re-org
5 | 1.2.3.10.1 | TASK: Financial Management Material Risk Inventory | N/A | 24d | 2015-06-29 | 2015-07-31 |  | Delete |  |  |  | No longer LOB after re-org
6 | 1.2.3.10.1.1 | Deliver Final Inventory to SBNA and SHUSA ERM | N/A | 24d | 2015-06-29 | 2015-07-30 |  | Delete |  |  |  | No longer LOB after re-org
6 | 1.2.3.10.1.2 | Financial Management Material Risk Inventory Prepared | N/A | 0d | 2015-07-31 | 2015-07-31 | Alhadeff/Carbone | Delete |  |  |  | No longer LOB after re-org
4 | 1.2.3.11 | MILESTONE:Corporate Center Material Risk Inventory | N/A | 24d | 2015-06-29 | 2015-07-31 |  | Delete |  |  |  | No longer LOB after re-org
5 | 1.2.3.11.1 | TASK: Corporate Center Material Risk Inventory | N/A | 24d | 2015-06-29 | 2015-07-31 |  | Delete |  |  |  | No longer LOB after re-org
6 | 1.2.3.11.1.1 | Deliver Final Inventory to SBNA and SHUSA ERM | N/A | 24d | 2015-06-29 | 2015-07-30 |  | Delete |  |  |  | No longer LOB after re-org
6 | 1.2.3.11.1.2 | Corporate Center Material Risk Inventory Prepared | N/A | 0d | 2015-07-31 | 2015-07-31 | Alhadeff/Carbone | Delete |  |  |  | No longer LOB after re-org
4 | 1.2.3.12 | MILESTONE: Legal Material Risk Inventory | 100% | 26d | 2015-06-26 | 2015-07-31
5 | 1.2.3.12.1 | TASK: Legal Material Risk Inventory | 100% | 26d | 2015-06-26 | 2015-07-31
6 | 1.2.3.12.1.1 | Deliver Final Inventory to SBNA and SHUSA ERM | 100% | 26d | 2015-06-26 | 2015-07-31
6 | 1.2.3.12.1.2 | Legal Material Risk Inventory Prepared | 100% | 1d | 2015-07-31 | 2015-07-31 | Alhadeff/Carbone | Contact | Alhadeff/Carbone -> M. Carbone
4 | 1.2.3.13 | MILESTONE:HR Material Risk Inventory | 100% | 26d | 2015-06-26 | 2015-07-31
5 | 1.2.3.13.1 | TASK: HR Material Risk Inventory | 100% | 26d | 2015-06-26 | 2015-07-31
6 | 1.2.3.13.1.1 | Deliver Final Inventory to SBNA and SHUSA ERM | 100% | 25d | 2015-06-26 | 2015-07-30
6 | 1.2.3.13.1.2 | HR Material Risk Inventory Prepared | 100% | 1d | 2015-07-31 | 2015-07-31 | Alhadeff/Carbone | Contact | Alhadeff/Carbone -> M. Carbone
4 | 1.2.3.14 | MILESTONE:Tech and Operations Material Risk Inventory | 100% | 26d | 2015-06-26 | 2015-07-31
5 | 1.2.3.14.1 | TASK: Tech and Operations Material Risk Inventory | 100% | 26d | 2015-06-26 | 2015-07-31
6 | 1.2.3.14.1.1 | Deliver Final Inventory to SBNA and SHUSA ERM | 100% | 2d | 2015-07-29 | 2015-07-30
6 | 1.2.3.14.1.2 | Tech and Operations Material Risk Inventory Prepared | 100% | 0d | 2015-07-31 | 2015-07-31 | Alhadeff/Carbone | Contact | Alhadeff/Carbone -> M. Carbone
4 | 1.2.3.15 | MILESTONE:Finance Material Risk Inventory | 100% | 24d | 2015-06-29 | 2015-07-31
5 | 1.2.3.15.1 | TASK: Finance Material Risk Inventory | 100% | 24d | 2015-06-29 | 2015-07-31
6 | 1.2.3.15.1.1 | Deliver Final Inventory to SBNA and SHUSA ERM | 100% | 24d | 2015-06-29 | 2015-07-30
6 | 1.2.3.15.1.2 | Finance Material Risk Inventory Prepared | 100% | 0d | 2015-07-31 | 2015-07-31 | Alhadeff/Carbone | Contact | Alhadeff/Carbone -> M. Carbone
4 | 1.2.3.16 | MILESTONE:Hold SBNA Aggregation Workshops (include 2nd LOD challenge) | 50% | 45d | 2015-08-03 | 2015-10-02
5 | 1.2.3.16.1 | TASK: Credit Risk Aggregation | 50% | 41d? | 2015-08-03 | 2015-09-28 |  | Date Change |  | 2015-08-01 | 2015-08-31 |  | Finish one month early
6 | 1.2.3.16.1.1 | ERM disseminates Workshop Pre-Read Materials to Risk Managers | 50% | 16d? | 2015-08-03 | 2015-08-24 |  | Delete | Remove detail |  |  | Unnecessary detail complicates the plan
6 | 1.2.3.16.1.2 | ERM facilitates Aggregation and Enrichment Activities | 50% | 25d? | 2015-08-25 | 2015-09-28 |  | Delete | Remove detail |  |  | Unnecessary detail complicates the plan
6 | 1.2.3.16.1.3 | Risk Manager presents inventory to level II subcommittee | 50% | 1d? | 2015-08-03 | 2015-08-03 |  | Delete | Remove detail |  |  | Unnecessary detail complicates the plan
6 | 1.2.3.16.1.4 | Credit Risk Aggregation Prepared | 50% | 0d | 2015-08-03 | 2015-08-03 | Alhadeff/Carbone | Delete | Remove detail |  |  | Unnecessary detail complicates the plan
5 | 1.2.3.16.2 | TASK: Operational Risk Material Risk Aggregation | 50% | 41d? | 2015-08-03 | 2015-09-28 |  | Date Change |  | 2015-08-01 | 2015-08-31 |  | Finish one month early
6 | 1.2.3.16.2.1 | ERM disseminates Workshop Pre-Read Materials to Risk Managers | 50% | 16d? | 2015-08-03 | 2015-08-24 |  | Delete | Remove detail |  |  | Unnecessary detail complicates the plan
6 | 1.2.3.16.2.2 | ERM facilitates Aggregation and Enrichment Activities | 50% | 25d? | 2015-08-25 | 2015-09-28 |  | Delete | Remove detail |  |  | Unnecessary detail complicates the plan
6 | 1.2.3.16.2.3 | Risk Manager presents inventory to level II subcommittee | 50% | 1d? | 2015-08-03 | 2015-08-03 |  | Delete | Remove detail |  |  | Unnecessary detail complicates the plan
6 | 1.2.3.16.2.4 | Operational Risk Material Risk Aggregation Prepared | 50% | 0d | 2015-08-03 | 2015-08-03 | Alhadeff/Carbone | Delete | Remove detail |  |  | Unnecessary detail complicates the plan
5 | 1.2.3.16.3 | TASK: Compliance Material Risk Aggregation | 50% | 41d? | 2015-08-03 | 2015-09-28 |  | Date Change |  | 2015-08-01 | 2015-08-31 |  | Finish one month early
6 | 1.2.3.16.3.1 | ERM disseminates Workshop Pre-Read Materials to Risk Managers | 50% | 16d? | 2015-08-03 | 2015-08-24 |  | Delete | Remove detail |  |  | Unnecessary detail complicates the plan
6 | 1.2.3.16.3.2 | ERM facilitates Aggregation and Enrichment Activities | 50% | 25d? | 2015-08-25 | 2015-09-28 |  | Delete | Remove detail |  |  | Unnecessary detail complicates the plan
6 | 1.2.3.16.3.3 | Risk Manager presents inventory to level II subcommittee | 50% | 1d? | 2015-08-03 | 2015-08-03 |  | Delete | Remove detail |  |  | Unnecessary detail complicates the plan
6 | 1.2.3.16.3.4 | Compliance Material Risk Aggregation Prepared | 50% | 0d | 2015-08-03 | 2015-08-03 | Alhadeff/Carbone | Delete | Remove detail |  |  | Unnecessary detail complicates the plan
5 | 1.2.3.16.4 | TASK: Model Material Risk Aggregation | 50% | 41d? | 2015-08-03 | 2015-09-28 |  | Date Change |  | 2015-08-01 | 2015-08-31 |  | Finish one month early
6 | 1.2.3.16.4.1 | ERM disseminates Workshop Pre-Read Materials to Risk Managers | 50% | 16d? | 2015-08-03 | 2015-08-24 |  | Delete | Remove detail |  |  | Unnecessary detail complicates the plan
6 | 1.2.3.16.4.2 | ERM facilitates Aggregation and Enrichment Activities | 50% | 25d? | 2015-08-25 | 2015-09-28 |  | Delete | Remove detail |  |  | Unnecessary detail complicates the plan
6 | 1.2.3.16.4.3 | Risk Manager presents inventory to level II subcommittee | 50% | 1d? | 2015-08-03 | 2015-08-03 |  | Delete | Remove detail |  |  | Unnecessary detail complicates the plan
6 | 1.2.3.16.4.4 | Model Material Risk Aggregation Prepared | 50% | 0d | 2015-08-03 | 2015-08-03 | Alhadeff/Carbone | Delete | Remove detail |  |  | Unnecessary detail complicates the plan
5 | 1.2.3.16.5 | TASK: Liquidity/Market Material Risk Aggregation | 50% | 41d? | 2015-08-03 | 2015-09-28 |  | Date Change |  | 2015-08-01 | 2015-08-31 |  | Finish one month early
6 | 1.2.3.16.5.1 | ERM disseminates Workshop Pre-Read Materials to Risk Managers | 50% | 16d? | 2015-08-03 | 2015-08-24 |  | Delete | Remove detail |  |  | Unnecessary detail complicates the plan
6 | 1.2.3.16.5.2 | ERM facilitates Aggregation and Enrichment Activities | 50% | 25d? | 2015-08-25 | 2015-09-28 |  | Delete | Remove detail |  |  | Unnecessary detail complicates the plan
6 | 1.2.3.16.5.3 | Risk Manager presents inventory to level II subcommittee | 50% | 1d? | 2015-08-03 | 2015-08-03 |  | Delete | Remove detail |  |  | Unnecessary detail complicates the plan
6 | 1.2.3.16.5.4 | Liquidity/Market Material Risk Aggregation Prepared | 50% | 0d | 2015-08-03 | 2015-08-03 | Alhadeff/Carbone | Delete | Remove detail |  |  | Unnecessary detail complicates the plan
5 | 1.2.3.16.6 | TASK: Reputational/Strategic Material Risk Aggregation | 50% | 41d? | 2015-08-03 | 2015-09-28 |  | Date Change |  | 2015-08-01 | 2015-08-31 |  | Finish one month early
6 | 1.2.3.16.6.1 | ERM disseminates Workshop Pre-Read Materials to Risk Managers | 50% | 16d? | 2015-08-03 | 2015-08-24 |  | Delete | Remove detail |  |  | Unnecessary detail complicates the plan
6 | 1.2.3.16.6.2 | ERM facilitates Aggregation and Enrichment Workshop | 50% | 25d? | 2015-08-25 | 2015-09-28 |  | Delete | Remove detail |  |  | Unnecessary detail complicates the plan
6 | 1.2.3.16.6.3 | Risk Manager presents inventory to level II subcommittee | 50% | 1d? | 2015-08-03 | 2015-08-03 |  | Delete | Remove detail |  |  | Unnecessary detail complicates the plan
6 | 1.2.3.16.6.4 | Reputational/Strategic Material Risk Aggregation Prepared | 50% | 0d | 2015-08-03 | 2015-08-03 | Alhadeff/Carbone | Delete | Remove detail |  |  | Unnecessary detail complicates the plan
4 | 1.2.3.17 | Present Results to SBNA ERMC | 0% | 48d | 2015-07-28 | 2015-10-01 | Alhadeff/Carbone
4 | 1.2.3.18 | Present Results to SBNA BERC | 0% | 48d | 2015-07-28 | 2015-10-01 | Alhadeff/Carbone
4 | 1.2.3.19 | Present SBNA Results to CCAR | 0% | 25d | 2015-08-31 | 2015-10-02 |  | Delete |  |  |  | Only happens at SHUSA-verify with CCAR
4 | 1.2.3.20 | Deliver SBNA Material Risks to CCAR and Capital Plan | 0% | 0d | 2015-10-02 | 2015-10-02 |  | Delete |  |  |  | Only happens at SHUSA-verify with CCAR
3 | 1.2.4 | DELIVERABLE: Design and execute the Material Risk Program across SCUSA | 2% | 92d | 2015-05-28 | 2015-10-02 | D. Allaire | Contact | Allaire -> T. Ploetz
4 | 1.2.4.1 | MILESTONE: Automotive Finance Material Risk Inventory | 8% | 25d | 2015-06-29 | 2015-07-31 |  | Date Change |  | 2015-08-01 | 2015-08-31 | New dates approved for SCUSA | Start/Finish one month late
5 | 1.2.4.1.1 | TASK:Automotive Finance Material Risk Inventory | 8% | 25d | 2015-06-29 | 2015-07-31 |  | Date Change |  | 2015-08-01 | 2015-08-31 | New dates approved for SCUSA | Start/Finish one month late
6 | 1.2.4.1.1.1 | Deliver Final Inventory to SCUSA SHUSA ERM | 4% | 25d | 2015-06-29 | 2015-07-31 |  | Delete | Remove detail |  |  | Unnecessary detail complicates the plan
6 | 1.2.4.1.1.2 | Automotive Finance Material Risk Inventory Prepared | 100% | 1d | 2015-07-31 | 2015-07-31 | Ploetz/Smith | Delete | Remove detail |  |  | Unnecessary detail complicates the plan
4 | 1.2.4.2 | MILESTONE: Personal Lending Material Risk Inventory | 8% | 25d | 2015-06-29 | 2015-07-31 |  | Date Change |  | 2015-08-01 | 2015-08-31 | New dates approved for SCUSA | Start/Finish one month late
5 | 1.2.4.2.1 | TASK:Personal Lending Material Risk Inventory | 8% | 25d | 2015-06-29 | 2015-07-31 |  | Date Change |  | 2015-08-01 | 2015-08-31 | New dates approved for SCUSA | Start/Finish one month late
6 | 1.2.4.2.1.1 | Deliver Final Inventory to SCUSA SHUSA ERM | 4% | 25d | 2015-06-29 | 2015-07-31 |  | Delete | Remove detail |  |  | Unnecessary detail complicates the plan
6 | 1.2.4.2.1.2 | Personal Lending Material Risk Inventory Prepared | 99% | 1d | 2015-07-31 | 2015-07-31 | Ploetz/Smith | Delete | Remove detail |  |  | Unnecessary detail complicates the plan
4 | 1.2.4.3 | MILESTONE: Human Resources Material Risk Inventory | 8% | 25d | 2015-06-29 | 2015-07-31 |  | Rename/Date Change | "Support Functions Inventory" | 2015-08-01 | 2015-08-31 | Change to process approved for SCUSA | Start/Finish one month late
5 | 1.2.4.3.1 | TASK:Human Resources Material Risk Inventory | 8% | 25d | 2015-06-29 | 2015-07-31 |  | Date Change |  | 2015-08-01 | 2015-08-31 | New dates approved for SCUSA | Start/Finish one month late
6 | 1.2.4.3.1.1 | Deliver Final Inventory to SCUSA SHUSA ERM | 4% | 25d | 2015-06-29 | 2015-07-31 |  | Delete | Remove detail |  |  | Unnecessary detail complicates the plan
6 | 1.2.4.3.1.2 | Human Resources Material Risk Inventory Prepared | 100% | 1d | 2015-07-31 | 2015-07-31 | Ploetz/Smith | Delete | Remove detail |  |  | Unnecessary detail complicates the plan
4 | 1.2.4.4 | MILESTONE: Finance and Accounting Material Risk Inventory | 8% | 25d | 2015-06-29 | 2015-07-31 |  | Delete |  |  |  | SCUSA not creating these inventories
5 | 1.2.4.4.1 | TASK:Finance and Accounting Material Risk Inventory | 8% | 25d | 2015-06-29 | 2015-07-31 |  | Delete |  |  |  | SCUSA not creating these inventories
6 | 1.2.4.4.1.1 | Deliver Final Inventory to SCUSA SHUSA ERM | 4% | 25d | 2015-06-29 | 2015-07-31 |  | Delete |  |  |  | SCUSA not creating these inventories
6 | 1.2.4.4.1.2 | Finance and Accounting Material Risk Inventory Prepared | 100% | 1d | 2015-07-31 | 2015-07-31 | Ploetz/Smith | Delete |  |  |  | SCUSA not creating these inventories
4 | 1.2.4.5 | MILESTONE: Technology and Operations Material Risk Inventory | 8% | 25d | 2015-06-29 | 2015-07-31 |  | Delete |  |  |  | SCUSA not creating these inventories
5 | 1.2.4.5.1 | TASK:Technology and Operations Material Risk Inventory | 8% | 25d | 2015-06-29 | 2015-07-31 |  | Delete |  |  |  | SCUSA not creating these inventories
6 | 1.2.4.5.1.1 | Deliver Final Inventory to SCUSA SHUSA ERM | 4% | 25d | 2015-06-29 | 2015-07-31 |  | Delete |  |  |  | SCUSA not creating these inventories
6 | 1.2.4.5.1.2 | Technology and Operations Material Risk Inventory Prepared | 100% | 1d | 2015-07-31 | 2015-07-31 | Ploetz/Smith | Delete |  |  |  | SCUSA not creating these inventories
4 | 1.2.4.6 | MILESTONE: Legal Material Risk Inventory | 8% | 25d | 2015-06-29 | 2015-07-31 |  | Delete |  |  |  | SCUSA not creating these inventories
5 | 1.2.4.6.1 | TASK:Legal Material Risk Inventory | 8% | 25d | 2015-06-29 | 2015-07-31 |  | Delete |  |  |  | SCUSA not creating these inventories
6 | 1.2.4.6.1.1 | Deliver Final Inventory to SCUSA SHUSA ERM | 4% | 25d | 2015-06-29 | 2015-07-31 |  | Delete |  |  |  | SCUSA not creating these inventories
6 | 1.2.4.6.1.2 | Legal Material Risk Inventory Prepared | 100% | 1d | 2015-07-31 | 2015-07-31 | Ploetz/Smith | Delete |  |  |  | SCUSA not creating these inventories
4 | 1.2.4.7 | MILESTONE: SCUSA Aggregation Workshops (include 2 LOD challenge) | 0% | 45d | 2015-08-03 | 2015-10-02 |  | Date Change |  | 2015-08-01 | 2015-08-31 | New dates approved for SCUSA | Finish one month early
5 | 1.2.4.7.1 | TASK: Credit Risk Aggregation | 0% | 41d? | 2015-08-03 | 2015-09-28 |  | Date Change |  | 2015-08-01 | 2015-08-31 | New dates approved for SCUSA | Finish one month early
6 | 1.2.4.7.1.1 | ERM disseminates Workshop Pre-Read Materials to Risk Managers | 0% | 16d? | 2015-08-03 | 2015-08-24 |  | Delete | Remove detail |  |  | Unnecessary detail complicates the plan
6 | 1.2.4.7.1.2 | ERM facilitates Aggregation and Enrichment Activities | 0% | 25d? | 2015-08-25 | 2015-09-28 |  | Delete | Remove detail |  |  | Unnecessary detail complicates the plan
6 | 1.2.4.7.1.3 | Risk Manager presents inventory to level II subcommittee | 0% | 1d? | 2015-08-03 | 2015-08-03 |  | Delete | Remove detail |  |  | Unnecessary detail complicates the plan
6 | 1.2.4.7.1.4 | Credit Risk Aggregation Prepared | 0% | 0d | 2015-08-03 | 2015-08-03 | Ploetz/Smith | Delete | Remove detail |  |  | Unnecessary detail complicates the plan
5 | 1.2.4.7.2 | TASK: Operational Risk Material Risk Aggregation | 0% | 41d? | 2015-08-03 | 2015-09-28 |  | Date Change |  | 2015-08-01 | 2015-08-31 | New dates approved for SCUSA | Finish one month early
6 | 1.2.4.7.2.1 | ERM disseminates Workshop Pre-Read Materials to Risk Managers | 0% | 16d? | 2015-08-03 | 2015-08-24 |  | Delete | Remove detail |  |  | Unnecessary detail complicates the plan
6 | 1.2.4.7.2.2 | ERM facilitates Aggregation and Enrichment Activities | 0% | 25d? | 2015-08-25 | 2015-09-28 |  | Delete | Remove detail |  |  | Unnecessary detail complicates the plan
6 | 1.2.4.7.2.3 | Risk Manager presents inventory to level II subcommittee | 0% | 1d? | 2015-08-03 | 2015-08-03 |  | Delete | Remove detail |  |  | Unnecessary detail complicates the plan
6 | 1.2.4.7.2.4 | Operational Risk Material Risk Aggregation Prepared | 0% | 0d | 2015-08-03 | 2015-08-03 | Ploetz/Smith | Delete | Remove detail |  |  | Unnecessary detail complicates the plan
5 | 1.2.4.7.3 | TASK: Compliance Material Risk Aggregation | 0% | 41d? | 2015-08-03 | 2015-09-28 |  | Date Change |  | 2015-08-01 | 2015-08-31 | New dates approved for SCUSA | Finish one month early
6 | 1.2.4.7.3.1 | ERM disseminates Workshop Pre-Read Materials to Risk Managers | 0% | 16d? | 2015-08-03 | 2015-08-24 |  | Delete | Remove detail |  |  | Unnecessary detail complicates the plan
6 | 1.2.4.7.3.2 | ERM facilitates Aggregation and Enrichment Activities | 0% | 25d? | 2015-08-25 | 2015-09-28 |  | Delete | Remove detail |  |  | Unnecessary detail complicates the plan
6 | 1.2.4.7.3.3 | Risk Manager presents inventory to level II subcommittee | 0% | 1d? | 2015-08-03 | 2015-08-03 |  | Delete | Remove detail |  |  | Unnecessary detail complicates the plan
6 | 1.2.4.7.3.4 | Compliance Material Risk Aggregation Prepared | 0% | 0d | 2015-08-03 | 2015-08-03 | Ploetz/Smith | Delete | Remove detail |  |  | Unnecessary detail complicates the plan
5 | 1.2.4.7.4 | TASK: Model Material Risk Aggregation | 0% | 41d? | 2015-08-03 | 2015-09-28 |  | Date Change |  | 2015-08-01 | 2015-08-31 | New dates approved for SCUSA | Finish one month early
6 | 1.2.4.7.4.1 | ERM disseminates Workshop Pre-Read Materials to Risk Managers | 0% | 16d? | 2015-08-03 | 2015-08-24 |  | Delete | Remove detail |  |  | Unnecessary detail complicates the plan
6 | 1.2.4.7.4.2 | ERM facilitates Aggregation and Enrichment Activities | 0% | 25d? | 2015-08-25 | 2015-09-28 |  | Delete | Remove detail |  |  | Unnecessary detail complicates the plan
6 | 1.2.4.7.4.3 | Risk Manager presents inventory to level II subcommittee | 0% | 1d? | 2015-08-03 | 2015-08-03 |  | Delete | Remove detail |  |  | Unnecessary detail complicates the plan
6 | 1.2.4.7.4.4 | Model Material Risk Aggregation Prepared | 0% | 0d | 2015-08-03 | 2015-08-03 | Ploetz/Smith | Delete | Remove detail |  |  | Unnecessary detail complicates the plan
5 | 1.2.4.7.5 | TASK: Liquidity/Market Material Risk Aggregation | 0% | 41d? | 2015-08-03 | 2015-09-28 |  | Date Change |  | 2015-08-01 | 2015-08-31 | New dates approved for SCUSA | Finish one month early
6 | 1.2.4.7.5.1 | ERM disseminates Workshop Pre-Read Materials to Risk Managers | 0% | 16d? | 2015-08-03 | 2015-08-24 |  | Delete | Remove detail |  |  | Unnecessary detail complicates the plan
6 | 1.2.4.7.5.2 | ERM facilitates Aggregation and Enrichment Activities | 0% | 25d? | 2015-08-25 | 2015-09-28 |  | Delete | Remove detail |  |  | Unnecessary detail complicates the plan
6 | 1.2.4.7.5.3 | Risk Manager presents inventory to level II subcommittee | 0% | 1d? | 2015-08-03 | 2015-08-03 |  | Delete | Remove detail |  |  | Unnecessary detail complicates the plan
6 | 1.2.4.7.5.4 | Liquidity/Market Material Risk Aggregation Prepared | 0% | 0d | 2015-08-03 | 2015-08-03 | Ploetz/Smith | Delete | Remove detail |  |  | Unnecessary detail complicates the plan
5 | 1.2.4.7.6 | TASK: Reputational/Strategic Material Risk Aggregation | 0% | 41d? | 2015-08-03 | 2015-09-28 |  | Date Change |  | 2015-08-01 | 2015-08-31 | New dates approved for SCUSA | Finish one month early
6 | 1.2.4.7.6.1 | ERM disseminates Workshop Pre-Read Materials to Risk Managers | 0% | 16d? | 2015-08-03 | 2015-08-24 |  | Delete | Remove detail |  |  | Unnecessary detail complicates the plan
6 | 1.2.4.7.6.2 | ERM facilitates Aggregation and Enrichment Workshop | 0% | 25d? | 2015-08-25 | 2015-09-28 |  | Delete | Remove detail |  |  | Unnecessary detail complicates the plan
6 | 1.2.4.7.6.3 | Risk Manager presents inventory to level II subcommittee | 0% | 1d? | 2015-08-03 | 2015-08-03 |  | Delete | Remove detail |  |  | Unnecessary detail complicates the plan
6 | 1.2.4.7.6.4 | Reputational/Strategic Material Risk Aggregation Prepared | 0% | 0d | 2015-08-03 | 2015-08-03 | Ploetz/Smith | Delete | Remove detail |  |  | Unnecessary detail complicates the plan
4 | 1.2.4.8 | MILESTONE:Present Results to SCUSA ERMC | 0% | 48d | 2015-07-28 | 2015-10-01 | Ploetz/Smith | Contact | Ploetz/Smith -> T. Ploetz
4 | 1.2.4.9 | MILESTONE:Present Results to SCUSA BERC | 0% | 48d | 2015-07-28 | 2015-10-01 | Ploetz/Smith | Contact | Ploetz/Smith -> T. Ploetz
4 | 1.2.4.10 | Present SCUSA Material Risks to CCAR | 0% | 2d | 2015-10-01 | 2015-10-02 |  | Delete |  |  |  | Entity not required-verify with CCAR
4 | 1.2.4.11 | Deliver SCUSA Material Risks to CCAR and Capital Plan | 0% | 0d | 2015-10-02 | 2015-10-02 |  | Delete |  |  |  | Entity not required-verify with CCAR
3 | 1.2.5 | DELIVERABLE: Design and execute the Material Risk Program across New York Santander Investment Securities (SIS) | 10% | 92d | 2015-05-28 | 2015-10-02 | D. Allaire | Contact | Allaire -> J. Bathon
4 | 1.2.5.1 | MILESTONE:GBM-Cash Equities Brokerage Material Risk Inventory | 100% | 2d | 2015-06-29 | 2015-06-30 |  | Date Change |  | 2015-06-29 | 2015-07-31 |  | Finish one month late
5 | 1.2.5.1.1 | TASK:GBM-Cash Equities Brokerage Material Risk Inventory | 100% | 2d | 2015-06-29 | 2015-06-30 |  | Date Change |  | 2015-06-29 | 2015-07-31 |  | Finish one month late
6 | 1.2.5.1.1.1 | Deliver Final Inventory to SIS and SHUSA ERM | 100% | 2d | 2015-06-29 | 2015-06-30 |  | Date Change |  | 2015-06-29 | 2015-07-31 |  | Finish one month late
6 | 1.2.5.1.1.2 | Present inventory to ERMC | 100% | 2d | 2015-06-29 | 2015-06-30 |  | Date Change |  | 2015-06-29 | 2015-07-31 |  | Finish one month late
6 | 1.2.5.1.1.3 | Cash Equities Brokerage Material Risk Inventory Prepared | 100% | 0d | 2015-06-30 | 2015-06-30 | Murphy/Khurana | Date Change |  | 2015-06-29 | 2015-07-31 |  | Finish one month late
4 | 1.2.5.2 | MILESTONE:GBM- Debt Underwriting Material Risk Inventory | 100% | 2d | 2015-06-29 | 2015-06-30 |  | Date Change |  | 2015-06-29 | 2015-07-31 |  | Finish one month late
5 | 1.2.5.2.1 | TASK:GBM- Debt Underwriting Material Risk Inventory | 100% | 2d | 2015-06-29 | 2015-06-30 |  | Date Change |  | 2015-06-29 | 2015-07-31 |  | Finish one month late
6 | 1.2.5.2.1.1 | Deliver Final Inventory to SIS and SHUSA ERM | 100% | 2d | 2015-06-29 | 2015-06-30 |  | Date Change |  | 2015-06-29 | 2015-07-31 |  | Finish one month late
6 | 1.2.5.2.1.2 | Present inventory to ERMC | 100% | 2d | 2015-06-29 | 2015-06-30 |  | Date Change |  | 2015-06-29 | 2015-07-31 |  | Finish one month late
6 | 1.2.5.2.1.3 | Debt Underwriting Material Risk Inventory Prepared | 100% | 0d | 2015-06-30 | 2015-06-30 | Murphy/Khurana | Date Change |  | 2015-06-29 | 2015-07-31 |  | Finish one month late
4 | 1.2.5.3 | MILESTONE:GBM Equity Underwriting Material Risk Inventory | 100% | 2d | 2015-06-29 | 2015-06-30 |  | Date Change |  | 2015-06-29 | 2015-07-31 |  | Finish one month late
5 | 1.2.5.3.1 | TASK:GBM Equity Underwriting Material Risk Inventory | 100% | 2d | 2015-06-29 | 2015-06-30 |  | Date Change |  | 2015-06-29 | 2015-07-31 |  | Finish one month late
6 | 1.2.5.3.1.1 | Deliver Final Inventory to SIS and SHUSA ERM | 100% | 2d | 2015-06-29 | 2015-06-30 |  | Date Change |  | 2015-06-29 | 2015-07-31 |  | Finish one month late
6 | 1.2.5.3.1.2 | Present inventory to ERMC | 100% | 2d | 2015-06-29 | 2015-06-30 |  | Date Change |  | 2015-06-29 | 2015-07-31 |  | Finish one month late
6 | 1.2.5.3.1.3 | Equity Underwriting Material Risk Inventory Prepared | 100% | 0d | 2015-06-30 | 2015-06-30 | Murphy/Khurana | Date Change |  | 2015-06-29 | 2015-07-31 |  | Finish one month late
4 | 1.2.5.4 | MILESTONE:GBM- Fixed Income/Bond TradingMaterial Risk Inventory | 100% | 2d | 2015-06-29 | 2015-06-30 |  | Date Change |  | 2015-06-29 | 2015-07-31 |  | Finish one month late
5 | 1.2.5.4.1 | TASK:GBM- Fixed Income/Bond TradingMaterial Risk Inventory | 100% | 2d | 2015-06-29 | 2015-06-30 |  | Date Change |  | 2015-06-29 | 2015-07-31 |  | Finish one month late
6 | 1.2.5.4.1.1 | Deliver Final Inventory to SIS and SHUSA ERM | 100% | 2d | 2015-06-29 | 2015-06-30 |  | Date Change |  | 2015-06-29 | 2015-07-31 |  | Finish one month late
6 | 1.2.5.4.1.2 | Present inventory to ERMC | 100% | 2d | 2015-06-29 | 2015-06-30 |  | Date Change |  | 2015-06-29 | 2015-07-31 |  | Finish one month late
6 | 1.2.5.4.1.3 | Fixed Income/Bond TradingMaterial Risk Inventory Prepared | 100% | 0d | 2015-06-30 | 2015-06-30 | Murphy/Khurana | Date Change |  | 2015-06-29 | 2015-07-31 |  | Finish one month late
4 | 1.2.5.5 | MILESTONE:GBM - Futures Brokerage Material Risk Inventory | 100% | 2d | 2015-06-29 | 2015-06-30 |  | Date Change |  | 2015-06-29 | 2015-07-31 |  | Finish one month late
5 | 1.2.5.5.1 | TASK:GBM - Futures Brokerage Material Risk Inventory | 100% | 2d | 2015-06-29 | 2015-06-30 |  | Date Change |  | 2015-06-29 | 2015-07-31 |  | Finish one month late
6 | 1.2.5.5.1.1 | Deliver Final Inventory to SIS and SHUSA ERM | 100% | 2d | 2015-06-29 | 2015-06-30 |  | Date Change |  | 2015-06-29 | 2015-07-31 |  | Finish one month late
6 | 1.2.5.5.1.2 | Present inventory to ERMC | 100% | 2d | 2015-06-29 | 2015-06-30 |  | Date Change |  | 2015-06-29 | 2015-07-31 |  | Finish one month late
6 | 1.2.5.5.1.3 | Futures Brokerage Material Risk Inventory Prepared | 100% | 0d | 2015-06-30 | 2015-06-30 |  | Date Change |  | 2015-06-29 | 2015-07-31 |  | Finish one month late
4 | 1.2.5.6 | MILESTONE:GBM - Fixed Income and Equity Research Material Risk Inventory | 100% | 2d | 2015-06-29 | 2015-06-30 |  | Date Change |  | 2015-06-29 | 2015-07-31 |  | Finish one month late
5 | 1.2.5.6.1 | TASK:GBM - Fixed Income and Equity Research Material Risk Inventory | 100% | 2d | 2015-06-29 | 2015-06-30 |  | Date Change |  | 2015-06-29 | 2015-07-31 |  | Finish one month late
6 | 1.2.5.6.1.1 | Deliver Final Inventory to SIS and SHUSA ERM | 100% | 2d | 2015-06-29 | 2015-06-30 |  | Date Change |  | 2015-06-29 | 2015-07-31 |  | Finish one month late
6 | 1.2.5.6.1.2 | Present inventory to ERMC | 100% | 2d | 2015-06-29 | 2015-06-30 |  | Date Change |  | 2015-06-29 | 2015-07-31 |  | Finish one month late
6 | 1.2.5.6.1.3 | Fixed Income and Equity Research Material Risk Inventory Prepared | 100% | 0d | 2015-06-30 | 2015-06-30 | Murphy/Khurana | Date Change |  | 2015-06-29 | 2015-07-31 |  | Finish one month late
4 | 1.2.5.7 | MILESTONE:Human Resources Material Risk Inventory | 100% | 2d | 2015-06-29 | 2015-06-30 |  | Delete |  |  |  | SIS captured these risks in lines of business-confirm with NY
5 | 1.2.5.7.1 | TASK:Human Resources Material Risk Inventory | 100% | 2d | 2015-06-29 | 2015-06-30 |  | Delete |  |  |  | SIS captured these risks in lines of business-confirm with NY
6 | 1.2.5.7.1.1 | Deliver Final Inventory to SIS and SHUSA ERM | 100% | 2d | 2015-06-29 | 2015-06-30 |  | Delete |  |  |  | SIS captured these risks in lines of business-confirm with NY
6 | 1.2.5.7.1.2 | Present inventory to ERMC | 100% | 2d | 2015-06-29 | 2015-06-30 |  | Delete |  |  |  | SIS captured these risks in lines of business-confirm with NY
6 | 1.2.5.7.1.3 | Human Resources Material Risk Inventory Prepared | 100% | 0d | 2015-06-30 | 2015-06-30 | Murphy/Khurana | Delete |  |  |  | SIS captured these risks in lines of business-confirm with NY
4 | 1.2.5.8 | MILESTONE:Finance Material Risk Inventory | 100% | 2d | 2015-06-29 | 2015-06-30 |  | Delete |  |  |  | SIS captured these risks in lines of business-confirm with NY
5 | 1.2.5.8.1 | TASK:Finance Material Risk Inventory | 100% | 2d | 2015-06-29 | 2015-06-30 |  | Delete |  |  |  | SIS captured these risks in lines of business-confirm with NY
6 | 1.2.5.8.1.1 | Deliver Final Inventory to SIS and SHUSA ERM | 100% | 2d | 2015-06-29 | 2015-06-30 |  | Delete |  |  |  | SIS captured these risks in lines of business-confirm with NY
6 | 1.2.5.8.1.2 | Present inventory to ERMC | 100% | 2d | 2015-06-29 | 2015-06-30 |  | Delete |  |  |  | SIS captured these risks in lines of business-confirm with NY
6 | 1.2.5.8.1.3 | Finance Material Risk Inventory Prepared | 100% | 0d | 2015-06-30 | 2015-06-30 | Murphy/Khurana | Delete |  |  |  | SIS captured these risks in lines of business-confirm with NY
4 | 1.2.5.9 | MILESTONE:Technology and Operations Material Risk Inventory | 100% | 2d | 2015-06-29 | 2015-06-30 |  | Delete |  |  |  | SIS captured these risks in lines of business-confirm with NY
5 | 1.2.5.9.1 | TASK:Technology and Operations Material Risk Inventory | 100% | 2d | 2015-06-29 | 2015-06-30 |  | Delete |  |  |  | SIS captured these risks in lines of business-confirm with NY
6 | 1.2.5.9.1.1 | Deliver Final Inventory to SIS and SHUSA ERM | 100% | 2d | 2015-06-29 | 2015-06-30 |  | Delete |  |  |  | SIS captured these risks in lines of business-confirm with NY
6 | 1.2.5.9.1.2 | Present inventory to ERMC | 100% | 2d | 2015-06-29 | 2015-06-30 |  | Delete |  |  |  | SIS captured these risks in lines of business-confirm with NY
6 | 1.2.5.9.1.3 | Technology and Operations Material Risk Inventory Prepared | 100% | 0d | 2015-06-30 | 2015-06-30 | Murphy/Khurana | Delete |  |  |  | SIS captured these risks in lines of business-confirm with NY
4 | 1.2.5.10 | MILESTONE:Legal Material Risk Inventory | 100% | 2d | 2015-06-29 | 2015-06-30 |  | Delete |  |  |  | SIS captured these risks in lines of business-confirm with NY
5 | 1.2.5.10.1 | TASK:Legal Material Risk Inventory | 100% | 2d | 2015-06-29 | 2015-06-30 |  | Delete |  |  |  | SIS captured these risks in lines of business-confirm with NY
6 | 1.2.5.10.1.1 | Deliver Final Inventory to SIS and SHUSA ERM | 100% | 2d | 2015-06-29 | 2015-06-30 |  | Delete |  |  |  | SIS captured these risks in lines of business-confirm with NY
6 | 1.2.5.10.1.2 | Present inventory to ERMC | 100% | 2d | 2015-06-29 | 2015-06-30 |  | Delete |  |  |  | SIS captured these risks in lines of business-confirm with NY
6 | 1.2.5.10.1.3 | Legal Material Risk Inventory Prepared | 100% | 0d | 2015-06-30 | 2015-06-30 | Murphy/Khurana | Delete |  |  |  | SIS captured these risks in lines of business-confirm with NY
4 | 1.2.5.11 | MILESTONE: Hold NY SIS Aggregation Workshops (include 2nd LOD challenge) | 0% | 45d | 2015-08-03 | 2015-10-02 |  | Date Change |  | 2015-08-01 | 2015-08-31
5 | 1.2.5.11.1 | TASK: Credit Risk Aggregation |  | 41d? | 2015-08-03 | 2015-09-28 |  | Date Change |  | 2015-08-01 | 2015-08-31 |  | Finish one month early
6 | 1.2.5.11.1.1 | ERM disseminates Workshop Pre-Read Materials to Risk Managers | 100% | 16d? | 2015-08-03 | 2015-08-24 |  | Delete | Remove detail |  |  | Unnecessary detail complicates the plan
6 | 1.2.5.11.1.2 | ERM facilitates Aggregation and Enrichment Activities | 100% | 25d? | 2015-08-25 | 2015-09-28 |  | Delete | Remove detail |  |  | Unnecessary detail complicates the plan
6 | 1.2.5.11.1.3 | Risk Manager presents inventory to level II subcommittee | 50% | 1d? | 2015-08-03 | 2015-08-03 |  | Delete | Remove detail |  |  | Unnecessary detail complicates the plan
6 | 1.2.5.11.1.4 | Credit Risk Aggregation Prepared | 50% | 0d | 2015-08-03 | 2015-08-03 | Murphy/Khurana | Delete | Remove detail |  |  | Unnecessary detail complicates the plan
5 | 1.2.5.11.2 | TASK: Operational Risk Material Risk Aggregation | 0% | 41d? | 2015-08-03 | 2015-09-28 |  | Date Change |  | 2015-08-01 | 2015-08-31 |  | Finish one month early
6 | 1.2.5.11.2.1 | ERM disseminates Workshop Pre-Read Materials to Risk Managers | 100% | 16d? | 2015-08-03 | 2015-08-24 |  | Delete | Remove detail |  |  | Unnecessary detail complicates the plan
6 | 1.2.5.11.2.2 | ERM facilitates Aggregation and Enrichment Activities | 100% | 25d? | 2015-08-25 | 2015-09-28 |  | Delete | Remove detail |  |  | Unnecessary detail complicates the plan
6 | 1.2.5.11.2.3 | Risk Manager presents inventory to level II subcommittee | 50% | 1d? | 2015-08-03 | 2015-08-03 |  | Delete | Remove detail |  |  | Unnecessary detail complicates the plan
6 | 1.2.5.11.2.4 | Operational Risk Material Risk Aggregation Prepared | 50% | 0d | 2015-08-03 | 2015-08-03 | Murphy/Khurana | Delete | Remove detail |  |  | Unnecessary detail complicates the plan
5 | 1.2.5.11.3 | TASK: Compliance Material Risk Aggregation | 0% | 41d? | 2015-08-03 | 2015-09-28 |  | Date Change |  | 2015-08-01 | 2015-08-31 |  | Finish one month early
6 | 1.2.5.11.3.1 | ERM disseminates Workshop Pre-Read Materials to Risk Managers | 100% | 16d? | 2015-08-03 | 2015-08-24 |  | Delete | Remove detail |  |  | Unnecessary detail complicates the plan
6 | 1.2.5.11.3.2 | ERM facilitates Aggregation and Enrichment Activities | 100% | 25d? | 2015-08-25 | 2015-09-28 |  | Delete | Remove detail |  |  | Unnecessary detail complicates the plan
6 | 1.2.5.11.3.3 | Risk Manager presents inventory to level II subcommittee | 50% | 1d? | 2015-08-03 | 2015-08-03 |  | Delete | Remove detail |  |  | Unnecessary detail complicates the plan
6 | 1.2.5.11.3.4 | Compliance Material Risk Aggregation Prepared | 50% | 0d | 2015-08-03 | 2015-08-03 | Murphy/Khurana | Delete | Remove detail |  |  | Unnecessary detail complicates the plan
5 | 1.2.5.11.4 | TASK: Model Material Risk Aggregation | 0% | 41d? | 2015-08-03 | 2015-09-28 |  | Date Change |  | 2015-08-01 | 2015-08-31 |  | Finish one month early
6 | 1.2.5.11.4.1 | ERM disseminates Workshop Pre-Read Materials to Risk Managers | 100% | 16d? | 2015-08-03 | 2015-08-24 |  | Delete | Remove detail |  |  | Unnecessary detail complicates the plan
6 | 1.2.5.11.4.2 | ERM facilitates Aggregation and Enrichment Workshop | 100% | 25d? | 2015-08-25 | 2015-09-28 |  | Delete | Remove detail |  |  | Unnecessary detail complicates the plan
6 | 1.2.5.11.4.3 | Risk Manager presents inventory to level II subcommittee | 50% | 1d? | 2015-08-03 | 2015-08-03 |  | Delete | Remove detail |  |  | Unnecessary detail complicates the plan
6 | 1.2.5.11.4.4 | Model Material Risk Aggregation Prepared | 50% | 0d | 2015-08-03 | 2015-08-03 | Murphy/Khurana | Delete | Remove detail |  |  | Unnecessary detail complicates the plan
5 | 1.2.5.11.5 | TASK: Liquidity/Market Material Risk Aggregation | 0% | 41d? | 2015-08-03 | 2015-09-28 |  | Date Change |  | 2015-08-01 | 2015-08-31 |  | Finish one month early
6 | 1.2.5.11.5.1 | ERM disseminates Workshop Pre-Read Materials to Risk Managers | 100% | 16d? | 2015-08-03 | 2015-08-24 |  | Delete | Remove detail |  |  | Unnecessary detail complicates the plan
6 | 1.2.5.11.5.2 | ERM facilitates Aggregation and Enrichment Activities | 100% | 25d? | 2015-08-25 | 2015-09-28 |  | Delete | Remove detail |  |  | Unnecessary detail complicates the plan
6 | 1.2.5.11.5.3 | Risk Manager presents inventory to level II subcommittee | 50% | 1d? | 2015-08-03 | 2015-08-03 |  | Delete | Remove detail |  |  | Unnecessary detail complicates the plan
6 | 1.2.5.11.5.4 | Liquidity/Market Material Risk Aggregation Prepared | 50% | 0d | 2015-08-03 | 2015-08-03 | Murphy/Khurana | Delete | Remove detail |  |  | Unnecessary detail complicates the plan
5 | 1.2.5.11.6 | TASK: Reputational/Strategic Material Risk Aggregation | 0% | 41d? | 2015-08-03 | 2015-09-28 |  | Date Change |  | 2015-08-01 | 2015-08-31 |  | Finish one month early
6 | 1.2.5.11.6.1 | ERM disseminates Workshop Pre-Read Materials to Risk Managers | 100% | 16d? | 2015-08-03 | 2015-08-24 |  | Delete | Remove detail |  |  | Unnecessary detail complicates the plan
6 | 1.2.5.11.6.2 | ERM facilitates Aggregation and Enrichment Activities | 100% | 25d? | 2015-08-25 | 2015-09-28 |  | Delete | Remove detail |  |  | Unnecessary detail complicates the plan
6 | 1.2.5.11.6.3 | Risk Manager presents inventory to level II subcommittee | 50% | 1d? | 2015-08-03 | 2015-08-03 |  | Delete | Remove detail |  |  | Unnecessary detail complicates the plan
6 | 1.2.5.11.6.4 | Reputational/Strategic Material Risk Aggregation Prepared | 50% | 0d | 2015-08-03 | 2015-08-03 | Murphy/Khurana | Delete | Remove detail |  |  | Unnecessary detail complicates the plan
4 | 1.2.5.12 | MILESTONE:Present Results to NY SIS ERMC | 0% | 48d | 2015-07-28 | 2015-10-01 | Murphy/Khurana | Contact | Murphy/Khurana -> J. Bathon
4 | 1.2.5.13 | MILESTONE:Present Results to NY SIS BERC | 0% | 48d | 2015-07-28 | 2015-10-01 | Murphy/Khurana | Contact | Murphy/Khurana -> J. Bathon
4 | 1.2.5.14 | Present NY SIS Material Risks to CCAR | 0% | 2d | 2015-10-01 | 2015-10-02 |  | Delete |  |  |  | Entities level not needed-verify with CCAR
4 | 1.2.5.15 | Deliver NY SIS Material Risks to CCAR and Capital Plan | 0% | 0d | 2015-10-02 | 2015-10-02 |  | Delete |  |  |  | Entities level not needed-verify with CCAR
3 | 1.2.6 | DELIVERABLE: Design and execute the Material Risk Program across Puerto Rico | 89% | 92d | 2015-05-28 | 2015-10-02 | D. Allaire | Contact | Allaire -> Jurado
4 | 1.2.6.1 | MILESTONE:Retail Banking Material Risk Inventory | 95% | 25d | 2015-06-29 | 2015-07-31
5 | 1.2.6.1.1 | TASK: Personal Loans Banking Material Risk Inventory | 100% | 25d | 2015-06-29 | 2015-07-31
6 | 1.2.6.1.1.1 | Deliver Final Inventory to PR and SHUSA ERM | 100% | 25d | 2015-06-29 | 2015-07-31
6 | 1.2.6.1.1.2 | Personal Loans Banking Material Risk Inventory Prepared | 100% | 0d | 2015-07-31 | 2015-07-31 | Jurado/Fabricio | Contact | Jurado/Fabricio -> Jurado
5 | 1.2.6.1.2 | TASK: Small Business Banking Material Risk Inventory | 100% | 25d | 2015-06-29 | 2015-07-31
6 | 1.2.6.1.2.1 | Deliver Final Inventory to PR and SHUSA ERM | 100% | 25d | 2015-06-29 | 2015-07-31
6 | 1.2.6.1.2.2 | Small Business Banking Material Risk Inventory Prepared | 100% | 1d | 2015-07-31 | 2015-07-31 | Jurado/Fabricio | Contact | Jurado/Fabricio -> Jurado
5 | 1.2.6.1.3 | TASK: Santander Insurance Agency Material Risk Inventory | 100% | 25d | 2015-06-29 | 2015-07-31
6 | 1.2.6.1.3.1 | Deliver Final Inventory to PR and SHUSA ERM | 100% | 25d | 2015-06-29 | 2015-07-31
6 | 1.2.6.1.3.2 | Santander Insurance Agency Material Risk Inventory Prepared | 100% | 0d | 2015-07-31 | 2015-07-31 | Jurado/Fabricio | Contact | Jurado/Fabricio -> Jurado
5 | 1.2.6.1.4 | TASK: Credit Cards Material Risk Inventory | 100% | 25d | 2015-06-29 | 2015-07-31
6 | 1.2.6.1.4.1 | Deliver Final Inventory to PR and SHUSA ERM | 100% | 25d | 2015-06-29 | 2015-07-31
6 | 1.2.6.1.4.2 | Credit Cards Material Risk Inventory Prepared | 100% | 1d | 2015-07-31 | 2015-07-31 | Jurado/Fabricio | Contact | Jurado/Fabricio -> Jurado
5 | 1.2.6.1.5 | TASK: Mortgages Material Risk Inventory | 100% | 25d | 2015-06-29 | 2015-07-31
6 | 1.2.6.1.5.1 | Deliver Final Inventory to PR and SHUSA ERM | 100% | 25d | 2015-06-29 | 2015-07-31
6 | 1.2.6.1.5.2 | Mortgages Material Risk Inventory Prepared | 100% | 1d | 2015-07-31 | 2015-07-31 | Jurado/Fabricio | Contact | Jurado/Fabricio -> Jurado
4 | 1.2.6.2 | MILESTONE:Global Banking/Commercial Banking and CRE/Speciality and Gov't Banking Material Risk Inventory | 100% | 25d | 2015-06-29 | 2015-07-31
5 | 1.2.6.2.1 | TASK: GBM Material Risk Inventory | 100% | 25d | 2015-06-29 | 2015-07-31
6 | 1.2.6.2.1.1 | Deliver Final Inventory to PR and SHUSA ERM | 100% | 25d | 2015-06-29 | 2015-07-31
6 | 1.2.6.2.1.2 | GBM Material Risk Inventory Prepared | 100% | 0d | 2015-07-31 | 2015-07-31 | Jurado/Fabricio | Contact | Jurado/Fabricio -> Jurado
5 | 1.2.6.2.2 | TASK: Enterprise Material Risk Inventory | 100% | 25d | 2015-06-29 | 2015-07-31
6 | 1.2.6.2.2.1 | Deliver Final Inventory to PR and SHUSA ERM | 100% | 25d | 2015-06-29 | 2015-07-31
6 | 1.2.6.2.2.2 | Enterprise Material Risk Inventory Prepared | 100% | 0d | 2015-07-31 | 2015-07-31 | Jurado/Fabricio | Contact | Jurado/Fabricio -> Jurado
5 | 1.2.6.2.3 | TASK: Institutional/Public Sector Material Risk Inventory | 100% | 25d | 2015-06-29 | 2015-07-31
6 | 1.2.6.2.3.1 | Deliver Final Inventory to PR and SHUSA ERM | 100% | 25d | 2015-06-29 | 2015-07-31
6 | 1.2.6.2.3.2 | Institutional/Public Sector Material Risk Inventory Prepared | 100% | 0d | 2015-07-31 | 2015-07-31 | Jurado/Fabricio | Contact | Jurado/Fabricio -> Jurado
4 | 1.2.6.3 | MILESTONE:Global Banking/Commercial Banking/CRE & Speciality: Create Global Banking Material Risk Inventory | 100% | 47d | 2015-05-28 | 2015-07-31
5 | 1.2.6.3.1 | TASK:Global Banking/Commercial Banking/CRE & Speciality: Create Global Banking Material Risk Inventory | 100% | 47d | 2015-05-28 | 2015-07-31
6 | 1.2.6.3.1.1 | Create Segment Material Risk Inventory (Aggregation) | 100% | 47d | 2015-05-28 | 2015-07-31
6 | 1.2.6.3.1.2 | Segment head presents inventory to ERMC | 100% | 25d | 2015-06-29 | 2015-07-31
6 | 1.2.6.3.1.3 | Global Banking Material Risk Inventory Prepared | 100% | 0d | 2015-07-31 | 2015-07-31 | Jurado/Fabricio | Contact | Jurado/Fabricio -> Jurado
4 | 1.2.6.4 | MILESTONE:Mortgage Servicing Material Risk Inventory | 100% | 25d | 2015-06-29 | 2015-07-31
5 | 1.2.6.4.1 | TASK:Mortgage Servicing Material Risk Inventory | 100% | 25d | 2015-06-29 | 2015-07-31
6 | 1.2.6.4.1.1 | Deliver Final Inventory to PR and SHUSA ERM | 100% | 25d | 2015-06-29 | 2015-07-31
6 | 1.2.6.4.1.2 | Present inventory to ERMC | 100% | 25d | 2015-06-29 | 2015-07-31
6 | 1.2.6.4.1.3 | Mortgage Servicing Material Risk Inventory Prepared | 100% | 0d | 2015-07-31 | 2015-07-31 | Jurado/Fabricio | Contact | Jurado/Fabricio -> Jurado
4 | 1.2.6.5 | MILESTONE:Investment Services Material Risk Inventory | 95% | 25d | 2015-06-29 | 2015-07-31
5 | 1.2.6.5.1 | TASK:Investment Services Material Risk Inventory | 95% | 25d | 2015-06-29 | 2015-07-31
6 | 1.2.6.5.1.1 | Deliver Final Inventory to PR and SHUSA ERM | 95% | 25d | 2015-06-29 | 2015-07-31
6 | 1.2.6.5.1.2 | Present inventory to ERMC | 95% | 25d | 2015-06-29 | 2015-07-31
6 | 1.2.6.5.1.3 | Investment Services Material Risk Inventory Prepared | 95% | 0d | 2015-07-31 | 2015-07-31 | Jurado/Fabricio | Contact | Jurado/Fabricio -> Jurado
4 | 1.2.6.6 | MILESTONE:Trust Material Risk Inventory | 100% | 25d | 2015-06-29 | 2015-07-31
5 | 1.2.6.6.1 | TASK:Trust Material Risk Inventory | 100% | 25d | 2015-06-29 | 2015-07-31
6 | 1.2.6.6.1.1 | Deliver Final Inventory to PR and SHUSA ERM | 100% | 25d | 2015-06-29 | 2015-07-31
6 | 1.2.6.6.1.2 | Present inventory to ERMC | 100% | 25d | 2015-06-29 | 2015-07-31
6 | 1.2.6.6.1.3 | Trust Material Risk Inventory Prepared | 100% | 0d | 2015-07-31 | 2015-07-31 | Jurado/Fabricio | Contact | Jurado/Fabricio -> Jurado
4 | 1.2.6.7 | MILESTONE:Pension Plan Material Risk Inventory | 95% | 25d | 2015-06-29 | 2015-07-31
5 | 1.2.6.7.1 | TASK:Pension Plan Material Risk Inventory | 95% | 25d | 2015-06-29 | 2015-07-31
6 | 1.2.6.7.1.1 | Deliver Final Inventory to PR and SHUSA ERM | 95% | 25d | 2015-06-29 | 2015-07-31
6 | 1.2.6.7.1.2 | Present inventory to ERMC | 95% | 25d | 2015-06-29 | 2015-07-31
6 | 1.2.6.7.1.3 | Pension Plan Material Risk Inventory Prepared | 95% | 0d | 2015-07-31 | 2015-07-31 | Jurado/Fabricio | Contact | Jurado/Fabricio -> Jurado
4 | 1.2.6.8 | MILESTONE:Foreign Accounts Material Risk Inventory | 95% | 25d | 2015-06-29 | 2015-07-31
5 | 1.2.6.8.1 | TASK:Foreign Accounts Material Risk Inventory | 95% | 25d | 2015-06-29 | 2015-07-31
6 | 1.2.6.8.1.1 | Deliver Final Inventory to PR and SHUSA ERM | 95% | 25d | 2015-06-29 | 2015-07-31
6 | 1.2.6.8.1.2 | Present inventory to ERMC | 95% | 25d | 2015-06-29 | 2015-07-31
6 | 1.2.6.8.1.3 | Foreign Accounts Material Risk Inventory Prepared | 95% | 1d | 2015-07-31 | 2015-07-31 | Jurado/Fabricio | Contact | Jurado/Fabricio -> Jurado
4 | 1.2.6.9 | MILESTONE:Human Resources Material Risk Inventory | N/A | 47d | 2015-05-28 | 2015-07-31 |  | Delete |  |  |  | PR captured these risks in lines of business-confirm with PR
5 | 1.2.6.9.1 | TASK:Human Resources Material Risk Inventory | N/A | 47d | 2015-05-28 | 2015-07-31 |  | Delete |  |  |  | PR captured these risks in lines of business-confirm with PR
6 | 1.2.6.9.1.1 | Create risk Inventory | N/A | 38d | 2015-05-28 | 2015-07-20 |  | Delete |  |  |  | PR captured these risks in lines of business-confirm with PR
6 | 1.2.6.9.1.2 | Deliver Final Inventory to PR and SHUSA ERM | N/A | 25d | 2015-06-29 | 2015-07-31 |  | Delete |  |  |  | PR captured these risks in lines of business-confirm with PR
6 | 1.2.6.9.1.3 | Present inventory to ERMC | N/A | 25d | 2015-06-29 | 2015-07-31 |  | Delete |  |  |  | PR captured these risks in lines of business-confirm with PR
6 | 1.2.6.9.1.4 | Human Resources Material Risk Inventory Prepared | N/A | 0d | 2015-07-31 | 2015-07-31 | Jurado/Fabricio | Delete |  |  |  | PR captured these risks in lines of business-confirm with PR
4 | 1.2.6.10 | MILESTONE:Technology and Operations Material Risk Inventory | N/A | 25d | 2015-06-29 | 2015-07-31 |  | Delete |  |  |  | PR captured these risks in lines of business-confirm with PR
5 | 1.2.6.10.1 | TASK:Technology and Operations Material Risk Inventory | N/A | 25d | 2015-06-29 | 2015-07-31 |  | Delete |  |  |  | PR captured these risks in lines of business-confirm with PR
6 | 1.2.6.10.1.1 | Deliver Final Inventory to PR and SHUSA ERM | N/A | 25d | 2015-06-29 | 2015-07-31 |  | Delete |  |  |  | PR captured these risks in lines of business-confirm with PR
6 | 1.2.6.10.1.2 | Present inventory to ERMC | N/A | 25d | 2015-06-29 | 2015-07-31 |  | Delete |  |  |  | PR captured these risks in lines of business-confirm with PR
6 | 1.2.6.10.1.3 | Technology and Operations Material Risk Inventory Prepared | N/A | 0d | 2015-07-31 | 2015-07-31 | Jurado/Fabricio | Delete |  |  |  | PR captured these risks in lines of business-confirm with PR
4 | 1.2.6.11 | MILESTONE:Legal Material Risk Inventory | N/A | 25d | 2015-06-29 | 2015-07-31 |  | Delete |  |  |  | PR captured these risks in lines of business-confirm with PR
5 | 1.2.6.11.1 | TASK:Legal Material Risk Inventory | N/A | 25d | 2015-06-29 | 2015-07-31 |  | Delete |  |  |  | PR captured these risks in lines of business-confirm with PR
6 | 1.2.6.11.1.1 | Deliver Final Inventory to PR and SHUSA ERM | N/A | 25d | 2015-06-29 | 2015-07-31 |  | Delete |  |  |  | PR captured these risks in lines of business-confirm with PR
6 | 1.2.6.11.1.2 | Present inventory to ERMC | N/A | 25d | 2015-06-29 | 2015-07-31 |  | Delete |  |  |  | PR captured these risks in lines of business-confirm with PR
6 | 1.2.6.11.1.3 | Legal Material Risk Inventory Prepared | N/A | 0d | 2015-07-31 | 2015-07-31 | Jurado/Fabricio | Delete |  |  |  | PR captured these risks in lines of business-confirm with PR
4 | 1.2.6.12 | MILESTONE:Finance Material Risk Inventory | 100% | 25d | 2015-06-29 | 2015-07-31
5 | 1.2.6.12.1 | TASK:Finance Material Risk Inventory | 100% | 25d | 2015-06-29 | 2015-07-31
6 | 1.2.6.12.1.1 | Deliver Final Inventory to PR and SHUSA ERM | 100% | 25d | 2015-06-29 | 2015-07-31
6 | 1.2.6.12.1.2 | Present inventory to ERMC | 100% | 25d | 2015-06-29 | 2015-07-31
6 | 1.2.6.12.1.3 | Finance Material Risk Inventory Prepared | 100% | 0d | 2015-07-31 | 2015-07-31 | Jurado/Fabricio | Contact | Jurado/Fabricio -> Jurado
4 | 1.2.6.13 | MILESTONE:SFS - Island Finance Material Risk Inventory | 100% | 25d | 2015-06-29 | 2015-07-31
5 | 1.2.6.13.1 | TASK:SFS - Island Finance Material Risk Inventory | 100% | 25d | 2015-06-29 | 2015-07-31
6 | 1.2.6.13.1.1 | Deliver Final Inventory to PR and SHUSA ERM | 100% | 25d | 2015-06-29 | 2015-07-31
6 | 1.2.6.13.1.2 | Present inventory to ERMC | 100% | 25d | 2015-06-29 | 2015-07-31
6 | 1.2.6.13.1.3 | SFS - Island Finance Material Risk Inventory Prepared | 100% | 0d | 2015-07-31 | 2015-07-31 | Jurado/Fabricio | Contact | Jurado/Fabricio -> Jurado
4 | 1.2.6.14 | MILESTONE:SFS - Special Assets Material Risk Inventory | 100% | 25d | 2015-06-29 | 2015-07-31
5 | 1.2.6.14.1 | TASK:SFS - Special Assets Material Risk Inventory | 100% | 25d | 2015-06-29 | 2015-07-31
6 | 1.2.6.14.1.1 | Deliver Final Inventory to PR and SHUSA ERM | 100% | 25d | 2015-06-29 | 2015-07-31
6 | 1.2.6.14.1.2 | Present inventory to ERMC | 100% | 25d | 2015-06-29 | 2015-07-31
6 | 1.2.6.14.1.3 | SFS - Special Assets Material Risk Inventory Prepared | 100% | 0d | 2015-07-31 | 2015-07-31 | Jurado/Fabricio | Contact | Jurado/Fabricio -> Jurado
4 | 1.2.6.15 | MILESTONE:Santander Overseas Bank - GBM Material Risk Inventory | 100% | 25d | 2015-06-29 | 2015-07-31
5 | 1.2.6.15.1 | TASK:Santander Overseas Bank - GBM Material Risk Inventory | 100% | 25d | 2015-06-29 | 2015-07-31
6 | 1.2.6.15.1.1 | Deliver Final Inventory to PR and SHUSA ERM | 100% | 25d | 2015-06-29 | 2015-07-31
6 | 1.2.6.15.1.2 | Present inventory to ERMC | 100% | 25d | 2015-06-29 | 2015-07-31
6 | 1.2.6.15.1.3 | Santander Overseas Bank - GBM Material Risk Inventory Prepared | 100% | 1d | 2015-07-31 | 2015-07-31 | Jurado/Fabricio | Contact | Jurado/Fabricio -> Jurado
4 | 1.2.6.16 | MILESTONE: Hold Puerto Rico Aggregation Workshops (include 2nd LOD challenge) | 98% | 45d | 2015-08-03 | 2015-10-02 |  | Date Change |  | 2015-08-01 | 2015-08-31 |  | Finish one month early
5 | 1.2.6.16.1 | TASK: Credit Risk Aggregation | 98% | 41d? | 2015-08-03 | 2015-09-28 |  | Date Change |  | 2015-08-01 | 2015-08-31 |  | Finish one month early
6 | 1.2.6.16.1.1 | ERM disseminates Workshop Pre-Read Materials to Risk Managers | 50% | 16d? | 2015-08-03 | 2015-08-24 |  | Delete | Remove detail |  |  | Unnecessary detail complicates the plan
6 | 1.2.6.16.1.2 | ERM facilitates Aggregation and Enrichment Activities | 50% | 25d? | 2015-08-25 | 2015-09-28 |  | Delete | Remove detail |  |  | Unnecessary detail complicates the plan
6 | 1.2.6.16.1.3 | Risk Manager presents inventory to level II subcommittee | 0% | 1d? | 2015-08-03 | 2015-08-03 |  | Delete | Remove detail |  |  | Unnecessary detail complicates the plan
6 | 1.2.6.16.1.4 | Credit Risk Aggregation Prepared | 0% | 0d | 2015-08-03 | 2015-08-03 | Jurado/Fabricio | Delete | Remove detail |  |  | Unnecessary detail complicates the plan
5 | 1.2.6.16.2 | TASK: Operational Risk Material Risk Aggregation | 98% | 41d? | 2015-08-03 | 2015-09-28 |  | Date Change |  | 2015-08-01 | 2015-08-31 |  | Finish one month early
6 | 1.2.6.16.2.1 | ERM disseminates Workshop Pre-Read Materials to Risk Managers | 50% | 16d? | 2015-08-03 | 2015-08-24 |  | Delete | Remove detail |  |  | Unnecessary detail complicates the plan
6 | 1.2.6.16.2.2 | ERM facilitates Aggregation and Enrichment Activities | 50% | 25d? | 2015-08-25 | 2015-09-28 |  | Delete | Remove detail |  |  | Unnecessary detail complicates the plan
6 | 1.2.6.16.2.3 | Risk Manager presents inventory to level II subcommittee | 0% | 1d? | 2015-08-03 | 2015-08-03 |  | Delete | Remove detail |  |  | Unnecessary detail complicates the plan
6 | 1.2.6.16.2.4 | Operational Risk Material Risk Aggregation Prepared | 0% | 0d | 2015-08-03 | 2015-08-03 | Jurado/Fabricio | Delete | Remove detail |  |  | Unnecessary detail complicates the plan
5 | 1.2.6.16.3 | TASK: Compliance Material Risk Aggregation | 98% | 41d? | 2015-08-03 | 2015-09-28 |  | Date Change |  | 2015-08-01 | 2015-08-31 |  | Finish one month early
6 | 1.2.6.16.3.1 | ERM disseminates Workshop Pre-Read Materials to Risk Managers | 50% | 16d? | 2015-08-03 | 2015-08-24 |  | Delete | Remove detail |  |  | Unnecessary detail complicates the plan
6 | 1.2.6.16.3.2 | ERM facilitates Aggregation and Enrichment Workshop | 50% | 25d? | 2015-08-25 | 2015-09-28 |  | Delete | Remove detail |  |  | Unnecessary detail complicates the plan
6 | 1.2.6.16.3.3 | Risk Manager presents inventory to level II subcommittee | 0% | 1d? | 2015-08-03 | 2015-08-03 |  | Delete | Remove detail |  |  | Unnecessary detail complicates the plan
6 | 1.2.6.16.3.4 | Compliance Material Risk Aggregation Prepared | 0% | 0d | 2015-08-03 | 2015-08-03 | Jurado/Fabricio | Delete | Remove detail |  |  | Unnecessary detail complicates the plan
5 | 1.2.6.16.4 | TASK: Model Material Risk Aggregation | 98% | 41d? | 2015-08-03 | 2015-09-28 |  | Date Change |  | 2015-08-01 | 2015-08-31 |  | Finish one month early
6 | 1.2.6.16.4.1 | ERM disseminates Workshop Pre-Read Materials to Risk Managers | 50% | 16d? | 2015-08-03 | 2015-08-24 |  | Delete | Remove detail |  |  | Unnecessary detail complicates the plan
6 | 1.2.6.16.4.2 | ERM facilitates Aggregation and Enrichment Activities | 50% | 25d? | 2015-08-25 | 2015-09-28 |  | Delete | Remove detail |  |  | Unnecessary detail complicates the plan
6 | 1.2.6.16.4.3 | Risk Manager presents inventory to level II subcommittee | 0% | 1d? | 2015-08-03 | 2015-08-03 |  | Delete | Remove detail |  |  | Unnecessary detail complicates the plan
6 | 1.2.6.16.4.4 | Model Material Risk Aggregation Prepared | 0% | 0d | 2015-08-03 | 2015-08-03 | Jurado/Fabricio | Delete | Remove detail |  |  | Unnecessary detail complicates the plan
5 | 1.2.6.16.5 | TASK: Liquidity/Market Material Risk Aggregation | 98% | 41d? | 2015-08-03 | 2015-09-28 |  | Date Change |  | 2015-08-01 | 2015-08-31 |  | Finish one month early
6 | 1.2.6.16.5.1 | ERM disseminates Workshop Pre-Read Materials to Risk Managers | 50% | 16d? | 2015-08-03 | 2015-08-24 |  | Delete | Remove detail |  |  | Unnecessary detail complicates the plan
6 | 1.2.6.16.5.2 | ERM facilitates Aggregation and Enrichment Activities | 50% | 25d? | 2015-08-25 | 2015-09-28 |  | Delete | Remove detail |  |  | Unnecessary detail complicates the plan
6 | 1.2.6.16.5.3 | Risk Manager presents inventory to level II subcommittee | 0% | 1d? | 2015-08-03 | 2015-08-03 |  | Delete | Remove detail |  |  | Unnecessary detail complicates the plan
6 | 1.2.6.16.5.4 | Liquidity/Market Material Risk Aggregation Prepared | 0% | 0d | 2015-08-03 | 2015-08-03 | Jurado/Fabricio | Delete | Remove detail |  |  | Unnecessary detail complicates the plan
5 | 1.2.6.16.6 | TASK: Reputational/Strategic Material Risk Aggregation | 98% | 41d? | 2015-08-03 | 2015-09-28 |  | Date Change |  | 2015-08-01 | 2015-08-31 |  | Finish one month early
6 | 1.2.6.16.6.1 | ERM disseminates Workshop Pre-Read Materials to Risk Managers | 50% | 16d? | 2015-08-03 | 2015-08-24 |  | Delete | Remove detail |  |  | Unnecessary detail complicates the plan
6 | 1.2.6.16.6.2 | ERM facilitates Aggregation and Enrichment Workshop | 50% | 25d? | 2015-08-25 | 2015-09-28 |  | Delete | Remove detail |  |  | Unnecessary detail complicates the plan
6 | 1.2.6.16.6.3 | Risk Manager presents inventory to level II subcommittee | 0% | 1d? | 2015-08-03 | 2015-08-03 |  | Delete | Remove detail |  |  | Unnecessary detail complicates the plan
6 | 1.2.6.16.6.4 | Reputational/Strategic Material Risk Aggregation Prepared | 0% | 0d | 2015-08-03 | 2015-08-03 | Jurado/Fabricio | Delete | Remove detail |  |  | Unnecessary detail complicates the plan
4 | 1.2.6.17 | MILESTONE:Present Results to PR Santander Bancorp ERMC | 50% | 48d | 2015-07-28 | 2015-10-01 | Jurado/Fabricio | Contact | Jurado/Fabricio -> Jurado
4 | 1.2.6.18 | MILESTONE:Present Results to PR Santander Bancorp BERC | 50% | 48d | 2015-07-28 | 2015-10-01 | Jurado/Fabricio | Contact | Jurado/Fabricio -> Jurado
4 | 1.2.6.19 | Present Puerto Rico Material Risks to CCAR | 0% | 2d | 2015-10-01 | 2015-10-02 |  | Delete |  |  |  | Not provided at entity level-verify with CCAR
4 | 1.2.6.20 | Deliver Puerto Rico Material Risks to CCAR and Capital Plan | 0% | 0d | 2015-10-02 | 2015-10-02 |  | Delete |  |  |  | Not provided at entity level-verify with CCAR
3 | 1.2.7 | DELIVERABLE: Design and execute the Material Risk Program across Miami | 2% | 92d | 2015-05-28 | 2015-10-02 | D. Allaire | Contact | Allaire -> Prado
4 | 1.2.7.1 | MILESTONE:Private Banking Material Risk Inventory | 100% | 2d | 2015-06-29 | 2015-06-30 |  | Date Change |  | 2015-06-29 | 2015-07-31
5 | 1.2.7.1.1 | TASK:Private Banking Material Risk Inventory | 100% | 2d | 2015-06-29 | 2015-06-30 |  | Date/Name Change: "BSI" |  | 2015-06-29 | 2015-07-31 | Miami produced single MRI as "BSI" | What is BSI?
6 | 1.2.7.1.1.1 | Deliver Final Inventory to Miami and SHUSA ERM | 100% | 2d | 2015-06-29 | 2015-06-30 |  | Date Change |  | 2015-06-29 | 2015-07-31 |  | Finish one month late
6 | 1.2.7.1.1.2 | Present inventory to ERMC | 100% | 2d | 2015-06-29 | 2015-06-30 |  | Date Change |  | 2015-06-29 | 2015-07-31 |  | Finish one month late
6 | 1.2.7.1.1.3 | Private Banking Material Risk Inventory Prepared | 100% | 0d | 2015-06-30 | 2015-06-30 | Prado/Madargia | Date Change/Contact | Prado/Madargia -> Prado | 2015-06-29 | 2015-07-31 |  | Finish one month late
4 | 1.2.7.2 | MILESTONE:Personal Lending Material Risk Inventory | 100% | 2d | 2015-06-29 | 2015-06-30 |  | Delete |  |  |  | BSI is not creating these inventories
5 | 1.2.7.2.1 | TASK:Personal Lending Material Risk Inventory | 100% | 2d | 2015-06-29 | 2015-06-30 |  | Delete |  |  |  | BSI is not creating these inventories
6 | 1.2.7.2.1.1 | Deliver Final Inventory to Miami and SHUSA ERM | 100% | 2d | 2015-06-29 | 2015-06-30 |  | Delete |  |  |  | BSI is not creating these inventories
6 | 1.2.7.2.1.2 | Present inventory to ERMC | 100% | 2d | 2015-06-29 | 2015-06-30 |  | Delete |  |  |  | BSI is not creating these inventories
6 | 1.2.7.2.1.3 | Personal Lending Material Risk Inventory Prepared | 100% | 0d | 2015-06-30 | 2015-06-30 | Prado/Madargia | Delete |  |  |  | BSI is not creating these inventories
4 | 1.2.7.3 | MILESTONE: Hold Miami Aggregation Workshops (include 2 LOD challenge) | 0% | 45d | 2015-08-03 | 2015-10-02 |  | Date Change |  | 2015-08-01 | 2015-08-31 |  | Finish one month early
5 | 1.2.7.3.1 | TASK: Credit Risk Aggregation | 0% | 41d? | 2015-08-03 | 2015-09-28 |  | Date Change |  | 2015-08-01 | 2015-08-31 |  | Finish one month early
6 | 1.2.7.3.1.1 | ERM disseminates Workshop Pre-Read Materials to Risk Managers | 100% | 16d? | 2015-08-03 | 2015-08-24 |  | Delete | Remove detail |  |  | Unnecessary detail complicates the plan
6 | 1.2.7.3.1.2 | ERM facilitates Aggregation and Enrichment Activities | 100% | 25d? | 2015-08-25 | 2015-09-28 |  | Delete | Remove detail |  |  | Unnecessary detail complicates the plan
6 | 1.2.7.3.1.3 | Risk Manager presents inventory to level II subcommittee | 50% | 1d? | 2015-08-03 | 2015-08-03 |  | Delete | Remove detail |  |  | Unnecessary detail complicates the plan
6 | 1.2.7.3.1.4 | Credit Risk Aggregation Prepared | 50% | 0d | 2015-08-03 | 2015-08-03 | Prado/Madargia | Delete | Remove detail |  |  | Unnecessary detail complicates the plan
5 | 1.2.7.3.2 | TASK: Operational Risk Material Risk Aggregation | 0% | 41d? | 2015-08-03 | 2015-09-28 |  | Date Change |  | 2015-08-01 | 2015-08-31 |  | Finish one month early
6 | 1.2.7.3.2.1 | ERM disseminates Workshop Pre-Read Materials to Risk Managers | 100% | 16d? | 2015-08-03 | 2015-08-24 |  | Delete | Remove detail |  |  | Unnecessary detail complicates the plan
6 | 1.2.7.3.2.2 | ERM facilitates Aggregation and Enrichment Activities | 100% | 25d? | 2015-08-25 | 2015-09-28 |  | Delete | Remove detail |  |  | Unnecessary detail complicates the plan
6 | 1.2.7.3.2.3 | Risk Manager presents inventory to level II subcommittee | 50% | 1d? | 2015-08-03 | 2015-08-03 |  | Delete | Remove detail |  |  | Unnecessary detail complicates the plan
6 | 1.2.7.3.2.4 | Operational Risk Material Risk Aggregation Prepared | 50% | 0d | 2015-08-03 | 2015-08-03 | Prado/Madargia | Delete | Remove detail |  |  | Unnecessary detail complicates the plan
5 | 1.2.7.3.3 | TASK: Compliance Material Risk Aggregation | 0% | 41d? | 2015-08-03 | 2015-09-28 |  | Date Change |  | 2015-08-01 | 2015-08-31 |  | Finish one month early
6 | 1.2.7.3.3.1 | ERM disseminates Workshop Pre-Read Materials to Risk Managers | 100% | 16d? | 2015-08-03 | 2015-08-24 |  | Delete | Remove detail |  |  | Unnecessary detail complicates the plan
6 | 1.2.7.3.3.2 | ERM facilitates Aggregation and Enrichment Activities | 100% | 25d? | 2015-08-25 | 2015-09-28 |  | Delete | Remove detail |  |  | Unnecessary detail complicates the plan
6 | 1.2.7.3.3.3 | Risk Manager presents inventory to level II subcommittee | 50% | 1d? | 2015-08-03 | 2015-08-03 |  | Delete | Remove detail |  |  | Unnecessary detail complicates the plan
6 | 1.2.7.3.3.4 | Compliance Material Risk Aggregation Prepared | 50% | 0d | 2015-08-03 | 2015-08-03 | Prado/Madargia | Delete | Remove detail |  |  | Unnecessary detail complicates the plan
5 | 1.2.7.3.4 | TASK: Model Material Risk Aggregation | 0% | 41d? | 2015-08-03 | 2015-09-28 |  | Date Change |  | 2015-08-01 | 2015-08-31 |  | Finish one month early
6 | 1.2.7.3.4.1 | ERM disseminates Workshop Pre-Read Materials to Risk Managers | 100% | 16d? | 2015-08-03 | 2015-08-24 |  | Delete | Remove detail |  |  | Unnecessary detail complicates the plan
6 | 1.2.7.3.4.2 | ERM facilitates Aggregation and Enrichment Workshop | 100% | 25d? | 2015-08-25 | 2015-09-28 |  | Delete | Remove detail |  |  | Unnecessary detail complicates the plan
6 | 1.2.7.3.4.3 | Risk Manager presents inventory to level II subcommittee | 50% | 1d? | 2015-08-03 | 2015-08-03 |  | Delete | Remove detail |  |  | Unnecessary detail complicates the plan
6 | 1.2.7.3.4.4 | Model Material Risk Aggregation Prepared | 50% | 0d | 2015-08-03 | 2015-08-03 | Prado/Madargia | Delete | Remove detail |  |  | Unnecessary detail complicates the plan
5 | 1.2.7.3.5 | TASK: Liquidity/Market Material Risk Aggregation | 0% | 41d? | 2015-08-03 | 2015-09-28 |  | Date Change |  | 2015-08-01 | 2015-08-31 |  | Finish one month early
6 | 1.2.7.3.5.1 | ERM disseminates Workshop Pre-Read Materials to Risk Managers | 100% | 16d? | 2015-08-03 | 2015-08-24 |  | Delete | Remove detail |  |  | Unnecessary detail complicates the plan
6 | 1.2.7.3.5.2 | ERM facilitates Aggregation and Enrichment Activities | 100% | 25d? | 2015-08-25 | 2015-09-28 |  | Delete | Remove detail |  |  | Unnecessary detail complicates the plan
6 | 1.2.7.3.5.3 | Risk Manager presents inventory to level II subcommittee | 50% | 1d? | 2015-08-03 | 2015-08-03 |  | Delete | Remove detail |  |  | Unnecessary detail complicates the plan
6 | 1.2.7.3.5.4 | Liquidity/Market Material Risk Aggregation Prepared | 50% | 0d | 2015-08-03 | 2015-08-03 | Prado/Madargia | Delete | Remove detail |  |  | Unnecessary detail complicates the plan
5 | 1.2.7.3.6 | TASK: Reputational/Strategic Material Risk Aggregation | 0% | 41d? | 2015-08-03 | 2015-09-28 |  | Date Change |  | 2015-08-01 | 2015-08-31 |  | Finish one month early
6 | 1.2.7.3.6.1 | ERM disseminates Workshop Pre-Read Materials to Risk Managers | 100% | 16d? | 2015-08-03 | 2015-08-24 |  | Delete | Remove detail |  |  | Unnecessary detail complicates the plan
6 | 1.2.7.3.6.2 | ERM facilitates Aggregation and Enrichment Workshop | 100% | 25d? | 2015-08-25 | 2015-09-28 |  | Delete | Remove detail |  |  | Unnecessary detail complicates the plan
6 | 1.2.7.3.6.3 | Risk Manager presents inventory to level II subcommittee | 50% | 1d? | 2015-08-03 | 2015-08-03 |  | Delete | Remove detail |  |  | Unnecessary detail complicates the plan
6 | 1.2.7.3.6.4 | Reputational/Strategic Material Risk Aggregation Prepared | 50% | 0d | 2015-08-03 | 2015-08-03 | Prado/Madargia | Delete | Remove detail |  |  | Unnecessary detail complicates the plan
4 | 1.2.7.4 | MILESTONE:Present Miami to SCUSA ERMC | 0% | 48d | 2015-07-28 | 2015-10-01 | Prado/Madargia | Contact | Prado/Madargia -> Prado
4 | 1.2.7.5 | MILESTONE:Present Miami to SCUSA BERC | 0% | 48d | 2015-07-28 | 2015-10-01 | Prado/Madargia | Contact | Prado/Madargia -> Prado
4 | 1.2.7.6 | Present Miami Material Risks to CCAR | 0% | 2d | 2015-10-01 | 2015-10-02 |  | Delete |  |  |  | Not deliver at entity level-verify with CCAR
4 | 1.2.7.7 | Deliver Miami Material Risks to CCAR and Capital Plan | 0% | 0d | 2015-10-02 | 2015-10-02 |  | Delete |  |  |  | Not deliver at entity level-verify with CCAR
2 | 1.3 | Review foundational Risk ID processes including data and technology supporting the Material Risk Program and build multi-year enhancement objectives | 0% | 95d | 2016-01-18 | 2016-05-27 | E. Smith
3 | 1.3.1 | DELIVERABLE: Assess foundational Risk ID processes and ensure complete Foundational Risk Inventory is in place | 0% | 30d | 2016-01-18 | 2016-02-26 | D. Allaire | Contact | D. Allaire -> E. Smith
4 | 1.3.1.1 | MILESTONE: Assess Foundational Risk Processes and ensure complete foundational risk inventory is in place | 0% | 30d | 2016-01-18 | 2016-02-26
5 | 1.3.1.1.1 | Identify existing Foundational Risk Processes | 0% | 30d | 2016-01-18 | 2016-02-26
5 | 1.3.1.1.2 | Confirm and validated foundational risk inventory - develop or enhance as needed | 0% | 30d | 2016-01-18 | 2016-02-26
5 | 1.3.1.1.3 | MILESTONE: Landscape of Foundational Risk Processes and risk inventory confirmed | 0% | 1d | 2016-02-26 | 2016-02-26
3 | 1.3.2 | DELIVERABLE: Review each foundational Risk ID process, identify deficiencies in data, technology and processes, and use gap analyses to determine how to optimize | 0% | 55d | 2016-02-29 | 2016-05-13 | D. Allaire | Contact | D. Allaire -> E. Smith
4 | 1.3.2.1 | MILESTONE: Review each Foundational Risk Process, identify deficient processes, and use gap analyses to determine how to optimize processes | 0% | 55d | 2016-02-29 | 2016-05-13
5 | 1.3.2.1.1 | Review and assess each Foundational Risk Process | 0% | 55d | 2016-02-29 | 2016-05-13
5 | 1.3.2.1.2 | Determine optimal future state for each process | 0% | 55d | 2016-02-29 | 2016-05-13
5 | 1.3.2.1.3 | Perform gap analyses for processes determined to be deficient | 0% | 55d | 2016-02-29 | 2016-05-13
5 | 1.3.2.1.4 | MILESTONE: Each Foundational Risk Process reviewed and assessed | 0% | 0d | 2016-03-31 | 2016-03-31
3 | 1.3.3 | DELIVERABLE: Develop remediation plans for foundational Risk ID processes | 0% | 23d | 2016-04-27 | 2016-05-27 | D. Allaire | Contact | D. Allaire -> E. Smith
4 | 1.3.3.1 | MILESTONE: Remediation of Foundational Risk Process plan Developed | 0% | 23d | 2016-04-27 | 2016-05-27
5 | 1.3.3.1.1 | Identify deficiencies in current plan | 0% | 23d | 2016-04-27 | 2016-05-27
5 | 1.3.3.1.2 | Determine optimal state for plan | 0% | 23d | 2016-04-27 | 2016-05-27
5 | 1.3.3.1.3 | Perform gap analysis in order to develop plan remediation | 0% | 23d | 2016-04-27 | 2016-05-27
5 | 1.3.3.1.4 | MILESTONE: Plan remediation developed | 0% | 0d | 2016-04-27 | 2016-04-27
2 | 1.4 | DELIVERABLE: Execute remediation plans for foundational Risk ID processes, including requirements definition, development and implementation of planned data and technology solutions to support risk identification | 0% |  | 2016-05-30 |  | E. Smith | Delete |  |  |  | This should not be in the plan | In the slide to Fed
2 | 1.5 | Long Term Planning Package | 0% | 295d | 2015-11-30 | 2017-01-13
3 | 1.5.1 | DELIVERABLE: Updated SHUSA Risk taxonomy for Material Risk Program | 0% | 35d | 2015-11-30 | 2016-01-15 | D. Allaire | Contact | D. Allaire -> E. Smith
4 | 1.5.1.1 | MILESTONE: Draft of updated risk taxonomy based on 2015 results | 0% | 16d | 2015-11-30 | 2015-12-20
4 | 1.5.1.2 | MILESTONE: Final updated risk taxonomy based on 2015 results | 0% | 24d | 2015-12-15 | 2016-01-15
3 | 1.5.2 | DELIVERABLE: Updated material risk inventory template and guidance for Material Risk Program | 0% | 30d | 2016-01-18 | 2016-02-26 | D. Allaire | Contact | D. Allaire -> E. Smith
4 | 1.5.2.1 | MILESTONE: Updated material risk inventory template | 0% | 30d | 2016-01-18 | 2016-02-26
4 | 1.5.2.2 | MILESTONE: Updated material risk guidance | 0% | 30d | 2016-01-18 | 2016-02-26
4 | 1.5.2.3 | MILESTONE: Updated aggregation and enrichment guidance | 0% | 30d | 2016-01-18 | 2016-02-26
3 | 1.5.3 | DELIVERABLE: Identify technology needs, requirements definition and implementation planning to support risk identification | 0% | 50d | 2016-05-16 | 2016-07-22 | D. Allaire | Delete |  |  |  | This should not be in the plan
4 | 1.5.3.1 | MILESTONE: Technology requirements and BRD for risk inventory template web interface | 0% | 14d | 2016-01-01 | 2016-01-20 |  | Delete |  |  |  | This should not be in the plan
4 | 1.5.3.2 | Deliver Technology requirements and BRD for Risk inventory template web interface | 0% | 0d | 2016-01-22 | 2016-01-22 |  | Delete |  |  |  | This should not be in the plan
4 | 1.5.3.3 | MILESTONE: Implementation of web interface for risk inventory template | 0% | 24d | 2016-01-20 | 2016-02-22 |  | Delete |  |  |  | This should not be in the plan
4 | 1.5.3.4 | MILESTONE: Web interface pilot with selected business entities | 0% | 20d | 2016-02-22 | 2016-03-18 |  | Delete |  |  |  | This should not be in the plan
4 | 1.5.3.5 | MILESTONE: Roll out of web interface across business entities | 0% | 10d | 2016-03-18 | 2016-03-31 |  | Delete |  |  |  | This should not be in the plan
3 | 1.5.4 | DELIVERABLE: Develop training materials, policies and procedures based on updated Material Risk Program process | 0% | 80d | 2016-02-29 | 2016-06-17 | D. Allaire | Contact | D. Allaire -> E. Smith
4 | 1.5.4.1 | MILESTONE: Development and rollout of training package for material risk ID process | 0% | 80d | 2016-02-29 | 2016-06-17
4 | 1.5.4.2 | MILESTONE: Update and rollout of Policies and procedures for material risk ID process | 0% | 80d | 2016-02-29 | 2016-06-17
3 | 1.5.5 | DELIVERABLE: Develop and implement planned data and technology solutions (e.g. automated interface for risk inventory template, database for foundational inputs and data sources for risk identification, etc.) | 0% | 175d | 2016-05-16 | 2017-01-13 | D. Allaire | Delete |  |  |  | This should not be in the plan
4 | 1.5.5.1 | MILESTONE: Development of technology requirements and BRDs for database with business entity level foundational inputs and data sources | 0% | 24d | 2016-03-15 | 2016-04-15 |  | Delete |  |  |  | This should not be in the plan
4 | 1.5.5.2 | MILESTONE: Implementation of database for foundational inputs and data sources | 0% | 110d | 2016-03-15 | 2016-08-15 |  | Delete |  |  |  | This should not be in the plan
4 | 1.5.5.3 | MILESTONE: Database pilot for selected business entities | 0% | 23d | 2016-08-15 | 2016-09-14 |  | Delete |  |  |  | This should not be in the plan
4 | 1.5.5.4 | MILESTONE: Roll out of database across business entities | 0% | 45d | 2016-09-14 | 2016-11-15 |  | Delete |  |  |  | This should not be in the plan
3 | 1.5.6 | DELIVERABLE: Training materials, policies and procedures for risk ID database and process | 0% | 44d | 2016-11-15 | 2017-01-13 | D. Allaire | Delete |  |  |  | This should not be in the plan | In the slide to Fed
4 | 1.5.6.1 | MILESTONE: Training package for material risk ID database and process developed and rolled out | 0% | 44d | 2016-11-15 | 2017-01-13 |  | Delete |  |  |  | This should not be in the plan
4 | 1.5.6.2 | MILESTONE: Policies and procedures for material risk ID process updated and rolled out | 0% | 44d | 2016-11-15 | 2017-01-13 |  | Delete |  |  |  | This should not be in the plan

## percentage update
WBS | Task Name | most updated % Complete | Original | OK if greater than zero(which means progress from Original) | % Complete | Task Name
0 | RT_Risk ID and Measurement 0728 1730 | 36% | 36% | 0% | 47%
1 | Risk ID & Measurement | 36% | 36% | 0% | 47%
1.1 | Risk Measurement Deliverables | 0% | 0% | 0% | 0% |  | % Complete
1.1.1 | DELIVERABLE: Program Design and Approval (Risk Taxonomy, Tools, Templates, Guidance) | 100% | 100% | 0% | 100% | DELIVERABLE: Program Design and Approval (Risk Taxonomy, Tools, Templates, Guidance) | 100% | 0%
1.1.2 | DELIVERABLE: SHUSA Material Risk Program | 0% | 0% | 0% | 0% | DELIVERABLE: SHUSA Material Risk Program | 0% | 0%
1.1.3 | DELIVERABLE: SBNA - Business Entity Material Risk Program | 0% | 0% | 0% | 0% | DELIVERABLE: SBNA - Business Entity Material Risk Program | 0% | 0%
1.1.4 | DELIVERABLE: SCUSA - Business Entity Material Risk Program | 0% | 0% | 0% | 0% | DELIVERABLE: SCUSA - Business Entity Material Risk Program | 0% | 0%
1.1.5 | DELIVERABLE: New York Santander Investment Securities (SIS) - Business Entity Material Risk Program | 0% | 0% | 0% | 0% | DELIVERABLE: New York Santander Investment Securities (SIS) - Business Entity Material Risk Program | 0% | 0%
1.1.6 | DELIVERABLE: Puerto Rico - Business Entity Material Risk Program | 0% | 0% | 0% | 0% | DELIVERABLE: Puerto Rico - Business Entity Material Risk Program | 0% | 0%
1.1.7 | DELIVERABLE: Miami - Business Entity Material Risk Program | 0% | 0% | 0% | 0% | DELIVERABLE: Miami - Business Entity Material Risk Program | 0% | 0%
1.1.8 | DELIVERABLE: Assess Foundational Risk Processes and ensure complete Foundational Risk Inventory is in place | 0% | 0% | 0% | 0% | DELIVERABLE: Assess Foundational Risk Processes and ensure complete Foundational Risk Inventory is in place | 0% | 0%
1.1.9 | DELIVERABLE: Review each Foundational Risk Process; identify deficient processes, and use gap analyses to determine how to optimize processes | 0% | 0% | 0% | 0% | DELIVERABLE: Review each Foundational Risk Process; identify deficient processes, and use gap analyses to determine how to optimize processes | 0% | 0%
1.1.10 | DELIVERABLE: Develop Foundational Risk Process remediation plan | 0% | 0% | 0% | 0% | DELIVERABLE: Develop Foundational Risk Process remediation plan | 0% | 0%
1.1.11 | DELIVERABLE: Updated risk taxonomy | 0% | 0% | 0% | 0% | DELIVERABLE: Updated risk taxonomy | 0% | 0%
1.1.12 | DELIVERABLE: Updated material risk inventory template and guidance | 0% | 0% | 0% | 0% | DELIVERABLE: Updated material risk inventory template and guidance | 0% | 0%
1.1.13 | DELIVERABLE: Identification of technology needs, requirements definition and implementation planning to support risk identification | 0% | 0% | 0% | 0% | DELIVERABLE: Identification of technology needs, requirements definition and implementation planning to support risk identification | 0% | 0%
1.1.14 | DELIVERABLE: Training materials, policies and procedures based on updated material risk program process | 0% | 0% | 0% | 0% | DELIVERABLE: Training materials, policies and procedures based on updated material risk program process | 0% | 0%
1.1.15 | DELIVERABLE: Development and implementation of planned data and technology solutions (e.g. automated interfaces for risk inventory template, database for foundational inputs and data sources for risk identification, etc) | 0% | 0% | 0% | 0% | DELIVERABLE: Development and implementation of planned data and technology solutions (e.g. automated interfaces for risk inventory template, database for foundational inputs and data sources for risk identification, etc) | 0% | 0%
1.1.16 | DELIVERABLE: Training materials, policies and procedures for risk ID database and process | 0% | 0% | 0% | 0% | DELIVERABLE: Training materials, policies and procedures for risk ID database and process | 0% | 0%
1.2 | Design and execute the Material Risk Program across SHUSA (leveraging existing data and technology) | 44% | 44% | 0% | 58% | Design and execute the Material Risk Program across SHUSA (leveraging existing data and technology) | 58% | -14%
1.2.1 | DELIVERABLE: Design material risk program and obtain approvals (incl. risk taxonomy, tools, templates, guidance) | 100% | 100% | 0% | 100% | DELIVERABLE: Design material risk program and obtain approvals (incl. risk taxonomy, tools, templates, guidance) | 100% | 0%
1.2.1.1 | MILESTONE: Program Design and Approval (Risk Taxonomy, Tools, Templates, Guidance) | 100% | 100% | 0% | 100% | MILESTONE: Program Design and Approval (Risk Taxonomy, Tools, Templates, Guidance) | 100% | 0%
1.2.2 | DELIVERABLE: Create risk inventory for the SHUSA, hold workshops for aggregation | 0% | 0% | 0% | 0% | DELIVERABLE: Create risk inventory for the SHUSA, hold workshops for aggregation | 0% | 0%
1.2.2.1 | MILESTONE: Preparation for Aggregation to Create SHUSA Material Risk Inventory | 0% | 0% | 0% | 0% | MILESTONE: Preparation for Aggregation to Create SHUSA Material Risk Inventory | 0% | 0%
1.2.2.1.1 | ERM Collects Risk Inventories from Entity Risk Managers | 0% | 0% | 0% | 0% | ERM Collects Risk Inventories from Entity Risk Managers | 0% | 0%
1.2.2.1.2 | ERM Sorts risks and groups by Risk Type | 0% | 0% | 0% | 0% | ERM Sorts risks and groups by Risk Type | 0% | 0%
1.2.2.1.3 | ERM Creates pre-Workshop, pre-read Materials and instructions for SHUSA Risk Managers | 0% | 0% | 0% | 0% | ERM Creates pre-Workshop, pre-read Materials and instructions for SHUSA Risk Managers | 0% | 0%
1.2.2.1.4 | ERM Distributes Workshop Materials to Responsible parties | 0% | 0% | 0% | 0% | ERM Distributes Workshop Materials to Responsible parties | 0% | 0%
1.2.2.1.5 | Aggregation to Create SHUSA Material Risk Inventory Prepared | 0% | 0% | 0% | 0% | Aggregation to Create SHUSA Material Risk Inventory Prepared | 0% | 0%
1.2.2.2 | MILESTONE: Hold SHUSA Aggregation Workshops (include 2nd LOD challenge) | 0% | 0% | 0% | 0% | MILESTONE: Hold SHUSA Aggregation Workshops (include 2nd LOD challenge) | 0% | 0%
1.2.2.2.1 | TASK: Credit Risk Material Risk Aggregation | 0% | 0% | 0% | 0% | TASK: Credit Risk Material Risk Aggregation | 0% | 0%
1.2.2.2.1.1 | Credit Risk performs pre-Read and analysis | 0% | 0% | 0% | 0% | Credit Risk performs pre-Read and analysis | 0% | 0%
1.2.2.2.1.2 | Risk Managers Conduct Credit pre-Workshop Enrichment and Aggregation Activites | 0% | 0% | 0% | 0% | Risk Managers Conduct Credit pre-Workshop Enrichment and Aggregation Activites | 0% | 0%
1.2.2.2.1.3 | ERM facilitates Credit Aggregation and Enrichment Workshop | 0% | 0% | 0% | 0% | ERM facilitates Credit Aggregation and Enrichment Workshop | 0% | 0%
1.2.2.2.1.4 | Present to Level II Subcommittees | 0% | 0% | 0% | 0% | Present to Level II Subcommittees | 0% | 0%
1.2.2.2.1.5 | Credit Risk Material Risk Aggregation Prepared | 0% | 0% | 0% | 0% | Credit Risk Material Risk Aggregation Prepared | 0% | 0%
1.2.2.2.2 | TASK: Operational Risk Material Risk Aggregation | 0% | 0% | 0% | 0% | TASK: Operational Risk Material Risk Aggregation | 0% | 0%
1.2.2.2.2.1 | Operational Risk performs pre-Read and analysis | 0% | 0% | 0% | 0% | Operational Risk performs pre-Read and analysis | 0% | 0%
1.2.2.2.2.2 | Risk Managers Conduct Operational Risk pre-Workshop Enrichment and Aggregation Activites | 0% | 0% | 0% | 0% | Risk Managers Conduct Operational Risk pre-Workshop Enrichment and Aggregation Activites | 0% | 0%
1.2.2.2.2.3 | ERM facilitates Operational Risk Aggregation and Enrichment Workshop | 0% | 0% | 0% | 0% | ERM facilitates Operational Risk Aggregation and Enrichment Workshop | 0% | 0%
1.2.2.2.2.4 | Present to Level II Subcommittees | 0% | 0% | 0% | 0% | Present to Level II Subcommittees | 0% | 0%
1.2.2.2.2.5 | Operational Risk Material Risk Aggregation Prepared | 0% | 0% | 0% | 0% | Operational Risk Material Risk Aggregation Prepared | 0% | 0%
1.2.2.2.3 | TASK: Compliance Material Risk Aggregation | 0% | 0% | 0% | 0% | TASK: Compliance Material Risk Aggregation | 0% | 0%
1.2.2.2.3.1 | Compliance performs pre-Read and analysis | 0% | 0% | 0% | 0% | Compliance performs pre-Read and analysis | 0% | 0%
1.2.2.2.3.2 | Risk Managers Conduct Compliance pre-Workshop Enrichment and Aggregation Activites | 0% | 0% | 0% | 0% | Risk Managers Conduct Compliance pre-Workshop Enrichment and Aggregation Activites | 0% | 0%
1.2.2.2.3.3 | ERM facilitates Compliance Aggregation and Enrichment Workshop | 0% | 0% | 0% | 0% | ERM facilitates Compliance Aggregation and Enrichment Workshop | 0% | 0%
1.2.2.2.3.4 | Present to Level II Subcommittees | 0% | 0% | 0% | 0% | Present to Level II Subcommittees | 0% | 0%
1.2.2.2.3.5 | Compliance Material Risk Aggregation Prepared | 0% | 0% | 0% | 0% | Compliance Material Risk Aggregation Prepared | 0% | 0%
1.2.2.2.4 | TASK: Model Material Risk Aggregation | 0% | 0% | 0% | 0% | TASK: Model Material Risk Aggregation | 0% | 0%
1.2.2.2.4.1 | Model Risk performs pre-Read and analysis | 0% | 0% | 0% | 0% | Model Risk performs pre-Read and analysis | 0% | 0%
1.2.2.2.4.2 | Risk Managers Conduct Model pre-Workshop Enrichment and Aggregation Activites | 0% | 0% | 0% | 0% | Risk Managers Conduct Model pre-Workshop Enrichment and Aggregation Activites | 0% | 0%
1.2.2.2.4.3 | ERM facilitates Model Aggregation and Enrichment Workshop | 0% | 0% | 0% | 0% | ERM facilitates Model Aggregation and Enrichment Workshop | 0% | 0%
1.2.2.2.4.4 | Present to Level II Subcommittees | 0% | 0% | 0% | 0% | Present to Level II Subcommittees | 0% | 0%
1.2.2.2.4.5 | Model Material Risk Aggregation Prepared | 0% | 0% | 0% | 0% | Model Material Risk Aggregation Prepared | 0% | 0%
1.2.2.2.5 | TASK: Market Material Risk Aggregation2 | 0% | 0% | 0% | 0% | TASK: Market Material Risk Aggregation2 | 0% | 0%
1.2.2.2.5.1 | Market Risk performs pre-Read and analysis | 0% | 0% | 0% | 0% | Market Risk performs pre-Read and analysis | 0% | 0%
1.2.2.2.5.2 | Risk Managers Conduct Market pre-Workshop Enrichment and Aggregation Activites | 0% | 0% | 0% | 0% | Risk Managers Conduct Market pre-Workshop Enrichment and Aggregation Activites | 0% | 0%
1.2.2.2.5.3 | ERM facilitates Market Aggregation and Enrichment Workshop | 0% | 0% | 0% | 0% | ERM facilitates Market Aggregation and Enrichment Workshop | 0% | 0%
1.2.2.2.5.4 | Present to Level II Subcommittees | 0% | 0% | 0% | 0% | Present to Level II Subcommittees | 0% | 0%
1.2.2.2.5.5 | Market Material Risk Aggregation Prepared | 0% | 0% | 0% | 0% | Market Material Risk Aggregation Prepared | 0% | 0%
1.2.2.2.6 | TASK: Liquidity Material Risk Aggregation | 0% | 0% | 0% | 0% | TASK: Liquidity Material Risk Aggregation | 0% | 0%
1.2.2.2.6.1 | Liquidity Risk performs pre-Read and analysis | 0% | 0% | 0% | 0% | Liquidity Risk performs pre-Read and analysis | 0% | 0%
1.2.2.2.6.2 | Risk Managers Conduct Liquidity pre-Workshop Enrichment and Aggregation Activites | 0% | 0% | 0% | 0% | Risk Managers Conduct Liquidity pre-Workshop Enrichment and Aggregation Activites | 0% | 0%
1.2.2.2.6.3 | ERM facilitates Liquidity Aggregation and Enrichment Workshop | 0% | 0% | 0% | 0% | ERM facilitates Liquidity Aggregation and Enrichment Workshop | 0% | 0%
1.2.2.2.6.4 | Present to Level II Subcommittees | 0% | 0% | 0% | 0% | Present to Level II Subcommittees | 0% | 0%
1.2.2.2.6.5 | Liquidity Material Risk Aggregation Prepared | 0% | 0% | 0% | 0% | Liquidity Material Risk Aggregation Prepared | 0% | 0%
1.2.2.2.7 | TASK: Strategic Material Risk Aggregation | 0% | 0% | 0% | 0% | TASK: Strategic Material Risk Aggregation | 0% | 0%
1.2.2.2.7.1 | Strategic Risk performs pre-Read and analysis | 0% | 0% | 0% | 0% | Strategic Risk performs pre-Read and analysis | 0% | 0%
1.2.2.2.7.2 | Risk Managers Conduct Strategic pre-Workshop Enrichment and Aggregation Activites | 0% | 0% | 0% | 0% | Risk Managers Conduct Strategic pre-Workshop Enrichment and Aggregation Activites | 0% | 0%
1.2.2.2.7.3 | ERM facilitates Strategic Aggregation and Enrichment Workshop | 0% | 0% | 0% | 0% | ERM facilitates Strategic Aggregation and Enrichment Workshop | 0% | 0%
1.2.2.2.7.4 | Present to Level II Subcommittees | 0% | 0% | 0% | 0% | Present to Level II Subcommittees | 0% | 0%
1.2.2.2.7.5 | Strategic Material Risk Aggregation Prepared | 0% | 0% | 0% | 0% | Strategic Material Risk Aggregation Prepared | 0% | 0%
1.2.2.2.8 | TASK: Reputational Material Risk Aggregation | 0% | 0% | 0% | 0% | TASK: Reputational Material Risk Aggregation | 0% | 0%
1.2.2.2.8.1 | Reputational Risk performs pre-Read and analysis | 0% | 0% | 0% | 0% | Reputational Risk performs pre-Read and analysis | 0% | 0%
1.2.2.2.8.2 | Risk Managers Conduct Reputational pre-Workshop Enrichment and Aggregation Activites | 0% | 0% | 0% | 0% | Risk Managers Conduct Reputational pre-Workshop Enrichment and Aggregation Activites | 0% | 0%
1.2.2.2.8.3 | ERM facilitates Reputational Aggregation and Enrichment Workshop | 0% | 0% | 0% | 0% | ERM facilitates Reputational Aggregation and Enrichment Workshop | 0% | 0%
1.2.2.2.8.4 | Present to Level II Subcommittees | 0% | 0% | 0% | 0% | Present to Level II Subcommittees | 0% | 0%
1.2.2.2.8.5 | Reputational Material Risk Aggregation Prepared | 0% | 0% | 0% | 0% | Reputational Material Risk Aggregation Prepared | 0% | 0%
1.2.2.3 | MILESTONE:Execute on SHUSA Top Down Aggregation (1st and 2nd LOD executive challenge) | 0% | 0% | 0% | 0% | MILESTONE:Execute on SHUSA Top Down Aggregation (1st and 2nd LOD executive challenge) | 0% | 0%
1.2.2.3.1 | TASK:SHUSA Top Down Aggregation | 0% | 0% | 0% | 0% | TASK:SHUSA Top Down Aggregation | 0% | 0%
1.2.2.3.1.1 | ERM consolidates risks into SHUSA Inventory | 0% | 0% | 0% | 0% | ERM consolidates risks into SHUSA Inventory | 0% | 0%
1.2.2.3.1.2 | ERM distributes inventory to SHUSA Business and Risk executives | 0% | 0% | 0% | 0% | ERM distributes inventory to SHUSA Business and Risk executives | 0% | 0%
1.2.2.3.1.3 | ERM incorporates final risks into SHUSA Inventory | 0% | 0% | 0% | 0% | ERM incorporates final risks into SHUSA Inventory | 0% | 0%
1.2.2.3.1.4 | SHUSA Top Down Aggregation Prepared | 0% | 0% | 0% | 0% | SHUSA Top Down Aggregation Prepared | 0% | 0%
1.2.2.4 | MILESTONE:Obtain approvals for Material Risks of SHUSA (final aggregation, Board and Management review and challenge) | 0% | 0% | 0% | 0% | MILESTONE:Obtain approvals for Material Risks of SHUSA (final aggregation, Board and Management review and challenge) | 0% | 0%
1.2.2.4.1 | TASK:Establish Clear Linkage of MRP Outputs to Capital Planning Scenario Design Process | 0% | 0% | 0% | 0% | TASK:Establish Clear Linkage of MRP Outputs to Capital Planning Scenario Design Process | 0% | 0%
1.2.2.4.1.1 | Present SHUSA Material Risks to CCAR and Capital Plan | 0% | 0% | 0% | 0% | Present SHUSA Material Risks to CCAR and Capital Plan | 0% | 0%
1.2.2.4.1.2 | Deliver SHUSA Material Risks to CCAR and Capital Plan | 0% | 0% | 0% | 0% | Deliver SHUSA Material Risks to CCAR and Capital Plan | 0% | 0%
1.2.2.4.2 | TASK:Material Risk SHUSA Approval | 0% | 0% | 0% | 0% | TASK:Material Risk SHUSA Approval | 0% | 0%
1.2.2.4.2.1 | Present SHUSA Material Risks to BERC | 0% | 0% | 0% | 0% | Present SHUSA Material Risks to BERC | 0% | 0%
1.2.2.4.2.2 | Present SHUSA Material Risks to ERMC | 0% | 0% | 0% | 0% | Present SHUSA Material Risks to ERMC | 0% | 0%
1.2.2.4.2.3 | Material Risk SHUSA Approval | 0% | 0% | 0% | 0% | Material Risk SHUSA Approval | 0% | 0%
1.2.2.5 | MILESTONE:Draft Risk ID and Assessment Policy and obtain approvals | 0% | 0% | 0% | 0% | MILESTONE:Draft Risk ID and Assessment Policy and obtain approvals | 0% | 0%
1.2.2.5.1 | TASK:Risk ID and Assessment Policy | 0% | 0% | 0% | 0% | TASK:Risk ID and Assessment Policy | 0% | 0%
1.2.2.5.1.1 | Risk ID and Assessment group drafts policy | 0% | 0% | 0% | 0% | Risk ID and Assessment group drafts policy | 0% | 0%
1.2.2.5.1.2 | Risk ID and Assessment group presents draft to ERMC for approval | 0% | 0% | 0% | 0% | Risk ID and Assessment group presents draft to ERMC for approval | 0% | 0%
1.2.2.5.1.3 | Risk ID and Assessment group presents to Risk Committee (BERC) | 0% | 0% | 0% | 0% | Risk ID and Assessment group presents to Risk Committee (BERC) | 0% | 0%
1.2.2.5.1.4 | Risk ID and Assessment Policy | 0% | 0% | 0% | 0% | Risk ID and Assessment Policy | 0% | 0%
1.2.3 | DELIVERABLE: Design and execute the Material Risk Program across SBNA | 51% | 51% | 0% | 65% | DELIVERABLE: Design and execute the Material Risk Program across SBNA | 65% | -14%
1.2.3.1 | MILESTONE:Preparation for Aggregation to Create Retail Banking Material Risk Inventory | 95% | 95% | 0% | 100% | MILESTONE:Preparation for Aggregation to Create Retail Banking Material Risk Inventory | 100% | -5%
1.2.3.1.1 | TASK: Small Business Banking Material Risk Inventory | 100% | 100% | 0% | 100% | TASK: Small Business Banking Material Risk Inventory | 100% | 0%
1.2.3.1.1.1 | Deliver Final Inventory to SBNA and SHUSA ERM | 100% | 100% | 0% | 100% | Deliver Final Inventory to SBNA and SHUSA ERM | 100% | 0%
1.2.3.1.1.2 | Small Business Banking Material Risk Inventory Prepared | 100% | 100% | 0% | 100% | Small Business Banking Material Risk Inventory Prepared | 100% | 0%
1.2.3.1.2 | TASK: Cards Material Risk Inventory | 100% | 100% | 0% | 100% | TASK: Cards Material Risk Inventory | 100% | 0%
1.2.3.1.2.1 | Deliver Final Inventory to SBNA and SHUSA ERM | 100% | 100% | 0% | 100% | Deliver Final Inventory to SBNA and SHUSA ERM | 100% | 0%
1.2.3.1.2.2 | Cards Material Risk Inventory Prepared | 100% | 100% | 0% | 100% | Cards Material Risk Inventory Prepared | 100% | 0%
1.2.3.1.3 | TASK: Mortgages Material Risk Inventory | 100% | 100% | 0% | 100% | TASK: Mortgages Material Risk Inventory | 100% | 0%
1.2.3.1.3.1 | Deliver Final Inventory to SBNA and SHUSA ERM | 100% | 100% | 0% | 100% | Deliver Final Inventory to SBNA and SHUSA ERM | 100% | 0%
1.2.3.1.3.2 | Mortgages Material Risk Inventory Prepared | 100% | 100% | 0% | 100% | Mortgages Material Risk Inventory Prepared | 100% | 0%
1.2.3.2 | MILESTONE:Retail: Create Retail Banking Material Risk Inventory | 100% | N/A | #REF! | 100% | MILESTONE:Retail: Create Retail Banking Material Risk Inventory | 100% | 0%
1.2.3.2.1 | TASK: Retail: Create Retail Banking Material Risk Inventory | 100% | N/A | #REF! | 100% | TASK: Retail: Create Retail Banking Material Risk Inventory | 100% | 0%
1.2.3.2.1.1 | Create Segment Material Risk Inventory (Aggregation) | 100% | N/A | #REF! | 100% | Create Segment Material Risk Inventory (Aggregation) | 100% | 0%
1.2.3.2.1.2 | Retail: Create Retail Banking Material Risk Inventory Prepared | 100% | N/A | #REF! | 100% | Retail: Create Retail Banking Material Risk Inventory Prepared | 100% | 0%
1.2.3.3 | MILESTONE:Commercial Banking Material Risk Inventory | 100% | N/A | #REF! | 100% | MILESTONE:Commercial Banking Material Risk Inventory | 100% | 0%
1.2.3.3.1 | TASK: Commercial and Industrial Material Risk Inventory | 100% | N/A | #REF! | 100% | TASK: Commercial and Industrial Material Risk Inventory | 100% | 0%
1.2.3.3.1.1 | Deliver Final Inventory to SBNA and SHUSA ERM | 100% | N/A | #REF! | 100% | Deliver Final Inventory to SBNA and SHUSA ERM | 100% | 0%
1.2.3.3.1.2 | Commercial and Industrial Material Risk Inventory Prepared | 100% | N/A | #REF! | 100% | Commercial and Industrial Material Risk Inventory Prepared | 100% | 0%
1.2.3.3.2 | TASK: Specialties Material Risk Inventory | 100% | N/A | #REF! | 100% | TASK: Specialties Material Risk Inventory | 100% | 0%
1.2.3.3.2.1 | Deliver Final Inventory to SBNA and SHUSA ERM | 100% | 100% | 0% | 100% | Deliver Final Inventory to SBNA and SHUSA ERM | 100% | 0%
1.2.3.3.2.2 | Specialties Material Risk Inventory Prepared | 100% | 100% | 0% | 100% | Specialties Material Risk Inventory Prepared | 100% | 0%
1.2.3.3.3 | TASK: Government Banking Material Risk Inventory | 100% | 100% | 0% | 100% | TASK: Government Banking Material Risk Inventory | 100% | 0%
1.2.3.3.3.1 | Deliver Final Inventory to SBNA and SHUSA ERM | 100% | 100% | 0% | 100% | Deliver Final Inventory to SBNA and SHUSA ERM | 100% | 0%
1.2.3.3.3.2 | Government Banking Material Risk Inventory Prepared | 100% | 100% | 0% | 100% | Government Banking Material Risk Inventory Prepared | 100% | 0%
1.2.3.4 | MILESTONE: Commercial: Create Commercial Banking Material Risk Inventory | 100% | 100% | 0% | 100% | MILESTONE: Commercial: Create Commercial Banking Material Risk Inventory | 100% | 0%
1.2.3.4.1 | TASK: Commercial: Create Commercial Banking Material Risk Inventory | 100% | 100% | 0% | 100% | TASK: Commercial: Create Commercial Banking Material Risk Inventory | 100% | 0%
1.2.3.4.1.1 | Create Segment Material Risk Inventory (Aggregation) | 100% | 100% | 0% | 100% | Create Segment Material Risk Inventory (Aggregation) | 100% | 0%
1.2.3.4.1.2 | Create Commercial Banking Material Risk Inventory Prepared | 100% | 100% | 0% | 100% | Create Commercial Banking Material Risk Inventory Prepared | 100% | 0%
1.2.3.5 | MILESTONE:Global Banking Material Risk Inventory | 100% | 100% | 0% | 100% | MILESTONE:Global Banking Material Risk Inventory | 100% | 0%
1.2.3.5.1 | TASK: MRG Material Risk Inventory | 100% | 100% | 0% | 100% | TASK: MRG Material Risk Inventory | 100% | 0%
1.2.3.5.1.1 | Deliver Final Inventory to SBNA and SHUSA ERM | 100% | 100% | 0% | 100% | Deliver Final Inventory to SBNA and SHUSA ERM | 100% | 0%
1.2.3.5.1.2 | MRG Material Risk Inventory Prepared | 100% | 100% | 0% | 100% | MRG Material Risk Inventory Prepared | 100% | 0%
1.2.3.5.2 | TASK: Large Corporates Material Risk Inventory | 100% | 100% | 0% | 100% | TASK: Large Corporates Material Risk Inventory | 100% | 0%
1.2.3.5.2.1 | Deliver Final Inventory to SBNA and SHUSA ERM | 100% | 100% | 0% | 100% | Deliver Final Inventory to SBNA and SHUSA ERM | 100% | 0%
1.2.3.5.2.2 | Large Corporates Material Risk Inventory Prepared | 100% | 100% | 0% | 100% | Large Corporates Material Risk Inventory Prepared | 100% | 0%
1.2.3.6 | MILESTONE:Global: Create Global Banking Material Risk Inventory | 100% | 100% | 0% | 100% | MILESTONE:Global: Create Global Banking Material Risk Inventory | 100% | 0%
1.2.3.6.1 | TASK: Global: Create Global Banking Material Risk Inventory | 100% | 100% | 0% | 100% | TASK: Global: Create Global Banking Material Risk Inventory | 100% | 0%
1.2.3.6.1.1 | Create Segment Material Risk Inventory (Aggregation) | 100% | 100% | 0% | 100% | Create Segment Material Risk Inventory (Aggregation) | 100% | 0%
1.2.3.6.1.2 | Global: Create Global Banking Material Risk Inventory Prepared | 100% | 100% | 0% | 100% | Global: Create Global Banking Material Risk Inventory Prepared | 100% | 0%
1.2.3.7 | MILESTONE:Automotive Finance Material Risk Inventory | 100% | 100% | 0% | 100% | MILESTONE:Automotive Finance Material Risk Inventory | 100% | 0%
1.2.3.7.1 | TASK: CEVF Material Risk Inventory | 100% | 100% | 0% | 100% | TASK: CEVF Material Risk Inventory | 100% | 0%
1.2.3.7.1.1 | Deliver Final Inventory to SBNA and SHUSA ERM | 100% | 100% | 0% | 100% | Deliver Final Inventory to SBNA and SHUSA ERM | 100% | 0%
1.2.3.7.1.2 | CEVF Material Risk Inventory Prepared | 100% | 100% | 0% | 100% | CEVF Material Risk Inventory Prepared | 100% | 0%
1.2.3.7.2 | TASK: Leasing Material Risk Inventory | 100% | 100% | 0% | 100% | TASK: Leasing Material Risk Inventory | 100% | 0%
1.2.3.7.2.1 | Deliver Final Inventory to SBNA and SHUSA ERM | 100% | 100% | 0% | 100% | Deliver Final Inventory to SBNA and SHUSA ERM | 100% | 0%
1.2.3.7.2.2 | Leasing Material Risk Inventory Prepared | 100% | 100% | 0% | 100% | Leasing Material Risk Inventory Prepared | 100% | 0%
1.2.3.7.3 | TASK: Dealer Floor Plan Material Risk Inventory | 100% | 100% | 0% | 100% | TASK: Dealer Floor Plan Material Risk Inventory | 100% | 0%
1.2.3.7.3.1 | Deliver Final Inventory to SBNA and SHUSA ERM | 100% | 100% | 0% | 100% | Deliver Final Inventory to SBNA and SHUSA ERM | 100% | 0%
1.2.3.7.3.2 | Dealer Floor Plan Material Risk Inventory Prepared | 100% | 100% | 0% | 100% | Dealer Floor Plan Material Risk Inventory Prepared | 100% | 0%
1.2.3.8 | MILESTONE: Automotive: Create Automotive Finance Material Risk Inventory | 100% | 100% | 0% | 100% | MILESTONE: Automotive: Create Automotive Finance Material Risk Inventory | 100% | 0%
1.2.3.8.1 | TASK: Automotive: Create Automotive Finance Material Risk Inventory | 100% | 100% | 0% | 100% | TASK: Automotive: Create Automotive Finance Material Risk Inventory | 100% | 0%
1.2.3.8.1.1 | Create Segment Material Risk Inventory (Aggregation) | 100% | 100% | 0% | 100% | Create Segment Material Risk Inventory (Aggregation) | 100% | 0%
1.2.3.8.1.2 | Automotive Finance Material Risk Inventory Prepared | 100% | 100% | 0% | 100% | Automotive Finance Material Risk Inventory Prepared | 100% | 0%
1.2.3.9 | MILESTONE: Commerical Real Estate Material Risk Inventory | 100% | 100% | 0% | 100% | MILESTONE: Commerical Real Estate Material Risk Inventory | 100% | 0%
1.2.3.9.1 | TASK: Commerical Real Estate Material Risk Inventory | 100% | 100% | 0% | 100% | TASK: Commerical Real Estate Material Risk Inventory | 100% | 0%
1.2.3.9.1.1 | Deliver Final Inventory to SBNA and SHUSA ERM | 100% | 100% | 0% | 100% | Deliver Final Inventory to SBNA and SHUSA ERM | 100% | 0%
1.2.3.9.1.2 | Commerical Real Estate Material Risk Inventory Prepared | 100% | 100% | 0% | 100% | Commerical Real Estate Material Risk Inventory Prepared | 100% | 0%
1.2.3.10 | MILESTONE:Financial Management Material Risk Inventory | N/A | 100% | 0% | 0% | MILESTONE:Financial Management Material Risk Inventory | 0% | #VALUE!
1.2.3.10.1 | TASK: Financial Management Material Risk Inventory | N/A | 100% | 0% | 0% | TASK: Financial Management Material Risk Inventory | 0% | #VALUE!
1.2.3.10.1.1 | Deliver Final Inventory to SBNA and SHUSA ERM | N/A | 100% | 0% | 0% | Deliver Final Inventory to SBNA and SHUSA ERM | 0% | #VALUE!
1.2.3.10.1.2 | Financial Management Material Risk Inventory Prepared | N/A | 100% | 0% | 0% | Financial Management Material Risk Inventory Prepared | 0% | #VALUE!
1.2.3.11 | MILESTONE:Corporate Center Material Risk Inventory | N/A | 100% | 0% | 0% | MILESTONE:Corporate Center Material Risk Inventory | 0% | #VALUE!
1.2.3.11.1 | TASK: Corporate Center Material Risk Inventory | N/A | 100% | 0% | 0% | TASK: Corporate Center Material Risk Inventory | 0% | #VALUE!
1.2.3.11.1.1 | Deliver Final Inventory to SBNA and SHUSA ERM | N/A | 100% | 0% | 0% | Deliver Final Inventory to SBNA and SHUSA ERM | 0% | #VALUE!
1.2.3.11.1.2 | Corporate Center Material Risk Inventory Prepared | N/A | 100% | 0% | 0% | Corporate Center Material Risk Inventory Prepared | 0% | #VALUE!
1.2.3.12 | MILESTONE: Legal Material Risk Inventory | 100% | 100% | 0% | 100% | MILESTONE: Legal Material Risk Inventory | 100% | 0%
1.2.3.12.1 | TASK: Legal Material Risk Inventory | 100% | N/A | #VALUE! | 100% | TASK: Legal Material Risk Inventory | 100% | 0%
1.2.3.12.1.1 | Deliver Final Inventory to SBNA and SHUSA ERM | 100% | N/A | #VALUE! | 100% | Deliver Final Inventory to SBNA and SHUSA ERM | 100% | 0%
1.2.3.12.1.2 | Legal Material Risk Inventory Prepared | 100% | N/A | #VALUE! | 100% | Legal Material Risk Inventory Prepared | 100% | 0%
1.2.3.13 | MILESTONE:HR Material Risk Inventory | 100% | N/A | #VALUE! | 100% | MILESTONE:HR Material Risk Inventory | 100% | 0%
1.2.3.13.1 | TASK: HR Material Risk Inventory | 100% | N/A | #VALUE! | 100% | TASK: HR Material Risk Inventory | 100% | 0%
1.2.3.13.1.1 | Deliver Final Inventory to SBNA and SHUSA ERM | 100% | N/A | #VALUE! | 100% | Deliver Final Inventory to SBNA and SHUSA ERM | 100% | 0%
1.2.3.13.1.2 | HR Material Risk Inventory Prepared | 100% | N/A | #VALUE! | 100% | HR Material Risk Inventory Prepared | 100% | 0%
1.2.3.14 | MILESTONE:Tech and Operations Material Risk Inventory | 100% | N/A | #VALUE! | 100% | MILESTONE:Tech and Operations Material Risk Inventory | 100% | 0%
1.2.3.14.1 | TASK: Tech and Operations Material Risk Inventory | 100% | 100% | 0% | 100% | TASK: Tech and Operations Material Risk Inventory | 100% | 0%
1.2.3.14.1.1 | Deliver Final Inventory to SBNA and SHUSA ERM | 100% | 100% | 0% | 100% | Deliver Final Inventory to SBNA and SHUSA ERM | 100% | 0%
1.2.3.14.1.2 | Tech and Operations Material Risk Inventory Prepared | 100% | 100% | 0% | 100% | Tech and Operations Material Risk Inventory Prepared | 100% | 0%
1.2.3.15 | MILESTONE:Finance Material Risk Inventory | 100% | 100% | 0% | 100% | MILESTONE:Finance Material Risk Inventory | 100% | 0%
1.2.3.15.1 | TASK: Finance Material Risk Inventory | 100% | 100% | 0% | 100% | TASK: Finance Material Risk Inventory | 100% | 0%
1.2.3.15.1.1 | Deliver Final Inventory to SBNA and SHUSA ERM | 100% | 100% | 0% | 100% | Deliver Final Inventory to SBNA and SHUSA ERM | 100% | 0%
1.2.3.15.1.2 | Finance Material Risk Inventory Prepared | 100% | 100% | 0% | 100% | Finance Material Risk Inventory Prepared | 100% | 0%
1.2.3.16 | MILESTONE:Hold SBNA Aggregation Workshops (include 2nd LOD challenge) | 50% | 100% | 0% | 50% | MILESTONE:Hold SBNA Aggregation Workshops (include 2nd LOD challenge) | 50% | 0%
1.2.3.16.1 | TASK: Credit Risk Aggregation | 50% | 100% | 0% | 50% | TASK: Credit Risk Aggregation | 50% | 0%
1.2.3.16.1.1 | ERM disseminates Workshop Pre-Read Materials to Risk Managers | 50% | 100% | 0% | 50% | ERM disseminates Workshop Pre-Read Materials to Risk Managers | 50% | 0%
1.2.3.16.1.2 | ERM facilitates Aggregation and Enrichment Activities | 50% | 100% | 0% | 50% | ERM facilitates Aggregation and Enrichment Activities | 50% | 0%
1.2.3.16.1.3 | Risk Manager presents inventory to level II subcommittee | 50% | 100% | 0% | 50% | Risk Manager presents inventory to level II subcommittee | 50% | 0%
1.2.3.16.1.4 | Credit Risk Aggregation Prepared | 50% | 100% | 0% | 50% | Credit Risk Aggregation Prepared | 50% | 0%
1.2.3.16.2 | TASK: Operational Risk Material Risk Aggregation | 50% | 100% | 0% | 50% | TASK: Operational Risk Material Risk Aggregation | 50% | 0%
1.2.3.16.2.1 | ERM disseminates Workshop Pre-Read Materials to Risk Managers | 50% | 100% | 0% | 50% | ERM disseminates Workshop Pre-Read Materials to Risk Managers | 50% | 0%
1.2.3.16.2.2 | ERM facilitates Aggregation and Enrichment Activities | 50% | 100% | 0% | 50% | ERM facilitates Aggregation and Enrichment Activities | 50% | 0%
1.2.3.16.2.3 | Risk Manager presents inventory to level II subcommittee | 50% | 50% | 0% | 50% | Risk Manager presents inventory to level II subcommittee | 50% | 0%
1.2.3.16.2.4 | Operational Risk Material Risk Aggregation Prepared | 50% | 50% | 0% | 50% | Operational Risk Material Risk Aggregation Prepared | 50% | 0%
1.2.3.16.3 | TASK: Compliance Material Risk Aggregation | 50% | 50% | 0% | 50% | TASK: Compliance Material Risk Aggregation | 50% | 0%
1.2.3.16.3.1 | ERM disseminates Workshop Pre-Read Materials to Risk Managers | 50% | 50% | 0% | 50% | ERM disseminates Workshop Pre-Read Materials to Risk Managers | 50% | 0%
1.2.3.16.3.2 | ERM facilitates Aggregation and Enrichment Activities | 50% | 50% | 0% | 50% | ERM facilitates Aggregation and Enrichment Activities | 50% | 0%
1.2.3.16.3.3 | Risk Manager presents inventory to level II subcommittee | 50% | 50% | 0% | 50% | Risk Manager presents inventory to level II subcommittee | 50% | 0%
1.2.3.16.3.4 | Compliance Material Risk Aggregation Prepared | 50% | 50% | 0% | 50% | Compliance Material Risk Aggregation Prepared | 50% | 0%
1.2.3.16.4 | TASK: Model Material Risk Aggregation | 50% | 50% | 0% | 50% | TASK: Model Material Risk Aggregation | 50% | 0%
1.2.3.16.4.1 | ERM disseminates Workshop Pre-Read Materials to Risk Managers | 50% | 50% | 0% | 50% | ERM disseminates Workshop Pre-Read Materials to Risk Managers | 50% | 0%
1.2.3.16.4.2 | ERM facilitates Aggregation and Enrichment Activities | 50% | 50% | 0% | 50% | ERM facilitates Aggregation and Enrichment Activities | 50% | 0%
1.2.3.16.4.3 | Risk Manager presents inventory to level II subcommittee | 50% | 50% | 0% | 50% | Risk Manager presents inventory to level II subcommittee | 50% | 0%
1.2.3.16.4.4 | Model Material Risk Aggregation Prepared | 50% | 50% | 0% | 50% | Model Material Risk Aggregation Prepared | 50% | 0%
1.2.3.16.5 | TASK: Liquidity/Market Material Risk Aggregation | 50% | 50% | 0% | 50% | TASK: Liquidity/Market Material Risk Aggregation | 50% | 0%
1.2.3.16.5.1 | ERM disseminates Workshop Pre-Read Materials to Risk Managers | 50% | 50% | 0% | 50% | ERM disseminates Workshop Pre-Read Materials to Risk Managers | 50% | 0%
1.2.3.16.5.2 | ERM facilitates Aggregation and Enrichment Activities | 50% | 50% | 0% | 50% | ERM facilitates Aggregation and Enrichment Activities | 50% | 0%
1.2.3.16.5.3 | Risk Manager presents inventory to level II subcommittee | 50% | 50% | 0% | 50% | Risk Manager presents inventory to level II subcommittee | 50% | 0%
1.2.3.16.5.4 | Liquidity/Market Material Risk Aggregation Prepared | 50% | 50% | 0% | 50% | Liquidity/Market Material Risk Aggregation Prepared | 50% | 0%
1.2.3.16.6 | TASK: Reputational/Strategic Material Risk Aggregation | 50% | 50% | 0% | 50% | TASK: Reputational/Strategic Material Risk Aggregation | 50% | 0%
1.2.3.16.6.1 | ERM disseminates Workshop Pre-Read Materials to Risk Managers | 50% | 50% | 0% | 50% | ERM disseminates Workshop Pre-Read Materials to Risk Managers | 50% | 0%
1.2.3.16.6.2 | ERM facilitates Aggregation and Enrichment Workshop | 50% | 50% | 0% | 50% | ERM facilitates Aggregation and Enrichment Workshop | 50% | 0%
1.2.3.16.6.3 | Risk Manager presents inventory to level II subcommittee | 50% | 50% | 0% | 50% | Risk Manager presents inventory to level II subcommittee | 50% | 0%
1.2.3.16.6.4 | Reputational/Strategic Material Risk Aggregation Prepared | 50% | 50% | 0% | 50% | Reputational/Strategic Material Risk Aggregation Prepared | 50% | 0%
1.2.3.17 | Present Results to SBNA ERMC | 0% | 50% | 0% | 0% | Present Results to SBNA ERMC | 0% | 0%
1.2.3.18 | Present Results to SBNA BERC | 0% | 50% | 0% | 0% | Present Results to SBNA BERC | 0% | 0%
1.2.3.19 | Present SBNA Results to CCAR | 0% | 50% | 0% | 0% | Present SBNA Results to CCAR | 0% | 0%
1.2.3.20 | Deliver SBNA Material Risks to CCAR and Capital Plan | 0% | 50% | 0% | 0% | Deliver SBNA Material Risks to CCAR and Capital Plan | 0% | 0%
1.2.4 | DELIVERABLE: Design and execute the Material Risk Program across SCUSA | 2% | 50% | 0% | 2% | DELIVERABLE: Design and execute the Material Risk Program across SCUSA | 2% | 0%
1.2.4.1 | MILESTONE: Automotive Finance Material Risk Inventory | 8% | 50% | 0% | 8% | MILESTONE: Automotive Finance Material Risk Inventory | 8% | 0%
1.2.4.1.1 | TASK:Automotive Finance Material Risk Inventory | 8% | 50% | 0% | 8% | TASK:Automotive Finance Material Risk Inventory | 8% | 0%
1.2.4.1.1.1 | Deliver Final Inventory to SCUSA SHUSA ERM | 4% | 50% | 0% | 4% | Deliver Final Inventory to SCUSA SHUSA ERM | 4% | 0%
1.2.4.1.1.2 | Automotive Finance Material Risk Inventory Prepared | 100% | 50% | 0% | 100% | Automotive Finance Material Risk Inventory Prepared | 100% | 0%
1.2.4.2 | MILESTONE: Personal Lending Material Risk Inventory | 8% | 0% | 0% | 8% | MILESTONE: Personal Lending Material Risk Inventory | 8% | 0%
1.2.4.2.1 | TASK:Personal Lending Material Risk Inventory | 8% | 0% | 0% | 8% | TASK:Personal Lending Material Risk Inventory | 8% | 0%
1.2.4.2.1.1 | Deliver Final Inventory to SCUSA SHUSA ERM | 4% | 0% | 0% | 4% | Deliver Final Inventory to SCUSA SHUSA ERM | 4% | 0%
1.2.4.2.1.2 | Personal Lending Material Risk Inventory Prepared | 99% | 0% | 0% | 99% | Personal Lending Material Risk Inventory Prepared | 99% | 0%
1.2.4.3 | MILESTONE: Human Resources Material Risk Inventory | 8% | 2% | 0% | 8% | MILESTONE: Human Resources Material Risk Inventory | 8% | 0%
1.2.4.3.1 | TASK:Human Resources Material Risk Inventory | 8% | 8% | 0% | 8% | TASK:Human Resources Material Risk Inventory | 8% | 0%
1.2.4.3.1.1 | Deliver Final Inventory to SCUSA SHUSA ERM | 4% | 8% | 0% | 4% | Deliver Final Inventory to SCUSA SHUSA ERM | 4% | 0%
1.2.4.3.1.2 | Human Resources Material Risk Inventory Prepared | 100% | 4% | 0% | 100% | Human Resources Material Risk Inventory Prepared | 100% | 0%
1.2.4.4 | MILESTONE: Finance and Accounting Material Risk Inventory | 8% | 100% | 0% | 8% | MILESTONE: Finance and Accounting Material Risk Inventory | 8% | 0%
1.2.4.4.1 | TASK:Finance and Accounting Material Risk Inventory | 8% | 8% | 0% | 8% | TASK:Finance and Accounting Material Risk Inventory | 8% | 0%
1.2.4.4.1.1 | Deliver Final Inventory to SCUSA SHUSA ERM | 4% | 8% | 0% | 4% | Deliver Final Inventory to SCUSA SHUSA ERM | 4% | 0%
1.2.4.4.1.2 | Finance and Accounting Material Risk Inventory Prepared | 100% | 4% | 0% | 100% | Finance and Accounting Material Risk Inventory Prepared | 100% | 0%
1.2.4.5 | MILESTONE: Technology and Operations Material Risk Inventory | 8% | 99% | 0% | 8% | MILESTONE: Technology and Operations Material Risk Inventory | 8% | 0%
1.2.4.5.1 | TASK:Technology and Operations Material Risk Inventory | 8% | 8% | 0% | 8% | TASK:Technology and Operations Material Risk Inventory | 8% | 0%
1.2.4.5.1.1 | Deliver Final Inventory to SCUSA SHUSA ERM | 4% | 8% | 0% | 4% | Deliver Final Inventory to SCUSA SHUSA ERM | 4% | 0%
1.2.4.5.1.2 | Technology and Operations Material Risk Inventory Prepared | 100% | 4% | 0% | 100% | Technology and Operations Material Risk Inventory Prepared | 100% | 0%
1.2.4.6 | MILESTONE: Legal Material Risk Inventory | 8% | 100% | 0% | 8% | MILESTONE: Legal Material Risk Inventory | 8% | 0%
1.2.4.6.1 | TASK:Legal Material Risk Inventory | 8% | 8% | 0% | 8% | TASK:Legal Material Risk Inventory | 8% | 0%
1.2.4.6.1.1 | Deliver Final Inventory to SCUSA SHUSA ERM | 4% | 8% | 0% | 4% | Deliver Final Inventory to SCUSA SHUSA ERM | 4% | 0%
1.2.4.6.1.2 | Legal Material Risk Inventory Prepared | 100% | 4% | 0% | 100% | Legal Material Risk Inventory Prepared | 100% | 0%
1.2.4.7 | MILESTONE: SCUSA Aggregation Workshops (include 2 LOD challenge) | 0% | 100% | 0% | 0% | MILESTONE: SCUSA Aggregation Workshops (include 2 LOD challenge) | 0% | 0%
1.2.4.7.1 | TASK: Credit Risk Aggregation | 0% | 8% | 0% | 0% | TASK: Credit Risk Aggregation | 0% | 0%
1.2.4.7.1.1 | ERM disseminates Workshop Pre-Read Materials to Risk Managers | 0% | 8% | 0% | 0% | ERM disseminates Workshop Pre-Read Materials to Risk Managers | 0% | 0%
1.2.4.7.1.2 | ERM facilitates Aggregation and Enrichment Activities | 0% | 4% | 0% | 0% | ERM facilitates Aggregation and Enrichment Activities | 0% | 0%
1.2.4.7.1.3 | Risk Manager presents inventory to level II subcommittee | 0% | 100% | 0% | 0% | Risk Manager presents inventory to level II subcommittee | 0% | 0%
1.2.4.7.1.4 | Credit Risk Aggregation Prepared | 0% | 8% | 0% | 0% | Credit Risk Aggregation Prepared | 0% | 0%
1.2.4.7.2 | TASK: Operational Risk Material Risk Aggregation | 0% | 8% | 0% | 0% | TASK: Operational Risk Material Risk Aggregation | 0% | 0%
1.2.4.7.2.1 | ERM disseminates Workshop Pre-Read Materials to Risk Managers | 0% | 4% | 0% | 0% | ERM disseminates Workshop Pre-Read Materials to Risk Managers | 0% | 0%
1.2.4.7.2.2 | ERM facilitates Aggregation and Enrichment Activities | 0% | 100% | 0% | 0% | ERM facilitates Aggregation and Enrichment Activities | 0% | 0%
1.2.4.7.2.3 | Risk Manager presents inventory to level II subcommittee | 0% | 0% | 0% | 0% | Risk Manager presents inventory to level II subcommittee | 0% | 0%
1.2.4.7.2.4 | Operational Risk Material Risk Aggregation Prepared | 0% | 0% | 0% | 0% | Operational Risk Material Risk Aggregation Prepared | 0% | 0%
1.2.4.7.3 | TASK: Compliance Material Risk Aggregation | 0% | 0% | 0% | 0% | TASK: Compliance Material Risk Aggregation | 0% | 0%
1.2.4.7.3.1 | ERM disseminates Workshop Pre-Read Materials to Risk Managers | 0% | 0% | 0% | 0% | ERM disseminates Workshop Pre-Read Materials to Risk Managers | 0% | 0%
1.2.4.7.3.2 | ERM facilitates Aggregation and Enrichment Activities | 0% | 0% | 0% | 0% | ERM facilitates Aggregation and Enrichment Activities | 0% | 0%
1.2.4.7.3.3 | Risk Manager presents inventory to level II subcommittee | 0% | 0% | 0% | 0% | Risk Manager presents inventory to level II subcommittee | 0% | 0%
1.2.4.7.3.4 | Compliance Material Risk Aggregation Prepared | 0% | 0% | 0% | 0% | Compliance Material Risk Aggregation Prepared | 0% | 0%
1.2.4.7.4 | TASK: Model Material Risk Aggregation | 0% | 0% | 0% | 0% | TASK: Model Material Risk Aggregation | 0% | 0%
1.2.4.7.4.1 | ERM disseminates Workshop Pre-Read Materials to Risk Managers | 0% | 0% | 0% | 0% | ERM disseminates Workshop Pre-Read Materials to Risk Managers | 0% | 0%
1.2.4.7.4.2 | ERM facilitates Aggregation and Enrichment Activities | 0% | 0% | 0% | 0% | ERM facilitates Aggregation and Enrichment Activities | 0% | 0%
1.2.4.7.4.3 | Risk Manager presents inventory to level II subcommittee | 0% | 0% | 0% | 0% | Risk Manager presents inventory to level II subcommittee | 0% | 0%
1.2.4.7.4.4 | Model Material Risk Aggregation Prepared | 0% | 0% | 0% | 0% | Model Material Risk Aggregation Prepared | 0% | 0%
1.2.4.7.5 | TASK: Liquidity/Market Material Risk Aggregation | 0% | 0% | 0% | 0% | TASK: Liquidity/Market Material Risk Aggregation | 0% | 0%
1.2.4.7.5.1 | ERM disseminates Workshop Pre-Read Materials to Risk Managers | 0% | 0% | 0% | 0% | ERM disseminates Workshop Pre-Read Materials to Risk Managers | 0% | 0%
1.2.4.7.5.2 | ERM facilitates Aggregation and Enrichment Activities | 0% | 0% | 0% | 0% | ERM facilitates Aggregation and Enrichment Activities | 0% | 0%
1.2.4.7.5.3 | Risk Manager presents inventory to level II subcommittee | 0% | 0% | 0% | 0% | Risk Manager presents inventory to level II subcommittee | 0% | 0%
1.2.4.7.5.4 | Liquidity/Market Material Risk Aggregation Prepared | 0% | 0% | 0% | 0% | Liquidity/Market Material Risk Aggregation Prepared | 0% | 0%
1.2.4.7.6 | TASK: Reputational/Strategic Material Risk Aggregation | 0% | 0% | 0% | 0% | TASK: Reputational/Strategic Material Risk Aggregation | 0% | 0%
1.2.4.7.6.1 | ERM disseminates Workshop Pre-Read Materials to Risk Managers | 0% | 0% | 0% | 0% | ERM disseminates Workshop Pre-Read Materials to Risk Managers | 0% | 0%
1.2.4.7.6.2 | ERM facilitates Aggregation and Enrichment Workshop | 0% | 0% | 0% | 0% | ERM facilitates Aggregation and Enrichment Workshop | 0% | 0%
1.2.4.7.6.3 | Risk Manager presents inventory to level II subcommittee | 0% | 0% | 0% | 0% | Risk Manager presents inventory to level II subcommittee | 0% | 0%
1.2.4.7.6.4 | Reputational/Strategic Material Risk Aggregation Prepared | 0% | 0% | 0% | 0% | Reputational/Strategic Material Risk Aggregation Prepared | 0% | 0%
1.2.4.8 | MILESTONE:Present Results to SCUSA ERMC | 0% | 0% | 0% | 0% | MILESTONE:Present Results to SCUSA ERMC | 0% | 0%
1.2.4.9 | MILESTONE:Present Results to SCUSA BERC | 0% | 0% | 0% | 0% | MILESTONE:Present Results to SCUSA BERC | 0% | 0%
1.2.4.10 | Present SCUSA Material Risks to CCAR | 0% | 0% | 0% | 0% | Present SCUSA Material Risks to CCAR | 0% | 0%
1.2.4.11 | Deliver SCUSA Material Risks to CCAR and Capital Plan | 0% | 0% | 0% | 0% | Deliver SCUSA Material Risks to CCAR and Capital Plan | 0% | 0%
1.2.5 | DELIVERABLE: Design and execute the Material Risk Program across New York Santander Investment Securities (SIS) | 10% | 0% | 0% | 85% | DELIVERABLE: Design and execute the Material Risk Program across New York Santander Investment Securities (SIS) | 85% | -75%
1.2.5.1 | MILESTONE:GBM-Cash Equities Brokerage Material Risk Inventory | 100% | 0% | 0% | 100% | MILESTONE:GBM-Cash Equities Brokerage Material Risk Inventory | 100% | 0%
1.2.5.1.1 | TASK:GBM-Cash Equities Brokerage Material Risk Inventory | 100% | 0% | 0% | 100% | TASK:GBM-Cash Equities Brokerage Material Risk Inventory | 100% | 0%
1.2.5.1.1.1 | Deliver Final Inventory to SIS and SHUSA ERM | 100% | 0% | 0% | 100% | Deliver Final Inventory to SIS and SHUSA ERM | 100% | 0%
1.2.5.1.1.2 | Present inventory to ERMC | 100% | 0% | 0% | 100% | Present inventory to ERMC | 100% | 0%
1.2.5.1.1.3 | Cash Equities Brokerage Material Risk Inventory Prepared | 100% | 0% | 0% | 100% | Cash Equities Brokerage Material Risk Inventory Prepared | 100% | 0%
1.2.5.2 | MILESTONE:GBM- Debt Underwriting Material Risk Inventory | 100% | 0% | 0% | 100% | MILESTONE:GBM- Debt Underwriting Material Risk Inventory | 100% | 0%
1.2.5.2.1 | TASK:GBM- Debt Underwriting Material Risk Inventory | 100% | 0% | 0% | 100% | TASK:GBM- Debt Underwriting Material Risk Inventory | 100% | 0%
1.2.5.2.1.1 | Deliver Final Inventory to SIS and SHUSA ERM | 100% | 0% | 0% | 100% | Deliver Final Inventory to SIS and SHUSA ERM | 100% | 0%
1.2.5.2.1.2 | Present inventory to ERMC | 100% | 10% | 0% | 100% | Present inventory to ERMC | 100% | 0%
1.2.5.2.1.3 | Debt Underwriting Material Risk Inventory Prepared | 100% | 100% | 0% | 100% | Debt Underwriting Material Risk Inventory Prepared | 100% | 0%
1.2.5.3 | MILESTONE:GBM Equity Underwriting Material Risk Inventory | 100% | 100% | 0% | 100% | MILESTONE:GBM Equity Underwriting Material Risk Inventory | 100% | 0%
1.2.5.3.1 | TASK:GBM Equity Underwriting Material Risk Inventory | 100% | 100% | 0% | 100% | TASK:GBM Equity Underwriting Material Risk Inventory | 100% | 0%
1.2.5.3.1.1 | Deliver Final Inventory to SIS and SHUSA ERM | 100% | 100% | 0% | 100% | Deliver Final Inventory to SIS and SHUSA ERM | 100% | 0%
1.2.5.3.1.2 | Present inventory to ERMC | 100% | 100% | 0% | 100% | Present inventory to ERMC | 100% | 0%
1.2.5.3.1.3 | Equity Underwriting Material Risk Inventory Prepared | 100% | 100% | 0% | 100% | Equity Underwriting Material Risk Inventory Prepared | 100% | 0%
1.2.5.4 | MILESTONE:GBM- Fixed Income/Bond TradingMaterial Risk Inventory | 100% | 100% | 0% | 100% | MILESTONE:GBM- Fixed Income/Bond TradingMaterial Risk Inventory | 100% | 0%
1.2.5.4.1 | TASK:GBM- Fixed Income/Bond TradingMaterial Risk Inventory | 100% | 100% | 0% | 100% | TASK:GBM- Fixed Income/Bond TradingMaterial Risk Inventory | 100% | 0%
1.2.5.4.1.1 | Deliver Final Inventory to SIS and SHUSA ERM | 100% | 100% | 0% | 100% | Deliver Final Inventory to SIS and SHUSA ERM | 100% | 0%
1.2.5.4.1.2 | Present inventory to ERMC | 100% | 100% | 0% | 100% | Present inventory to ERMC | 100% | 0%
1.2.5.4.1.3 | Fixed Income/Bond TradingMaterial Risk Inventory Prepared | 100% | 100% | 0% | 100% | Fixed Income/Bond TradingMaterial Risk Inventory Prepared | 100% | 0%
1.2.5.5 | MILESTONE:GBM - Futures Brokerage Material Risk Inventory | 100% | 100% | 0% | 100% | MILESTONE:GBM - Futures Brokerage Material Risk Inventory | 100% | 0%
1.2.5.5.1 | TASK:GBM - Futures Brokerage Material Risk Inventory | 100% | 100% | 0% | 100% | TASK:GBM - Futures Brokerage Material Risk Inventory | 100% | 0%
1.2.5.5.1.1 | Deliver Final Inventory to SIS and SHUSA ERM | 100% | 100% | 0% | 100% | Deliver Final Inventory to SIS and SHUSA ERM | 100% | 0%
1.2.5.5.1.2 | Present inventory to ERMC | 100% | 100% | 0% | 100% | Present inventory to ERMC | 100% | 0%
1.2.5.5.1.3 | Futures Brokerage Material Risk Inventory Prepared | 100% | 100% | 0% | 100% | Futures Brokerage Material Risk Inventory Prepared | 100% | 0%
1.2.5.6 | MILESTONE:GBM - Fixed Income and Equity Research Material Risk Inventory | 100% | 100% | 0% | 100% | MILESTONE:GBM - Fixed Income and Equity Research Material Risk Inventory | 100% | 0%
1.2.5.6.1 | TASK:GBM - Fixed Income and Equity Research Material Risk Inventory | 100% | 100% | 0% | 100% | TASK:GBM - Fixed Income and Equity Research Material Risk Inventory | 100% | 0%
1.2.5.6.1.1 | Deliver Final Inventory to SIS and SHUSA ERM | 100% | 100% | 0% | 100% | Deliver Final Inventory to SIS and SHUSA ERM | 100% | 0%
1.2.5.6.1.2 | Present inventory to ERMC | 100% | 100% | 0% | 100% | Present inventory to ERMC | 100% | 0%
1.2.5.6.1.3 | Fixed Income and Equity Research Material Risk Inventory Prepared | 100% | 100% | 0% | 100% | Fixed Income and Equity Research Material Risk Inventory Prepared | 100% | 0%
1.2.5.7 | MILESTONE:Human Resources Material Risk Inventory | 100% | 100% | 0% | 100% | MILESTONE:Human Resources Material Risk Inventory | 100% | 0%
1.2.5.7.1 | TASK:Human Resources Material Risk Inventory | 100% | 100% | 0% | 100% | TASK:Human Resources Material Risk Inventory | 100% | 0%
1.2.5.7.1.1 | Deliver Final Inventory to SIS and SHUSA ERM | 100% | 100% | 0% | 100% | Deliver Final Inventory to SIS and SHUSA ERM | 100% | 0%
1.2.5.7.1.2 | Present inventory to ERMC | 100% | 100% | 0% | 100% | Present inventory to ERMC | 100% | 0%
1.2.5.7.1.3 | Human Resources Material Risk Inventory Prepared | 100% | 100% | 0% | 100% | Human Resources Material Risk Inventory Prepared | 100% | 0%
1.2.5.8 | MILESTONE:Finance Material Risk Inventory | 100% | 100% | 0% | 100% | MILESTONE:Finance Material Risk Inventory | 100% | 0%
1.2.5.8.1 | TASK:Finance Material Risk Inventory | 100% | 100% | 0% | 100% | TASK:Finance Material Risk Inventory | 100% | 0%
1.2.5.8.1.1 | Deliver Final Inventory to SIS and SHUSA ERM | 100% | 100% | 0% | 100% | Deliver Final Inventory to SIS and SHUSA ERM | 100% | 0%
1.2.5.8.1.2 | Present inventory to ERMC | 100% | 100% | 0% | 100% | Present inventory to ERMC | 100% | 0%
1.2.5.8.1.3 | Finance Material Risk Inventory Prepared | 100% | 100% | 0% | 100% | Finance Material Risk Inventory Prepared | 100% | 0%
1.2.5.9 | MILESTONE:Technology and Operations Material Risk Inventory | 100% | 100% | 0% | 100% | MILESTONE:Technology and Operations Material Risk Inventory | 100% | 0%
1.2.5.9.1 | TASK:Technology and Operations Material Risk Inventory | 100% | 100% | 0% | 100% | TASK:Technology and Operations Material Risk Inventory | 100% | 0%
1.2.5.9.1.1 | Deliver Final Inventory to SIS and SHUSA ERM | 100% | 100% | 0% | 100% | Deliver Final Inventory to SIS and SHUSA ERM | 100% | 0%
1.2.5.9.1.2 | Present inventory to ERMC | 100% | 100% | 0% | 100% | Present inventory to ERMC | 100% | 0%
1.2.5.9.1.3 | Technology and Operations Material Risk Inventory Prepared | 100% | 100% | 0% | 100% | Technology and Operations Material Risk Inventory Prepared | 100% | 0%
1.2.5.10 | MILESTONE:Legal Material Risk Inventory | 100% | 100% | 0% | 100% | MILESTONE:Legal Material Risk Inventory | 100% | 0%
1.2.5.10.1 | TASK:Legal Material Risk Inventory | 100% | 100% | 0% | 100% | TASK:Legal Material Risk Inventory | 100% | 0%
1.2.5.10.1.1 | Deliver Final Inventory to SIS and SHUSA ERM | 100% | 100% | 0% | 100% | Deliver Final Inventory to SIS and SHUSA ERM | 100% | 0%
1.2.5.10.1.2 | Present inventory to ERMC | 100% | 100% | 0% | 100% | Present inventory to ERMC | 100% | 0%
1.2.5.10.1.3 | Legal Material Risk Inventory Prepared | 100% | 100% | 0% | 100% | Legal Material Risk Inventory Prepared | 100% | 0%
1.2.5.11 | MILESTONE: Hold NY SIS Aggregation Workshops (include 2nd LOD challenge) | 0% | 100% | 0% | 99% | MILESTONE: Hold NY SIS Aggregation Workshops (include 2nd LOD challenge) | 99% | -99%
1.2.5.11.1 | TASK: Credit Risk Aggregation |  | 100% | 0% | 99% | TASK: Credit Risk Aggregation | 99% | -99%
1.2.5.11.1.1 | ERM disseminates Workshop Pre-Read Materials to Risk Managers | 100% | 100% | 0% | 100% | ERM disseminates Workshop Pre-Read Materials to Risk Managers | 100% | 0%
1.2.5.11.1.2 | ERM facilitates Aggregation and Enrichment Activities | 100% | 100% | 0% | 100% | ERM facilitates Aggregation and Enrichment Activities | 100% | 0%
1.2.5.11.1.3 | Risk Manager presents inventory to level II subcommittee | 50% | 100% | 0% | 50% | Risk Manager presents inventory to level II subcommittee | 50% | 0%
1.2.5.11.1.4 | Credit Risk Aggregation Prepared | 50% | 100% | 0% | 50% | Credit Risk Aggregation Prepared | 50% | 0%
1.2.5.11.2 | TASK: Operational Risk Material Risk Aggregation | 0% | 100% | 0% | 99% | TASK: Operational Risk Material Risk Aggregation | 99% | -99%
1.2.5.11.2.1 | ERM disseminates Workshop Pre-Read Materials to Risk Managers | 100% | 100% | 0% | 100% | ERM disseminates Workshop Pre-Read Materials to Risk Managers | 100% | 0%
1.2.5.11.2.2 | ERM facilitates Aggregation and Enrichment Activities | 100% | 100% | 0% | 100% | ERM facilitates Aggregation and Enrichment Activities | 100% | 0%
1.2.5.11.2.3 | Risk Manager presents inventory to level II subcommittee | 50% | 0% | 0% | 50% | Risk Manager presents inventory to level II subcommittee | 50% | 0%
1.2.5.11.2.4 | Operational Risk Material Risk Aggregation Prepared | 50% |  | 0% | 50% | Operational Risk Material Risk Aggregation Prepared | 50% | 0%
1.2.5.11.3 | TASK: Compliance Material Risk Aggregation | 0% | 100% | 0% | 99% | TASK: Compliance Material Risk Aggregation | 99% | -99%
1.2.5.11.3.1 | ERM disseminates Workshop Pre-Read Materials to Risk Managers | 100% | 100% | 0% | 100% | ERM disseminates Workshop Pre-Read Materials to Risk Managers | 100% | 0%
1.2.5.11.3.2 | ERM facilitates Aggregation and Enrichment Activities | 100% | 50% | 0% | 100% | ERM facilitates Aggregation and Enrichment Activities | 100% | 0%
1.2.5.11.3.3 | Risk Manager presents inventory to level II subcommittee | 50% | 50% | 0% | 50% | Risk Manager presents inventory to level II subcommittee | 50% | 0%
1.2.5.11.3.4 | Compliance Material Risk Aggregation Prepared | 50% | 0% | 0% | 50% | Compliance Material Risk Aggregation Prepared | 50% | 0%
1.2.5.11.4 | TASK: Model Material Risk Aggregation | 0% | 100% | 0% | 99% | TASK: Model Material Risk Aggregation | 99% | -99%
1.2.5.11.4.1 | ERM disseminates Workshop Pre-Read Materials to Risk Managers | 100% | 100% | 0% | 100% | ERM disseminates Workshop Pre-Read Materials to Risk Managers | 100% | 0%
1.2.5.11.4.2 | ERM facilitates Aggregation and Enrichment Workshop | 100% | 50% | 0% | 100% | ERM facilitates Aggregation and Enrichment Workshop | 100% | 0%
1.2.5.11.4.3 | Risk Manager presents inventory to level II subcommittee | 50% | 50% | 0% | 50% | Risk Manager presents inventory to level II subcommittee | 50% | 0%
1.2.5.11.4.4 | Model Material Risk Aggregation Prepared | 50% | 0% | 0% | 50% | Model Material Risk Aggregation Prepared | 50% | 0%
1.2.5.11.5 | TASK: Liquidity/Market Material Risk Aggregation | 0% | 100% | 0% | 99% | TASK: Liquidity/Market Material Risk Aggregation | 99% | -99%
1.2.5.11.5.1 | ERM disseminates Workshop Pre-Read Materials to Risk Managers | 100% | 100% | 0% | 100% | ERM disseminates Workshop Pre-Read Materials to Risk Managers | 100% | 0%
1.2.5.11.5.2 | ERM facilitates Aggregation and Enrichment Activities | 100% | 50% | 0% | 100% | ERM facilitates Aggregation and Enrichment Activities | 100% | 0%
1.2.5.11.5.3 | Risk Manager presents inventory to level II subcommittee | 50% | 50% | 0% | 50% | Risk Manager presents inventory to level II subcommittee | 50% | 0%
1.2.5.11.5.4 | Liquidity/Market Material Risk Aggregation Prepared | 50% | 0% | 0% | 50% | Liquidity/Market Material Risk Aggregation Prepared | 50% | 0%
1.2.5.11.6 | TASK: Reputational/Strategic Material Risk Aggregation | 0% | 100% | 0% | 99% | TASK: Reputational/Strategic Material Risk Aggregation | 99% | -99%
1.2.5.11.6.1 | ERM disseminates Workshop Pre-Read Materials to Risk Managers | 100% | 100% | 0% | 100% | ERM disseminates Workshop Pre-Read Materials to Risk Managers | 100% | 0%
1.2.5.11.6.2 | ERM facilitates Aggregation and Enrichment Activities | 100% | 50% | 0% | 100% | ERM facilitates Aggregation and Enrichment Activities | 100% | 0%
1.2.5.11.6.3 | Risk Manager presents inventory to level II subcommittee | 50% | 50% | 0% | 50% | Risk Manager presents inventory to level II subcommittee | 50% | 0%
1.2.5.11.6.4 | Reputational/Strategic Material Risk Aggregation Prepared | 50% | 0% | 0% | 50% | Reputational/Strategic Material Risk Aggregation Prepared | 50% | 0%
1.2.5.12 | MILESTONE:Present Results to NY SIS ERMC | 0% | 100% | 0% | 0% | MILESTONE:Present Results to NY SIS ERMC | 0% | 0%
1.2.5.13 | MILESTONE:Present Results to NY SIS BERC | 0% | 100% | 0% | 0% | MILESTONE:Present Results to NY SIS BERC | 0% | 0%
1.2.5.14 | Present NY SIS Material Risks to CCAR | 0% | 50% | 0% | 0% | Present NY SIS Material Risks to CCAR | 0% | 0%
1.2.5.15 | Deliver NY SIS Material Risks to CCAR and Capital Plan | 0% | 50% | 0% | 0% | Deliver NY SIS Material Risks to CCAR and Capital Plan | 0% | 0%
1.2.6 | DELIVERABLE: Design and execute the Material Risk Program across Puerto Rico | 89% | 0% | 0% | 71% | DELIVERABLE: Design and execute the Material Risk Program across Puerto Rico | 71% | 18%
1.2.6.1 | MILESTONE:Retail Banking Material Risk Inventory | 95% | 100% | 0% | 100% | MILESTONE:Retail Banking Material Risk Inventory | 100% | -5%
1.2.6.1.1 | TASK: Personal Loans Banking Material Risk Inventory | 100% | 100% | 0% | 100% | TASK: Personal Loans Banking Material Risk Inventory | 100% | 0%
1.2.6.1.1.1 | Deliver Final Inventory to PR and SHUSA ERM | 100% | 50% | 0% | 100% | Deliver Final Inventory to PR and SHUSA ERM | 100% | 0%
1.2.6.1.1.2 | Personal Loans Banking Material Risk Inventory Prepared | 100% | 50% | 0% | 100% | Personal Loans Banking Material Risk Inventory Prepared | 100% | 0%
1.2.6.1.2 | TASK: Small Business Banking Material Risk Inventory | 100% | 0% | 0% | 100% | TASK: Small Business Banking Material Risk Inventory | 100% | 0%
1.2.6.1.2.1 | Deliver Final Inventory to PR and SHUSA ERM | 100% | 0% | 0% | 100% | Deliver Final Inventory to PR and SHUSA ERM | 100% | 0%
1.2.6.1.2.2 | Small Business Banking Material Risk Inventory Prepared | 100% | 0% | 0% | 100% | Small Business Banking Material Risk Inventory Prepared | 100% | 0%
1.2.6.1.3 | TASK: Santander Insurance Agency Material Risk Inventory | 100% | 0% | 0% | 100% | TASK: Santander Insurance Agency Material Risk Inventory | 100% | 0%
1.2.6.1.3.1 | Deliver Final Inventory to PR and SHUSA ERM | 100% | 89% | 0% | 100% | Deliver Final Inventory to PR and SHUSA ERM | 100% | 0%
1.2.6.1.3.2 | Santander Insurance Agency Material Risk Inventory Prepared | 100% | 95% | 0% | 100% | Santander Insurance Agency Material Risk Inventory Prepared | 100% | 0%
1.2.6.1.4 | TASK: Credit Cards Material Risk Inventory | 100% | 100% | 0% | 100% | TASK: Credit Cards Material Risk Inventory | 100% | 0%
1.2.6.1.4.1 | Deliver Final Inventory to PR and SHUSA ERM | 100% | 100% | 0% | 100% | Deliver Final Inventory to PR and SHUSA ERM | 100% | 0%
1.2.6.1.4.2 | Credit Cards Material Risk Inventory Prepared | 100% | 100% | 0% | 100% | Credit Cards Material Risk Inventory Prepared | 100% | 0%
1.2.6.1.5 | TASK: Mortgages Material Risk Inventory | 100% | 100% | 0% | 100% | TASK: Mortgages Material Risk Inventory | 100% | 0%
1.2.6.1.5.1 | Deliver Final Inventory to PR and SHUSA ERM | 100% | 100% | 0% | 100% | Deliver Final Inventory to PR and SHUSA ERM | 100% | 0%
1.2.6.1.5.2 | Mortgages Material Risk Inventory Prepared | 100% | 100% | 0% | 100% | Mortgages Material Risk Inventory Prepared | 100% | 0%
1.2.6.2 | MILESTONE:Global Banking/Commercial Banking and CRE/Speciality and Gov't Banking Material Risk Inventory | 100% | 100% | 0% | 100% | MILESTONE:Global Banking/Commercial Banking and CRE/Speciality and Gov't Banking Material Risk Inventory | 100% | 0%
1.2.6.2.1 | TASK: GBM Material Risk Inventory | 100% | 100% | 0% | 100% | TASK: GBM Material Risk Inventory | 100% | 0%
1.2.6.2.1.1 | Deliver Final Inventory to PR and SHUSA ERM | 100% | 100% | 0% | 100% | Deliver Final Inventory to PR and SHUSA ERM | 100% | 0%
1.2.6.2.1.2 | GBM Material Risk Inventory Prepared | 100% | 100% | 0% | 100% | GBM Material Risk Inventory Prepared | 100% | 0%
1.2.6.2.2 | TASK: Enterprise Material Risk Inventory | 100% | 100% | 0% | 100% | TASK: Enterprise Material Risk Inventory | 100% | 0%
1.2.6.2.2.1 | Deliver Final Inventory to PR and SHUSA ERM | 100% | 100% | 0% | 100% | Deliver Final Inventory to PR and SHUSA ERM | 100% | 0%
1.2.6.2.2.2 | Enterprise Material Risk Inventory Prepared | 100% | 100% | 0% | 100% | Enterprise Material Risk Inventory Prepared | 100% | 0%
1.2.6.2.3 | TASK: Institutional/Public Sector Material Risk Inventory | 100% | 100% | 0% | 100% | TASK: Institutional/Public Sector Material Risk Inventory | 100% | 0%
1.2.6.2.3.1 | Deliver Final Inventory to PR and SHUSA ERM | 100% | 100% | 0% | 100% | Deliver Final Inventory to PR and SHUSA ERM | 100% | 0%
1.2.6.2.3.2 | Institutional/Public Sector Material Risk Inventory Prepared | 100% | 100% | 0% | 100% | Institutional/Public Sector Material Risk Inventory Prepared | 100% | 0%
1.2.6.3 | MILESTONE:Global Banking/Commercial Banking/CRE & Speciality: Create Global Banking Material Risk Inventory | 100% | 100% | 0% | 100% | MILESTONE:Global Banking/Commercial Banking/CRE & Speciality: Create Global Banking Material Risk Inventory | 100% | 0%
1.2.6.3.1 | TASK:Global Banking/Commercial Banking/CRE & Speciality: Create Global Banking Material Risk Inventory | 100% | 100% | 0% | 100% | TASK:Global Banking/Commercial Banking/CRE & Speciality: Create Global Banking Material Risk Inventory | 100% | 0%
1.2.6.3.1.1 | Create Segment Material Risk Inventory (Aggregation) | 100% | 100% | 0% | 100% | Create Segment Material Risk Inventory (Aggregation) | 100% | 0%
1.2.6.3.1.2 | Segment head presents inventory to ERMC | 100% | 100% | 0% | 100% | Segment head presents inventory to ERMC | 100% | 0%
1.2.6.3.1.3 | Global Banking Material Risk Inventory Prepared | 100% | 100% | 0% | 100% | Global Banking Material Risk Inventory Prepared | 100% | 0%
1.2.6.4 | MILESTONE:Mortgage Servicing Material Risk Inventory | 100% | 100% | 0% | 100% | MILESTONE:Mortgage Servicing Material Risk Inventory | 100% | 0%
1.2.6.4.1 | TASK:Mortgage Servicing Material Risk Inventory | 100% | 100% | 0% | 100% | TASK:Mortgage Servicing Material Risk Inventory | 100% | 0%
1.2.6.4.1.1 | Deliver Final Inventory to PR and SHUSA ERM | 100% | 100% | 0% | 100% | Deliver Final Inventory to PR and SHUSA ERM | 100% | 0%
1.2.6.4.1.2 | Present inventory to ERMC | 100% | 100% | 0% | 100% | Present inventory to ERMC | 100% | 0%
1.2.6.4.1.3 | Mortgage Servicing Material Risk Inventory Prepared | 100% | 100% | 0% | 100% | Mortgage Servicing Material Risk Inventory Prepared | 100% | 0%
1.2.6.5 | MILESTONE:Investment Services Material Risk Inventory | 100% | 100% | 0% | 95% | MILESTONE:Investment Services Material Risk Inventory | 100% | 0%
1.2.6.5.1 | TASK:Investment Services Material Risk Inventory | 100% | 100% | 0% | 95% | TASK:Investment Services Material Risk Inventory | 100% | 0%
1.2.6.5.1.1 | Deliver Final Inventory to PR and SHUSA ERM | 100% | 100% | 0% | 95% | Deliver Final Inventory to PR and SHUSA ERM | 100% | 0%
1.2.6.5.1.2 | Present inventory to ERMC | 100% | 100% | 0% | 95% | Present inventory to ERMC | 100% | 0%
1.2.6.5.1.3 | Investment Services Material Risk Inventory Prepared | 100% | 100% | 0% | 95% | Investment Services Material Risk Inventory Prepared | 100% | 0%
1.2.6.6 | MILESTONE:Trust Material Risk Inventory | 100% | 100% | 0% | 100% | MILESTONE:Trust Material Risk Inventory | 100% | 0%
1.2.6.6.1 | TASK:Trust Material Risk Inventory | 100% | 100% | 0% | 100% | TASK:Trust Material Risk Inventory | 100% | 0%
1.2.6.6.1.1 | Deliver Final Inventory to PR and SHUSA ERM | 100% | 100% | 0% | 100% | Deliver Final Inventory to PR and SHUSA ERM | 100% | 0%
1.2.6.6.1.2 | Present inventory to ERMC | 100% | 100% | 0% | 100% | Present inventory to ERMC | 100% | 0%
1.2.6.6.1.3 | Trust Material Risk Inventory Prepared | 100% | 95% | 5% | 100% | Trust Material Risk Inventory Prepared | 100% | 0%
1.2.6.7 | MILESTONE:Pension Plan Material Risk Inventory | 100% | 95% | 5% | 100% | MILESTONE:Pension Plan Material Risk Inventory | 100% | 0%
1.2.6.7.1 | TASK:Pension Plan Material Risk Inventory | 100% | 95% | 5% | 100% | TASK:Pension Plan Material Risk Inventory | 100% | 0%
1.2.6.7.1.1 | Deliver Final Inventory to PR and SHUSA ERM | 100% | 95% | 5% | 100% | Deliver Final Inventory to PR and SHUSA ERM | 100% | 0%
1.2.6.7.1.2 | Present inventory to ERMC | 100% | 95% | 5% | 100% | Present inventory to ERMC | 100% | 0%
1.2.6.7.1.3 | Pension Plan Material Risk Inventory Prepared | 100% | 100% | 0% | 100% | Pension Plan Material Risk Inventory Prepared | 100% | 0%
1.2.6.8 | MILESTONE:Foreign Accounts Material Risk Inventory | 100% | 100% | 0% | 100% | MILESTONE:Foreign Accounts Material Risk Inventory | 100% | 0%
1.2.6.8.1 | TASK:Foreign Accounts Material Risk Inventory | 100% | 100% | 0% | 100% | TASK:Foreign Accounts Material Risk Inventory | 100% | 0%
1.2.6.8.1.1 | Deliver Final Inventory to PR and SHUSA ERM | 100% | 100% | 0% | 100% | Deliver Final Inventory to PR and SHUSA ERM | 100% | 0%
1.2.6.8.1.2 | Present inventory to ERMC | 100% | 100% | 0% | 100% | Present inventory to ERMC | 100% | 0%
1.2.6.8.1.3 | Foreign Accounts Material Risk Inventory Prepared | 100% | 95% | 5% | 100% | Foreign Accounts Material Risk Inventory Prepared | 100% | 0%
1.2.6.9 | MILESTONE:Human Resources Material Risk Inventory | N/A | 95% | 5% | 0% | MILESTONE:Human Resources Material Risk Inventory | 0% | #VALUE!
1.2.6.9.1 | TASK:Human Resources Material Risk Inventory | N/A | 95% | 5% | 0% | TASK:Human Resources Material Risk Inventory | 0% | #VALUE!
1.2.6.9.1.1 | Create risk Inventory | N/A | 95% | 5% | 0% | Create risk Inventory | 0% | #VALUE!
1.2.6.9.1.2 | Deliver Final Inventory to PR and SHUSA ERM | N/A | 95% | 5% | 0% | Deliver Final Inventory to PR and SHUSA ERM | 0% | #VALUE!
1.2.6.9.1.3 | Present inventory to ERMC | N/A | 95% | 5% | 0% | Present inventory to ERMC | 0% | #VALUE!
1.2.6.9.1.4 | Human Resources Material Risk Inventory Prepared | N/A | 95% | 5% | 0% | Human Resources Material Risk Inventory Prepared | 0% | #VALUE!
1.2.6.10 | MILESTONE:Technology and Operations Material Risk Inventory | N/A | 95% | 5% | 0% | MILESTONE:Technology and Operations Material Risk Inventory | 0% | #VALUE!
1.2.6.10.1 | TASK:Technology and Operations Material Risk Inventory | N/A | 95% | 5% | 0% | TASK:Technology and Operations Material Risk Inventory | 0% | #VALUE!
1.2.6.10.1.1 | Deliver Final Inventory to PR and SHUSA ERM | N/A | 95% | 5% | 0% | Deliver Final Inventory to PR and SHUSA ERM | 0% | #VALUE!
1.2.6.10.1.2 | Present inventory to ERMC | N/A | N/A | #VALUE! | 0% | Present inventory to ERMC | 0% | #VALUE!
1.2.6.10.1.3 | Technology and Operations Material Risk Inventory Prepared | N/A | N/A | #VALUE! | 0% | Technology and Operations Material Risk Inventory Prepared | 0% | #VALUE!
1.2.6.11 | MILESTONE:Legal Material Risk Inventory | N/A | N/A | #VALUE! | 0% | MILESTONE:Legal Material Risk Inventory | 0% | #VALUE!
1.2.6.11.1 | TASK:Legal Material Risk Inventory | N/A | N/A | #VALUE! | 0% | TASK:Legal Material Risk Inventory | 0% | #VALUE!
1.2.6.11.1.1 | Deliver Final Inventory to PR and SHUSA ERM | N/A | N/A | #VALUE! | 0% | Deliver Final Inventory to PR and SHUSA ERM | 0% | #VALUE!
1.2.6.11.1.2 | Present inventory to ERMC | N/A | N/A | #VALUE! | 0% | Present inventory to ERMC | 0% | #VALUE!
1.2.6.11.1.3 | Legal Material Risk Inventory Prepared | N/A | N/A | #VALUE! | 0% | Legal Material Risk Inventory Prepared | 0% | #VALUE!
1.2.6.12 | MILESTONE:Finance Material Risk Inventory | 100% | N/A | #VALUE! | 100% | MILESTONE:Finance Material Risk Inventory | 100% | 0%
1.2.6.12.1 | TASK:Finance Material Risk Inventory | 100% | N/A | #VALUE! | 100% | TASK:Finance Material Risk Inventory | 100% | 0%
1.2.6.12.1.1 | Deliver Final Inventory to PR and SHUSA ERM | 100% | N/A | #VALUE! | 100% | Deliver Final Inventory to PR and SHUSA ERM | 100% | 0%
1.2.6.12.1.2 | Present inventory to ERMC | 100% | N/A | #VALUE! | 100% | Present inventory to ERMC | 100% | 0%
1.2.6.12.1.3 | Finance Material Risk Inventory Prepared | 100% | N/A | #VALUE! | 100% | Finance Material Risk Inventory Prepared | 100% | 0%
1.2.6.13 | MILESTONE:SFS - Island Finance Material Risk Inventory | 100% | N/A | #VALUE! | 100% | MILESTONE:SFS - Island Finance Material Risk Inventory | 100% | 0%
1.2.6.13.1 | TASK:SFS - Island Finance Material Risk Inventory | 100% | N/A | #VALUE! | 100% | TASK:SFS - Island Finance Material Risk Inventory | 100% | 0%
1.2.6.13.1.1 | Deliver Final Inventory to PR and SHUSA ERM | 100% | N/A | #VALUE! | 100% | Deliver Final Inventory to PR and SHUSA ERM | 100% | 0%
1.2.6.13.1.2 | Present inventory to ERMC | 100% | N/A | #VALUE! | 100% | Present inventory to ERMC | 100% | 0%
1.2.6.13.1.3 | SFS - Island Finance Material Risk Inventory Prepared | 100% | 100% | 0% | 100% | SFS - Island Finance Material Risk Inventory Prepared | 100% | 0%
1.2.6.14 | MILESTONE:SFS - Special Assets Material Risk Inventory | 100% | 100% | 0% | 100% | MILESTONE:SFS - Special Assets Material Risk Inventory | 100% | 0%
1.2.6.14.1 | TASK:SFS - Special Assets Material Risk Inventory | 100% | 100% | 0% | 100% | TASK:SFS - Special Assets Material Risk Inventory | 100% | 0%
1.2.6.14.1.1 | Deliver Final Inventory to PR and SHUSA ERM | 100% | 100% | 0% | 100% | Deliver Final Inventory to PR and SHUSA ERM | 100% | 0%
1.2.6.14.1.2 | Present inventory to ERMC | 100% | 100% | 0% | 100% | Present inventory to ERMC | 100% | 0%
1.2.6.14.1.3 | SFS - Special Assets Material Risk Inventory Prepared | 100% | 100% | 0% | 100% | SFS - Special Assets Material Risk Inventory Prepared | 100% | 0%
1.2.6.15 | MILESTONE:Santander Overseas Bank - GBM Material Risk Inventory | 100% | 100% | 0% | 100% | MILESTONE:Santander Overseas Bank - GBM Material Risk Inventory | 100% | 0%
1.2.6.15.1 | TASK:Santander Overseas Bank - GBM Material Risk Inventory | 100% | 100% | 0% | 100% | TASK:Santander Overseas Bank - GBM Material Risk Inventory | 100% | 0%
1.2.6.15.1.1 | Deliver Final Inventory to PR and SHUSA ERM | 100% | 100% | 0% | 100% | Deliver Final Inventory to PR and SHUSA ERM | 100% | 0%
1.2.6.15.1.2 | Present inventory to ERMC | 100% | 100% | 0% | 100% | Present inventory to ERMC | 100% | 0%
1.2.6.15.1.3 | Santander Overseas Bank - GBM Material Risk Inventory Prepared | 100% | 100% | 0% | 100% | Santander Overseas Bank - GBM Material Risk Inventory Prepared | 100% | 0%
1.2.6.16 | MILESTONE: Hold Puerto Rico Aggregation Workshops (include 2nd LOD challenge) | 98% | 100% | 0% | 49% | MILESTONE: Hold Puerto Rico Aggregation Workshops (include 2nd LOD challenge) | 49% | 49%
1.2.6.16.1 | TASK: Credit Risk Aggregation | 98% | 100% | 0% | 49% | TASK: Credit Risk Aggregation | 49% | 49%
1.2.6.16.1.1 | ERM disseminates Workshop Pre-Read Materials to Risk Managers | 50% | 100% | 0% | 50% | ERM disseminates Workshop Pre-Read Materials to Risk Managers | 50% | 0%
1.2.6.16.1.2 | ERM facilitates Aggregation and Enrichment Activities | 50% | 100% | 0% | 50% | ERM facilitates Aggregation and Enrichment Activities | 50% | 0%
1.2.6.16.1.3 | Risk Manager presents inventory to level II subcommittee | 0% | 100% | 0% | 0% | Risk Manager presents inventory to level II subcommittee | 0% | 0%
1.2.6.16.1.4 | Credit Risk Aggregation Prepared | 0% | 100% | 0% | 0% | Credit Risk Aggregation Prepared | 0% | 0%
1.2.6.16.2 | TASK: Operational Risk Material Risk Aggregation | 98% | 100% | 0% | 49% | TASK: Operational Risk Material Risk Aggregation | 49% | 49%
1.2.6.16.2.1 | ERM disseminates Workshop Pre-Read Materials to Risk Managers | 50% | 100% | 0% | 50% | ERM disseminates Workshop Pre-Read Materials to Risk Managers | 50% | 0%
1.2.6.16.2.2 | ERM facilitates Aggregation and Enrichment Activities | 50% | 100% | 0% | 50% | ERM facilitates Aggregation and Enrichment Activities | 50% | 0%
1.2.6.16.2.3 | Risk Manager presents inventory to level II subcommittee | 0% | 98% | 0% | 0% | Risk Manager presents inventory to level II subcommittee | 0% | 0%
1.2.6.16.2.4 | Operational Risk Material Risk Aggregation Prepared | 0% | 98% | 0% | 0% | Operational Risk Material Risk Aggregation Prepared | 0% | 0%
1.2.6.16.3 | TASK: Compliance Material Risk Aggregation | 98% | 50% | 0% | 49% | TASK: Compliance Material Risk Aggregation | 49% | 49%
1.2.6.16.3.1 | ERM disseminates Workshop Pre-Read Materials to Risk Managers | 50% | 50% | 0% | 50% | ERM disseminates Workshop Pre-Read Materials to Risk Managers | 50% | 0%
1.2.6.16.3.2 | ERM facilitates Aggregation and Enrichment Workshop | 50% | 0% | 0% | 50% | ERM facilitates Aggregation and Enrichment Workshop | 50% | 0%
1.2.6.16.3.3 | Risk Manager presents inventory to level II subcommittee | 0% | 0% | 0% | 0% | Risk Manager presents inventory to level II subcommittee | 0% | 0%
1.2.6.16.3.4 | Compliance Material Risk Aggregation Prepared | 0% | 98% | 0% | 0% | Compliance Material Risk Aggregation Prepared | 0% | 0%
1.2.6.16.4 | TASK: Model Material Risk Aggregation | 98% | 50% | 0% | 49% | TASK: Model Material Risk Aggregation | 49% | 49%
1.2.6.16.4.1 | ERM disseminates Workshop Pre-Read Materials to Risk Managers | 50% | 50% | 0% | 50% | ERM disseminates Workshop Pre-Read Materials to Risk Managers | 50% | 0%
1.2.6.16.4.2 | ERM facilitates Aggregation and Enrichment Activities | 50% | 0% | 0% | 50% | ERM facilitates Aggregation and Enrichment Activities | 50% | 0%
1.2.6.16.4.3 | Risk Manager presents inventory to level II subcommittee | 0% | 0% | 0% | 0% | Risk Manager presents inventory to level II subcommittee | 0% | 0%
1.2.6.16.4.4 | Model Material Risk Aggregation Prepared | 0% | 98% | 0% | 0% | Model Material Risk Aggregation Prepared | 0% | 0%
1.2.6.16.5 | TASK: Liquidity/Market Material Risk Aggregation | 98% | 50% | 0% | 49% | TASK: Liquidity/Market Material Risk Aggregation | 49% | 49%
1.2.6.16.5.1 | ERM disseminates Workshop Pre-Read Materials to Risk Managers | 50% | 50% | 0% | 50% | ERM disseminates Workshop Pre-Read Materials to Risk Managers | 50% | 0%
1.2.6.16.5.2 | ERM facilitates Aggregation and Enrichment Activities | 50% | 0% | 0% | 50% | ERM facilitates Aggregation and Enrichment Activities | 50% | 0%
1.2.6.16.5.3 | Risk Manager presents inventory to level II subcommittee | 0% | 0% | 0% | 0% | Risk Manager presents inventory to level II subcommittee | 0% | 0%
1.2.6.16.5.4 | Liquidity/Market Material Risk Aggregation Prepared | 0% | 98% | 0% | 0% | Liquidity/Market Material Risk Aggregation Prepared | 0% | 0%
1.2.6.16.6 | TASK: Reputational/Strategic Material Risk Aggregation | 98% | 50% | 0% | 49% | TASK: Reputational/Strategic Material Risk Aggregation | 49% | 49%
1.2.6.16.6.1 | ERM disseminates Workshop Pre-Read Materials to Risk Managers | 50% | 50% | 0% | 50% | ERM disseminates Workshop Pre-Read Materials to Risk Managers | 50% | 0%
1.2.6.16.6.2 | ERM facilitates Aggregation and Enrichment Workshop | 50% | 0% | 0% | 50% | ERM facilitates Aggregation and Enrichment Workshop | 50% | 0%
1.2.6.16.6.3 | Risk Manager presents inventory to level II subcommittee | 0% | 0% | 0% | 0% | Risk Manager presents inventory to level II subcommittee | 0% | 0%
1.2.6.16.6.4 | Reputational/Strategic Material Risk Aggregation Prepared | 0% | 98% | 0% | 0% | Reputational/Strategic Material Risk Aggregation Prepared | 0% | 0%
1.2.6.17 | MILESTONE:Present Results to PR Santander Bancorp ERMC | 50% | 50% | 0% | 50% | MILESTONE:Present Results to PR Santander Bancorp ERMC | 50% | 0%
1.2.6.18 | MILESTONE:Present Results to PR Santander Bancorp BERC | 50% | 50% | 0% | 50% | MILESTONE:Present Results to PR Santander Bancorp BERC | 50% | 0%
1.2.6.19 | Present Puerto Rico Material Risks to CCAR | 0% | 0% | 0% | 0% | Present Puerto Rico Material Risks to CCAR | 0% | 0%
1.2.6.20 | Deliver Puerto Rico Material Risks to CCAR and Capital Plan | 0% | 0% | 0% | 0% | Deliver Puerto Rico Material Risks to CCAR and Capital Plan | 0% | 0%
1.2.7 | DELIVERABLE: Design and execute the Material Risk Program across Miami | 2% | 98% | 0% | 75% | DELIVERABLE: Design and execute the Material Risk Program across Miami | 75% | -73%
1.2.7.1 | MILESTONE:Private Banking Material Risk Inventory | 100% | 50% | 0% | 100% | MILESTONE:Private Banking Material Risk Inventory | 100% | 0%
1.2.7.1.1 | TASK:Private Banking Material Risk Inventory | 100% | 50% | 0% | 100% | TASK:Private Banking Material Risk Inventory | 100% | 0%
1.2.7.1.1.1 | Deliver Final Inventory to Miami and SHUSA ERM | 100% | 0% | 0% | 100% | Deliver Final Inventory to Miami and SHUSA ERM | 100% | 0%
1.2.7.1.1.2 | Present inventory to ERMC | 100% | 0% | 0% | 100% | Present inventory to ERMC | 100% | 0%
1.2.7.1.1.3 | Private Banking Material Risk Inventory Prepared | 100% | 50% | 0% | 100% | Private Banking Material Risk Inventory Prepared | 100% | 0%
1.2.7.2 | MILESTONE:Personal Lending Material Risk Inventory | 100% | 50% | 0% | 100% | MILESTONE:Personal Lending Material Risk Inventory | 100% | 0%
1.2.7.2.1 | TASK:Personal Lending Material Risk Inventory | 100% | 0% | 0% | 100% | TASK:Personal Lending Material Risk Inventory | 100% | 0%
1.2.7.2.1.1 | Deliver Final Inventory to Miami and SHUSA ERM | 100% | 0% | 0% | 100% | Deliver Final Inventory to Miami and SHUSA ERM | 100% | 0%
1.2.7.2.1.2 | Present inventory to ERMC | 100% | 2% | 0% | 100% | Present inventory to ERMC | 100% | 0%
1.2.7.2.1.3 | Personal Lending Material Risk Inventory Prepared | 100% | 100% | 0% | 100% | Personal Lending Material Risk Inventory Prepared | 100% | 0%
1.2.7.3 | MILESTONE: Hold Miami Aggregation Workshops (include 2 LOD challenge) | 0% | 100% | 0% | 99% | MILESTONE: Hold Miami Aggregation Workshops (include 2 LOD challenge) | 99% | -99%
1.2.7.3.1 | TASK: Credit Risk Aggregation | 0% | 100% | 0% | 99% | TASK: Credit Risk Aggregation | 99% | -99%
1.2.7.3.1.1 | ERM disseminates Workshop Pre-Read Materials to Risk Managers | 100% | 100% | 0% | 100% | ERM disseminates Workshop Pre-Read Materials to Risk Managers | 100% | 0%
1.2.7.3.1.2 | ERM facilitates Aggregation and Enrichment Activities | 100% | 100% | 0% | 100% | ERM facilitates Aggregation and Enrichment Activities | 100% | 0%
1.2.7.3.1.3 | Risk Manager presents inventory to level II subcommittee | 50% | 100% | 0% | 50% | Risk Manager presents inventory to level II subcommittee | 50% | 0%
1.2.7.3.1.4 | Credit Risk Aggregation Prepared | 50% | 100% | 0% | 50% | Credit Risk Aggregation Prepared | 50% | 0%
1.2.7.3.2 | TASK: Operational Risk Material Risk Aggregation | 0% | 100% | 0% | 99% | TASK: Operational Risk Material Risk Aggregation | 99% | -99%
1.2.7.3.2.1 | ERM disseminates Workshop Pre-Read Materials to Risk Managers | 100% | 100% | 0% | 100% | ERM disseminates Workshop Pre-Read Materials to Risk Managers | 100% | 0%
1.2.7.3.2.2 | ERM facilitates Aggregation and Enrichment Activities | 100% | 100% | 0% | 100% | ERM facilitates Aggregation and Enrichment Activities | 100% | 0%
1.2.7.3.2.3 | Risk Manager presents inventory to level II subcommittee | 50% | 0% | 0% | 50% | Risk Manager presents inventory to level II subcommittee | 50% | 0%
1.2.7.3.2.4 | Operational Risk Material Risk Aggregation Prepared | 50% | 0% | 0% | 50% | Operational Risk Material Risk Aggregation Prepared | 50% | 0%
1.2.7.3.3 | TASK: Compliance Material Risk Aggregation | 0% | 100% | 0% | 99% | TASK: Compliance Material Risk Aggregation | 99% | -99%
1.2.7.3.3.1 | ERM disseminates Workshop Pre-Read Materials to Risk Managers | 100% | 100% | 0% | 100% | ERM disseminates Workshop Pre-Read Materials to Risk Managers | 100% | 0%
1.2.7.3.3.2 | ERM facilitates Aggregation and Enrichment Activities | 100% | 50% | 0% | 100% | ERM facilitates Aggregation and Enrichment Activities | 100% | 0%
1.2.7.3.3.3 | Risk Manager presents inventory to level II subcommittee | 50% | 50% | 0% | 50% | Risk Manager presents inventory to level II subcommittee | 50% | 0%
1.2.7.3.3.4 | Compliance Material Risk Aggregation Prepared | 50% | 0% | 0% | 50% | Compliance Material Risk Aggregation Prepared | 50% | 0%
1.2.7.3.4 | TASK: Model Material Risk Aggregation | 0% | 100% | 0% | 99% | TASK: Model Material Risk Aggregation | 99% | -99%
1.2.7.3.4.1 | ERM disseminates Workshop Pre-Read Materials to Risk Managers | 100% | 100% | 0% | 100% | ERM disseminates Workshop Pre-Read Materials to Risk Managers | 100% | 0%
1.2.7.3.4.2 | ERM facilitates Aggregation and Enrichment Workshop | 100% | 50% | 0% | 100% | ERM facilitates Aggregation and Enrichment Workshop | 100% | 0%
1.2.7.3.4.3 | Risk Manager presents inventory to level II subcommittee | 50% | 50% | 0% | 50% | Risk Manager presents inventory to level II subcommittee | 50% | 0%
1.2.7.3.4.4 | Model Material Risk Aggregation Prepared | 50% | 0% | 0% | 50% | Model Material Risk Aggregation Prepared | 50% | 0%
1.2.7.3.5 | TASK: Liquidity/Market Material Risk Aggregation | 0% | 100% | 0% | 99% | TASK: Liquidity/Market Material Risk Aggregation | 99% | -99%
1.2.7.3.5.1 | ERM disseminates Workshop Pre-Read Materials to Risk Managers | 100% | 100% | 0% | 100% | ERM disseminates Workshop Pre-Read Materials to Risk Managers | 100% | 0%
1.2.7.3.5.2 | ERM facilitates Aggregation and Enrichment Activities | 100% | 50% | 0% | 100% | ERM facilitates Aggregation and Enrichment Activities | 100% | 0%
1.2.7.3.5.3 | Risk Manager presents inventory to level II subcommittee | 50% | 50% | 0% | 50% | Risk Manager presents inventory to level II subcommittee | 50% | 0%
1.2.7.3.5.4 | Liquidity/Market Material Risk Aggregation Prepared | 50% | 0% | 0% | 50% | Liquidity/Market Material Risk Aggregation Prepared | 50% | 0%
1.2.7.3.6 | TASK: Reputational/Strategic Material Risk Aggregation | 0% | 100% | 0% | 99% | TASK: Reputational/Strategic Material Risk Aggregation | 99% | -99%
1.2.7.3.6.1 | ERM disseminates Workshop Pre-Read Materials to Risk Managers | 100% | 100% | 0% | 100% | ERM disseminates Workshop Pre-Read Materials to Risk Managers | 100% | 0%
1.2.7.3.6.2 | ERM facilitates Aggregation and Enrichment Workshop | 100% | 50% | 0% | 100% | ERM facilitates Aggregation and Enrichment Workshop | 100% | 0%
1.2.7.3.6.3 | Risk Manager presents inventory to level II subcommittee | 50% | 50% | 0% | 50% | Risk Manager presents inventory to level II subcommittee | 50% | 0%
1.2.7.3.6.4 | Reputational/Strategic Material Risk Aggregation Prepared | 50% | 0% | 0% | 50% | Reputational/Strategic Material Risk Aggregation Prepared | 50% | 0%
1.2.7.4 | MILESTONE:Present Miami to SCUSA ERMC | 0% | 100% | 0% | 0% | MILESTONE:Present Miami to SCUSA ERMC | 0% | 0%
1.2.7.5 | MILESTONE:Present Miami to SCUSA BERC | 0% | 100% | 0% | 0% | MILESTONE:Present Miami to SCUSA BERC | 0% | 0%
1.2.7.6 | Present Miami Material Risks to CCAR | 0% | 50% | 0% | 0% | Present Miami Material Risks to CCAR | 0% | 0%
1.2.7.7 | Deliver Miami Material Risks to CCAR and Capital Plan | 0% | 50% | 0% | 0% | Deliver Miami Material Risks to CCAR and Capital Plan | 0% | 0%
1.3 | Review foundational Risk ID processes including data and technology supporting the Material Risk Program and build multi-year enhancement objectives | 0% | 0% | 0% | 0% | Review foundational Risk ID processes including data and technology supporting the Material Risk Program and build multi-year enhancement objectives | 0% | 0%
1.3.1 | DELIVERABLE: Assess foundational Risk ID processes and ensure complete Foundational Risk Inventory is in place | 0% | 100% | 0% | 0% | DELIVERABLE: Assess foundational Risk ID processes and ensure complete Foundational Risk Inventory is in place | 0% | 0%
1.3.1.1 | MILESTONE: Assess Foundational Risk Processes and ensure complete foundational risk inventory is in place | 0% | 100% | 0% | 0% | MILESTONE: Assess Foundational Risk Processes and ensure complete foundational risk inventory is in place | 0% | 0%
1.3.1.1.1 | Identify existing Foundational Risk Processes | 0% | 50% | 0% | 0% | Identify existing Foundational Risk Processes | 0% | 0%
1.3.1.1.2 | Confirm and validated foundational risk inventory - develop or enhance as needed | 0% | 50% | 0% | 0% | Confirm and validated foundational risk inventory - develop or enhance as needed | 0% | 0%
1.3.1.1.3 | MILESTONE: Landscape of Foundational Risk Processes and risk inventory confirmed | 0% | 0% | 0% | 0% | MILESTONE: Landscape of Foundational Risk Processes and risk inventory confirmed | 0% | 0%
1.3.2 | DELIVERABLE: Review each foundational Risk ID process, identify deficiencies in data, technology and processes, and use gap analyses to determine how to optimize | 0% | 0% | 0% | 0% | DELIVERABLE: Review each foundational Risk ID process, identify deficiencies in data, technology and processes, and use gap analyses to determine how to optimize | 0% | 0%
1.3.2.1 | MILESTONE: Review each Foundational Risk Process, identify deficient processes, and use gap analyses to determine how to optimize processes | 0% | 0% | 0% | 0% | MILESTONE: Review each Foundational Risk Process, identify deficient processes, and use gap analyses to determine how to optimize processes | 0% | 0%
1.3.2.1.1 | Review and assess each Foundational Risk Process | 0% | 0% | 0% | 0% | Review and assess each Foundational Risk Process | 0% | 0%
1.3.2.1.2 | Determine optimal future state for each process | 0% | 0% | 0% | 0% | Determine optimal future state for each process | 0% | 0%
1.3.2.1.3 | Perform gap analyses for processes determined to be deficient | 0% | 0% | 0% | 0% | Perform gap analyses for processes determined to be deficient | 0% | 0%
1.3.2.1.4 | MILESTONE: Each Foundational Risk Process reviewed and assessed | 0% | 0% | 0% | 0% | MILESTONE: Each Foundational Risk Process reviewed and assessed | 0% | 0%
1.3.3 | DELIVERABLE: Develop remediation plans for foundational Risk ID processes | 0% | 0% | 0% | 0% | DELIVERABLE: Develop remediation plans for foundational Risk ID processes | 0% | 0%
1.3.3.1 | MILESTONE: Remediation of Foundational Risk Process plan Developed | 0% | 0% | 0% | 0% | MILESTONE: Remediation of Foundational Risk Process plan Developed | 0% | 0%
1.3.3.1.1 | Identify deficiencies in current plan | 0% | 0% | 0% | 0% | Identify deficiencies in current plan | 0% | 0%
1.3.3.1.2 | Determine optimal state for plan | 0% | 0% | 0% | 0% | Determine optimal state for plan | 0% | 0%
1.3.3.1.3 | Perform gap analysis in order to develop plan remediation | 0% | 0% | 0% | 0% | Perform gap analysis in order to develop plan remediation | 0% | 0%
1.3.3.1.4 | MILESTONE: Plan remediation developed | 0% | 0% | 0% | 0% | MILESTONE: Plan remediation developed | 0% | 0%
1.4 | DELIVERABLE: Execute remediation plans for foundational Risk ID processes, including requirements definition, development and implementation of planned data and technology solutions to support risk identification | 0% | 0% | 0% | 0% | DELIVERABLE: Execute remediation plans for foundational Risk ID processes, including requirements definition, development and implementation of planned data and technology solutions to support risk identification | 0% | 0%
1.5 | Long Term Planning Package | 0% | 0% | 0% | 0% | Long Term Planning Package | 0% | 0%
1.5.1 | DELIVERABLE: Updated SHUSA Risk taxonomy for Material Risk Program | 0% | 0% | 0% | 0% | DELIVERABLE: Updated SHUSA Risk taxonomy for Material Risk Program | 0% | 0%
1.5.1.1 | MILESTONE: Draft of updated risk taxonomy based on 2015 results | 0% | 0% | 0% | 0% | MILESTONE: Draft of updated risk taxonomy based on 2015 results | 0% | 0%
1.5.1.2 | MILESTONE: Final updated risk taxonomy based on 2015 results | 0% | 0% | 0% | 0% | MILESTONE: Final updated risk taxonomy based on 2015 results | 0% | 0%
1.5.2 | DELIVERABLE: Updated material risk inventory template and guidance for Material Risk Program | 0% | 0% | 0% | 0% | DELIVERABLE: Updated material risk inventory template and guidance for Material Risk Program | 0% | 0%
1.5.2.1 | MILESTONE: Updated material risk inventory template | 0% | 0% | 0% | 0% | MILESTONE: Updated material risk inventory template | 0% | 0%
1.5.2.2 | MILESTONE: Updated material risk guidance | 0% | 0% | 0% | 0% | MILESTONE: Updated material risk guidance | 0% | 0%
1.5.2.3 | MILESTONE: Updated aggregation and enrichment guidance | 0% | 0% | 0% | 0% | MILESTONE: Updated aggregation and enrichment guidance | 0% | 0%
1.5.3 | DELIVERABLE: Identify technology needs, requirements definition and implementation planning to support risk identification | 0% | 0% | 0% | 0% | DELIVERABLE: Identify technology needs, requirements definition and implementation planning to support risk identification | 0% | 0%
1.5.3.1 | MILESTONE: Technology requirements and BRD for risk inventory template web interface | 0% | 0% | 0% | 0% | MILESTONE: Technology requirements and BRD for risk inventory template web interface | 0% | 0%
1.5.3.2 | Deliver Technology requirements and BRD for Risk inventory template web interface | 0% | 0% | 0% | 0% | Deliver Technology requirements and BRD for Risk inventory template web interface | 0% | 0%
1.5.3.3 | MILESTONE: Implementation of web interface for risk inventory template | 0% | 0% | 0% | 0% | MILESTONE: Implementation of web interface for risk inventory template | 0% | 0%
1.5.3.4 | MILESTONE: Web interface pilot with selected business entities | 0% | 0% | 0% | 0% | MILESTONE: Web interface pilot with selected business entities | 0% | 0%
1.5.3.5 | MILESTONE: Roll out of web interface across business entities | 0% | 0% | 0% | 0% | MILESTONE: Roll out of web interface across business entities | 0% | 0%
1.5.4 | DELIVERABLE: Develop training materials, policies and procedures based on updated Material Risk Program process | 0% | 0% | 0% | 0% | DELIVERABLE: Develop training materials, policies and procedures based on updated Material Risk Program process | 0% | 0%
1.5.4.1 | MILESTONE: Development and rollout of training package for material risk ID process | 0% | 0% | 0% | 0% | MILESTONE: Development and rollout of training package for material risk ID process | 0% | 0%
1.5.4.2 | MILESTONE: Update and rollout of Policies and procedures for material risk ID process | 0% | 0% | 0% | 0% | MILESTONE: Update and rollout of Policies and procedures for material risk ID process | 0% | 0%
1.5.5 | DELIVERABLE: Develop and implement planned data and technology solutions (e.g. automated interface for risk inventory template, database for foundational inputs and data sources for risk identification, etc.) | 0% | 0% | 0% | 0% | DELIVERABLE: Develop and implement planned data and technology solutions (e.g. automated interface for risk inventory template, database for foundational inputs and data sources for risk identification, etc.) | 0% | 0%
1.5.5.1 | MILESTONE: Development of technology requirements and BRDs for database with business entity level foundational inputs and data sources | 0% | 0% | 0% | 0% | MILESTONE: Development of technology requirements and BRDs for database with business entity level foundational inputs and data sources | 0% | 0%
1.5.5.2 | MILESTONE: Implementation of database for foundational inputs and data sources | 0% | 0% | 0% | 0% | MILESTONE: Implementation of database for foundational inputs and data sources | 0% | 0%
1.5.5.3 | MILESTONE: Database pilot for selected business entities | 0% | 0% | 0% | 0% | MILESTONE: Database pilot for selected business entities | 0% | 0%
1.5.5.4 | MILESTONE: Roll out of database across business entities | 0% | 0% | 0% | 0% | MILESTONE: Roll out of database across business entities | 0% | 0%
1.5.6 | DELIVERABLE: Training materials, policies and procedures for risk ID database and process | 0% | 0% | 0% | 0% | DELIVERABLE: Training materials, policies and procedures for risk ID database and process | 0% | 0%
1.5.6.1 | MILESTONE: Training package for material risk ID database and process developed and rolled out | 0% | 0% | 0% | 0% | MILESTONE: Training package for material risk ID database and process developed and rolled out | 0% | 0%
1.5.6.2 | MILESTONE: Policies and procedures for material risk ID process updated and rolled out | 0% | 0% | 0% | 0% | MILESTONE: Policies and procedures for material risk ID process updated and rolled out | 0% | 0%
|  |  | 0% | 0% |  |  |  | 0%
|  |  | 0% | 0% |  |  |  | 0%
|  |  | 0% | 0% |  |  |  | 0%
|  |  | 0% | 0% |  |  |  | 0%
|  |  | 0% | 0% |  |  |  | 0%
|  |  | 0% | 0% |  |  |  | 0%
|  |  | 0% | 0% |  |  |  | 0%
|  |  | 0% | 0% |  |  |  | 0%
|  |  | 0% | 0% |  |  |  | 0%

## Original Template
Outline Level | WBS | Task Name | % Complete | Duration | Start | Finish | Contact | Notes | Updated Notes
0 | 0 | RT_Risk ID and Measurement 0728 1730 | 36% | 510d? | 2015-02-02 | 2017-01-13
1 | 1 | Risk ID & Measurement | 36% | 510d? | 2015-02-02 | 2017-01-13
2 | 1.1 | Risk Measurement Deliverables | 0% | 445d | 2015-05-01 | 2017-01-13
3 | 1.1.1 | DELIVERABLE: Program Design and Approval (Risk Taxonomy, Tools, Templates, Guidance) | 100% | 0d | 2015-05-01 | 2015-05-01
3 | 1.1.2 | DELIVERABLE: SHUSA Material Risk Program | 0% | 0d | 2016-01-15 | 2016-01-15 | D. Allaire
3 | 1.1.3 | DELIVERABLE: SBNA - Business Entity Material Risk Program | 0% | 0d | 2015-10-02 | 2015-10-02 | D. Allaire
3 | 1.1.4 | DELIVERABLE: SCUSA - Business Entity Material Risk Program | 0% | 0d | 2015-10-02 | 2015-10-02 | D. Allaire
3 | 1.1.5 | DELIVERABLE: New York Santander Investment Securities (SIS) - Business Entity Material Risk Program | 0% | 0d | 2015-10-02 | 2015-10-02 | D. Allaire
3 | 1.1.6 | DELIVERABLE: Puerto Rico - Business Entity Material Risk Program | 0% | 0d | 2015-10-02 | 2015-10-02 | D. Allaire
3 | 1.1.7 | DELIVERABLE: Miami - Business Entity Material Risk Program | 0% | 0d | 2015-10-02 | 2015-10-02 | D. Allaire
3 | 1.1.8 | DELIVERABLE: Assess Foundational Risk Processes and ensure complete Foundational Risk Inventory is in place | 0% | 0d | 2016-02-26 | 2016-02-26 | D. Allaire
3 | 1.1.9 | DELIVERABLE: Review each Foundational Risk Process; identify deficient processes, and use gap analyses to determine how to optimize processes | 0% | 0d | 2016-03-31 | 2016-03-31 | D. Allaire
3 | 1.1.10 | DELIVERABLE: Develop Foundational Risk Process remediation plan | 0% | 0d | 2016-04-27 | 2016-04-27 | D. Allaire
3 | 1.1.11 | DELIVERABLE: Updated risk taxonomy | 0% | 0d | 2016-01-15 | 2016-01-15 | D. Allaire
3 | 1.1.12 | DELIVERABLE: Updated material risk inventory template and guidance | 0% | 0d | 2016-02-26 | 2016-02-26 | D. Allaire
3 | 1.1.13 | DELIVERABLE: Identification of technology needs, requirements definition and implementation planning to support risk identification | 0% | 0d | 2016-03-31 | 2016-03-31 | D. Allaire
3 | 1.1.14 | DELIVERABLE: Training materials, policies and procedures based on updated material risk program process | 0% | 0d | 2016-06-17 | 2016-06-17 | D. Allaire
3 | 1.1.15 | DELIVERABLE: Development and implementation of planned data and technology solutions (e.g. automated interfaces for risk inventory template, database for foundational inputs and data sources for risk identification, etc) | 0% | 0d | 2016-11-15 | 2016-11-15 | D. Allaire
3 | 1.1.16 | DELIVERABLE: Training materials, policies and procedures for risk ID database and process | 0% | 0d | 2017-01-13 | 2017-01-13 | D. Allaire
2 | 1.2 | Design and execute the Material Risk Program across SHUSA (leveraging existing data and technology) | 44% | 250d | 2015-02-02 | 2016-01-15 | D. Allaire
3 | 1.2.1 | DELIVERABLE: Design material risk program and obtain approvals (incl. risk taxonomy, tools, templates, guidance) | 100% | 65d | 2015-02-02 | 2015-05-01 | D. Allaire
4 | 1.2.1.1 | MILESTONE: Program Design and Approval (Risk Taxonomy, Tools, Templates, Guidance) | 100% | 65d | 2015-02-02 | 2015-05-01
3 | 1.2.2 | DELIVERABLE: Create risk inventory for the SHUSA, hold workshops for aggregation | 0% | 75d | 2015-10-05 | 2016-01-15 | D. Allaire
4 | 1.2.2.1 | MILESTONE: Preparation for Aggregation to Create SHUSA Material Risk Inventory | 0% | 11d | 2015-10-05 | 2015-10-19
5 | 1.2.2.1.1 | ERM Collects Risk Inventories from Entity Risk Managers | 0% | 5d? | 2015-10-05 | 2015-10-09
5 | 1.2.2.1.2 | ERM Sorts risks and groups by Risk Type | 0% | 5d? | 2015-10-05 | 2015-10-09
5 | 1.2.2.1.3 | ERM Creates pre-Workshop, pre-read Materials and instructions for SHUSA Risk Managers | 0% | 5d? | 2015-10-05 | 2015-10-09
5 | 1.2.2.1.4 | ERM Distributes Workshop Materials to Responsible parties | 0% | 5d? | 2015-10-05 | 2015-10-09
5 | 1.2.2.1.5 | Aggregation to Create SHUSA Material Risk Inventory Prepared | 0% | 0d | 2015-10-19 | 2015-10-19 | D. Mael | Technology
4 | 1.2.2.2 | MILESTONE: Hold SHUSA Aggregation Workshops (include 2nd LOD challenge) | 0% | 11d | 2015-10-12 | 2015-10-26
5 | 1.2.2.2.1 | TASK: Credit Risk Material Risk Aggregation | 0% | 11d? | 2015-10-12 | 2015-10-26
6 | 1.2.2.2.1.1 | Credit Risk performs pre-Read and analysis | 0% | 4d? | 2015-10-12 | 2015-10-15
6 | 1.2.2.2.1.2 | Risk Managers Conduct Credit pre-Workshop Enrichment and Aggregation Activites | 0% | 4d? | 2015-10-12 | 2015-10-15
6 | 1.2.2.2.1.3 | ERM facilitates Credit Aggregation and Enrichment Workshop | 0% | 11d? | 2015-10-12 | 2015-10-26
6 | 1.2.2.2.1.4 | Present to Level II Subcommittees | 0% | 2d? | 2015-10-12 | 2015-10-13
6 | 1.2.2.2.1.5 | Credit Risk Material Risk Aggregation Prepared | 0% | 0d | 2015-10-12 | 2015-10-12 | K. Martelon
5 | 1.2.2.2.2 | TASK: Operational Risk Material Risk Aggregation | 0% | 11d? | 2015-10-12 | 2015-10-26
6 | 1.2.2.2.2.1 | Operational Risk performs pre-Read and analysis | 0% | 4d? | 2015-10-12 | 2015-10-15
6 | 1.2.2.2.2.2 | Risk Managers Conduct Operational Risk pre-Workshop Enrichment and Aggregation Activites | 0% | 4d? | 2015-10-12 | 2015-10-15
6 | 1.2.2.2.2.3 | ERM facilitates Operational Risk Aggregation and Enrichment Workshop | 0% | 11d? | 2015-10-12 | 2015-10-26
6 | 1.2.2.2.2.4 | Present to Level II Subcommittees | 0% | 2d? | 2015-10-12 | 2015-10-13
6 | 1.2.2.2.2.5 | Operational Risk Material Risk Aggregation Prepared | 0% | 0d | 2015-10-12 | 2015-10-12 | J. Christie
5 | 1.2.2.2.3 | TASK: Compliance Material Risk Aggregation | 0% | 11d? | 2015-10-12 | 2015-10-26
6 | 1.2.2.2.3.1 | Compliance performs pre-Read and analysis | 0% | 4d? | 2015-10-12 | 2015-10-15
6 | 1.2.2.2.3.2 | Risk Managers Conduct Compliance pre-Workshop Enrichment and Aggregation Activites | 0% | 4d? | 2015-10-12 | 2015-10-15
6 | 1.2.2.2.3.3 | ERM facilitates Compliance Aggregation and Enrichment Workshop | 0% | 11d? | 2015-10-12 | 2015-10-26
6 | 1.2.2.2.3.4 | Present to Level II Subcommittees | 0% | 2d? | 2015-10-12 | 2015-10-13
6 | 1.2.2.2.3.5 | Compliance Material Risk Aggregation Prepared | 0% | 0d | 2015-10-12 | 2015-10-12 | J. Christie
5 | 1.2.2.2.4 | TASK: Model Material Risk Aggregation | 0% | 11d? | 2015-10-12 | 2015-10-26
6 | 1.2.2.2.4.1 | Model Risk performs pre-Read and analysis | 0% | 4d? | 2015-10-12 | 2015-10-15
6 | 1.2.2.2.4.2 | Risk Managers Conduct Model pre-Workshop Enrichment and Aggregation Activites | 0% | 4d? | 2015-10-12 | 2015-10-15
6 | 1.2.2.2.4.3 | ERM facilitates Model Aggregation and Enrichment Workshop | 0% | 11d? | 2015-10-12 | 2015-10-26
6 | 1.2.2.2.4.4 | Present to Level II Subcommittees | 0% | 2d? | 2015-10-12 | 2015-10-13
6 | 1.2.2.2.4.5 | Model Material Risk Aggregation Prepared | 0% | 0d | 2015-10-12 | 2015-10-12 | D. Mael
5 | 1.2.2.2.5 | TASK: Market Material Risk Aggregation2 | 0% | 11d? | 2015-10-12 | 2015-10-26
6 | 1.2.2.2.5.1 | Market Risk performs pre-Read and analysis | 0% | 4d? | 2015-10-12 | 2015-10-15
6 | 1.2.2.2.5.2 | Risk Managers Conduct Market pre-Workshop Enrichment and Aggregation Activites | 0% | 4d? | 2015-10-12 | 2015-10-15
6 | 1.2.2.2.5.3 | ERM facilitates Market Aggregation and Enrichment Workshop | 0% | 11d? | 2015-10-12 | 2015-10-26
6 | 1.2.2.2.5.4 | Present to Level II Subcommittees | 0% | 2d? | 2015-10-12 | 2015-10-13
6 | 1.2.2.2.5.5 | Market Material Risk Aggregation Prepared | 0% | 0d | 2015-10-12 | 2015-10-12 | R. Ballou
5 | 1.2.2.2.6 | TASK: Liquidity Material Risk Aggregation | 0% | 11d? | 2015-10-12 | 2015-10-26
6 | 1.2.2.2.6.1 | Liquidity Risk performs pre-Read and analysis | 0% | 4d? | 2015-10-12 | 2015-10-15
6 | 1.2.2.2.6.2 | Risk Managers Conduct Liquidity pre-Workshop Enrichment and Aggregation Activites | 0% | 4d? | 2015-10-12 | 2015-10-15
6 | 1.2.2.2.6.3 | ERM facilitates Liquidity Aggregation and Enrichment Workshop | 0% | 11d? | 2015-10-12 | 2015-10-26
6 | 1.2.2.2.6.4 | Present to Level II Subcommittees | 0% | 2d? | 2015-10-12 | 2015-10-13
6 | 1.2.2.2.6.5 | Liquidity Material Risk Aggregation Prepared | 0% | 0d | 2015-10-12 | 2015-10-12 | R. Ballou
5 | 1.2.2.2.7 | TASK: Strategic Material Risk Aggregation | 0% | 11d? | 2015-10-12 | 2015-10-26
6 | 1.2.2.2.7.1 | Strategic Risk performs pre-Read and analysis | 0% | 4d? | 2015-10-12 | 2015-10-15
6 | 1.2.2.2.7.2 | Risk Managers Conduct Strategic pre-Workshop Enrichment and Aggregation Activites | 0% | 4d? | 2015-10-12 | 2015-10-15
6 | 1.2.2.2.7.3 | ERM facilitates Strategic Aggregation and Enrichment Workshop | 0% | 11d? | 2015-10-12 | 2015-10-26
6 | 1.2.2.2.7.4 | Present to Level II Subcommittees | 0% | 2d? | 2015-10-12 | 2015-10-13
6 | 1.2.2.2.7.5 | Strategic Material Risk Aggregation Prepared | 0% | 0d | 2015-10-12 | 2015-10-12 | K. Martelon
5 | 1.2.2.2.8 | TASK: Reputational Material Risk Aggregation | 0% | 11d? | 2015-10-12 | 2015-10-26
6 | 1.2.2.2.8.1 | Reputational Risk performs pre-Read and analysis | 0% | 4d? | 2015-10-12 | 2015-10-15
6 | 1.2.2.2.8.2 | Risk Managers Conduct Reputational pre-Workshop Enrichment and Aggregation Activites | 0% | 4d? | 2015-10-12 | 2015-10-15
6 | 1.2.2.2.8.3 | ERM facilitates Reputational Aggregation and Enrichment Workshop | 0% | 11d? | 2015-10-12 | 2015-10-26
6 | 1.2.2.2.8.4 | Present to Level II Subcommittees | 0% | 2d? | 2015-10-12 | 2015-10-13
6 | 1.2.2.2.8.5 | Reputational Material Risk Aggregation Prepared | 0% | 0d | 2015-10-12 | 2015-10-12 | K. Martelon
4 | 1.2.2.3 | MILESTONE:Execute on SHUSA Top Down Aggregation (1st and 2nd LOD executive challenge) | 0% | 11d | 2015-10-26 | 2015-11-09
5 | 1.2.2.3.1 | TASK:SHUSA Top Down Aggregation | 0% | 11d | 2015-10-26 | 2015-11-09
6 | 1.2.2.3.1.1 | ERM consolidates risks into SHUSA Inventory | 0% | 1d | 2015-10-26 | 2015-10-26
6 | 1.2.2.3.1.2 | ERM distributes inventory to SHUSA Business and Risk executives | 0% | 2d | 2015-10-26 | 2015-10-27
6 | 1.2.2.3.1.3 | ERM incorporates final risks into SHUSA Inventory | 0% | 4d | 2015-10-26 | 2015-10-29
6 | 1.2.2.3.1.4 | SHUSA Top Down Aggregation Prepared | 0% | 1d | 2015-11-09 | 2015-11-09
4 | 1.2.2.4 | MILESTONE:Obtain approvals for Material Risks of SHUSA (final aggregation, Board and Management review and challenge) | 0% | 20d | 2015-11-09 | 2015-12-04
5 | 1.2.2.4.1 | TASK:Establish Clear Linkage of MRP Outputs to Capital Planning Scenario Design Process | 0% | 40d | 2015-10-12 | 2015-12-04
6 | 1.2.2.4.1.1 | Present SHUSA Material Risks to CCAR and Capital Plan | 0% | 40d | 2015-10-12 | 2015-12-04
6 | 1.2.2.4.1.2 | Deliver SHUSA Material Risks to CCAR and Capital Plan | 0% | 0d | 2015-12-04 | 2015-12-04 |  | CCAR
5 | 1.2.2.4.2 | TASK:Material Risk SHUSA Approval | 0% | 20d? | 2015-11-09 | 2015-12-04
6 | 1.2.2.4.2.1 | Present SHUSA Material Risks to BERC | 0% | 20d? | 2015-11-09 | 2015-12-04
6 | 1.2.2.4.2.2 | Present SHUSA Material Risks to ERMC | 0% | 20d? | 2015-11-09 | 2015-12-04
6 | 1.2.2.4.2.3 | Material Risk SHUSA Approval | 0% | 0d | 2015-12-04 | 2015-12-04
4 | 1.2.2.5 | MILESTONE:Draft Risk ID and Assessment Policy and obtain approvals | 0% | 60d | 2015-10-26 | 2016-01-15 |  | Technology
5 | 1.2.2.5.1 | TASK:Risk ID and Assessment Policy | 0% | 60d? | 2015-10-26 | 2016-01-15
6 | 1.2.2.5.1.1 | Risk ID and Assessment group drafts policy | 0% | 37d? | 2015-10-26 | 2015-12-15
6 | 1.2.2.5.1.2 | Risk ID and Assessment group presents draft to ERMC for approval | 0% | 26d? | 2015-12-01 | 2016-01-05
6 | 1.2.2.5.1.3 | Risk ID and Assessment group presents to Risk Committee (BERC) | 0% | 34d? | 2015-12-01 | 2016-01-15
6 | 1.2.2.5.1.4 | Risk ID and Assessment Policy | 0% | 0d | 2016-01-15 | 2016-01-15 | K. Martelon
3 | 1.2.3 | DELIVERABLE: Design and execute the Material Risk Program across SBNA | 51% | 92d | 2015-05-28 | 2015-10-02 | D. Allaire
4 | 1.2.3.1 | MILESTONE:Preparation for Aggregation to Create Retail Banking Material Risk Inventory | 95% | 24d | 2015-06-29 | 2015-07-31
5 | 1.2.3.1.1 | TASK: Small Business Banking Material Risk Inventory | 100% | 24d | 2015-06-29 | 2015-07-31
6 | 1.2.3.1.1.1 | Deliver Final Inventory to SBNA and SHUSA ERM | 100% | 24d | 2015-06-29 | 2015-07-30 |  | Collect Documentation
6 | 1.2.3.1.1.2 | Small Business Banking Material Risk Inventory Prepared | 100% | 0d | 2015-07-31 | 2015-07-31 | Alhadeff/Carbone
5 | 1.2.3.1.2 | TASK: Cards Material Risk Inventory | 100% | 24d | 2015-06-29 | 2015-07-31
6 | 1.2.3.1.2.1 | Deliver Final Inventory to SBNA and SHUSA ERM | 100% | 24d | 2015-06-29 | 2015-07-30 |  | Collect Documentation
6 | 1.2.3.1.2.2 | Cards Material Risk Inventory Prepared | 100% | 0d | 2015-07-31 | 2015-07-31 | Alhadeff/Carbone
5 | 1.2.3.1.3 | TASK: Mortgages Material Risk Inventory | 100% | 24d | 2015-06-29 | 2015-07-31
6 | 1.2.3.1.3.1 | Deliver Final Inventory to SBNA and SHUSA ERM | 100% | 24d | 2015-06-29 | 2015-07-30 |  | Collect Documentation
6 | 1.2.3.1.3.2 | Mortgages Material Risk Inventory Prepared | 100% | 0d | 2015-07-31 | 2015-07-31 | Alhadeff/Carbone
5 | 1.2.3.1.4 | TASK: Purchased Portfolios (RV/Marine) Material Risk Inventory | N/A | 24d | 2015-06-29 | 2015-07-31 |  |  | LOB merged away in reorg. No longer relevant
6 | 1.2.3.1.4.1 | Deliver Final Inventory to SBNA and SHUSA ERM | N/A | 24d | 2015-06-29 | 2015-07-30 |  | Collect Documentation | LOB merged away in reorg. No longer relevant
6 | 1.2.3.1.4.2 | Purchased Portfolios (RV/Marine) Material Risk Inventory Prepared | N/A | 0d | 2015-07-31 | 2015-07-31 | Alhadeff/Carbone |  | LOB merged away in reorg. No longer relevant
5 | 1.2.3.1.5 | TASK: Individual Material Risk Inventory | N/A | 24d | 2015-06-29 | 2015-07-31 |  |  | LOB merged away in reorg. No longer relevant
6 | 1.2.3.1.5.1 | Deliver Final Inventory to SBNA and SHUSA ERM | N/A | 24d | 2015-06-29 | 2015-07-30 |  | Collect Documentation | LOB merged away in reorg. No longer relevant
6 | 1.2.3.1.5.2 | Individual Material Risk Inventory Prepared | N/A | 0d | 2015-07-31 | 2015-07-31 | Alhadeff/Carbone |  | LOB merged away in reorg. No longer relevant
5 | 1.2.3.1.6 | TASK: Wealth Management Material Risk Inventory | N/A | 24d | 2015-06-29 | 2015-07-31 |  |  | LOB merged away in reorg. No longer relevant
6 | 1.2.3.1.6.1 | Deliver Final Inventory to SBNA and SHUSA ERM | N/A | 24d | 2015-06-29 | 2015-07-30 |  | Collect Documentation | LOB merged away in reorg. No longer relevant
6 | 1.2.3.1.6.2 | Wealth Management Material Risk Inventory Prepared | N/A | 0d | 2015-07-31 | 2015-07-31 | Alhadeff/Carbone |  | LOB merged away in reorg. No longer relevant
4 | 1.2.3.2 | MILESTONE:Retail: Create Retail Banking Material Risk Inventory | 100% | 24d | 2015-06-29 | 2015-07-31
5 | 1.2.3.2.1 | TASK: Retail: Create Retail Banking Material Risk Inventory | 100% | 24d | 2015-06-29 | 2015-07-31
6 | 1.2.3.2.1.1 | Create Segment Material Risk Inventory (Aggregation) | 100% | 24d | 2015-06-29 | 2015-07-30 |  | Collect Documentation
6 | 1.2.3.2.1.2 | Retail: Create Retail Banking Material Risk Inventory Prepared | 100% | 0d | 2015-07-31 | 2015-07-31 | Alhadeff/Carbone
4 | 1.2.3.3 | MILESTONE:Commercial Banking Material Risk Inventory | 100% | 24d | 2015-06-29 | 2015-07-31
5 | 1.2.3.3.1 | TASK: Commercial and Industrial Material Risk Inventory | 100% | 24d | 2015-06-29 | 2015-07-31
6 | 1.2.3.3.1.1 | Deliver Final Inventory to SBNA and SHUSA ERM | 100% | 24d | 2015-06-29 | 2015-07-30 |  | Collect Documentation
6 | 1.2.3.3.1.2 | Commercial and Industrial Material Risk Inventory Prepared | 100% | 0d | 2015-07-31 | 2015-07-31 | Alhadeff/Carbone
5 | 1.2.3.3.2 | TASK: Specialties Material Risk Inventory | 100% | 24d | 2015-06-29 | 2015-07-31
6 | 1.2.3.3.2.1 | Deliver Final Inventory to SBNA and SHUSA ERM | 100% | 24d | 2015-06-29 | 2015-07-30 |  | Collect Documentation
6 | 1.2.3.3.2.2 | Specialties Material Risk Inventory Prepared | 100% | 0d | 2015-07-31 | 2015-07-31 | Alhadeff/Carbone
5 | 1.2.3.3.3 | TASK: Government Banking Material Risk Inventory | 100% | 24d | 2015-06-29 | 2015-07-31
6 | 1.2.3.3.3.1 | Deliver Final Inventory to SBNA and SHUSA ERM | 100% | 24d | 2015-06-29 | 2015-07-30 |  | Collect Documentation
6 | 1.2.3.3.3.2 | Government Banking Material Risk Inventory Prepared | 100% | 0d | 2015-07-31 | 2015-07-31 | Alhadeff/Carbone
4 | 1.2.3.4 | MILESTONE: Commercial: Create Commercial Banking Material Risk Inventory | 100% | 24d | 2015-06-29 | 2015-07-31
5 | 1.2.3.4.1 | TASK: Commercial: Create Commercial Banking Material Risk Inventory | 100% | 24d | 2015-06-29 | 2015-07-31
6 | 1.2.3.4.1.1 | Create Segment Material Risk Inventory (Aggregation) | 100% | 24d | 2015-06-29 | 2015-07-30 |  | Collect Documentation
6 | 1.2.3.4.1.2 | Create Commercial Banking Material Risk Inventory Prepared | 100% | 0d | 2015-07-31 | 2015-07-31 | Alhadeff/Carbone
4 | 1.2.3.5 | MILESTONE:Global Banking Material Risk Inventory | 100% | 24d | 2015-06-29 | 2015-07-31
5 | 1.2.3.5.1 | TASK: MRG Material Risk Inventory | 100% | 24d | 2015-06-29 | 2015-07-31
6 | 1.2.3.5.1.1 | Deliver Final Inventory to SBNA and SHUSA ERM | 100% | 24d | 2015-06-29 | 2015-07-30 |  | Collect Documentation
6 | 1.2.3.5.1.2 | MRG Material Risk Inventory Prepared | 100% | 0d | 2015-07-31 | 2015-07-31 | Alhadeff/Carbone
5 | 1.2.3.5.2 | TASK: Large Corporates Material Risk Inventory | 100% | 24d | 2015-06-29 | 2015-07-31
6 | 1.2.3.5.2.1 | Deliver Final Inventory to SBNA and SHUSA ERM | 100% | 24d | 2015-06-29 | 2015-07-30 |  | Collect Documentation
6 | 1.2.3.5.2.2 | Large Corporates Material Risk Inventory Prepared | 100% | 0d | 2015-07-31 | 2015-07-31 | Alhadeff/Carbone
4 | 1.2.3.6 | MILESTONE:Global: Create Global Banking Material Risk Inventory | 100% | 24d | 2015-06-29 | 2015-07-31
5 | 1.2.3.6.1 | TASK: Global: Create Global Banking Material Risk Inventory | 100% | 24d | 2015-06-29 | 2015-07-31
6 | 1.2.3.6.1.1 | Create Segment Material Risk Inventory (Aggregation) | 100% | 24d | 2015-06-29 | 2015-07-30 |  | Collect Documentation
6 | 1.2.3.6.1.2 | Global: Create Global Banking Material Risk Inventory Prepared | 100% | 0d | 2015-07-31 | 2015-07-31 | Alhadeff/Carbone
4 | 1.2.3.7 | MILESTONE:Automotive Finance Material Risk Inventory | 100% | 2d | 2015-06-29 | 2015-06-30
5 | 1.2.3.7.1 | TASK: CEVF Material Risk Inventory | 100% | 2d | 2015-06-29 | 2015-06-30
6 | 1.2.3.7.1.1 | Deliver Final Inventory to SBNA and SHUSA ERM | 100% | 2d | 2015-06-29 | 2015-06-30 |  | Collect Documentation
6 | 1.2.3.7.1.2 | CEVF Material Risk Inventory Prepared | 100% | 0d | 2015-06-30 | 2015-06-30 | Alhadeff/Carbone
5 | 1.2.3.7.2 | TASK: Leasing Material Risk Inventory | 100% | 2d | 2015-06-29 | 2015-06-30
6 | 1.2.3.7.2.1 | Deliver Final Inventory to SBNA and SHUSA ERM | 100% | 2d | 2015-06-29 | 2015-06-30 |  | Collect Documentation
6 | 1.2.3.7.2.2 | Leasing Material Risk Inventory Prepared | 100% | 0d | 2015-06-30 | 2015-06-30 | Alhadeff/Carbone
5 | 1.2.3.7.3 | TASK: Dealer Floor Plan Material Risk Inventory | 100% | 2d | 2015-06-29 | 2015-06-30
6 | 1.2.3.7.3.1 | Deliver Final Inventory to SBNA and SHUSA ERM | 100% | 2d | 2015-06-29 | 2015-06-30 |  | Collect Documentation
6 | 1.2.3.7.3.2 | Dealer Floor Plan Material Risk Inventory Prepared | 100% | 0d | 2015-06-30 | 2015-06-30 | Alhadeff/Carbone
4 | 1.2.3.8 | MILESTONE: Automotive: Create Automotive Finance Material Risk Inventory | 100% | 24d | 2015-05-28 | 2015-06-30
5 | 1.2.3.8.1 | TASK: Automotive: Create Automotive Finance Material Risk Inventory | 100% | 24d | 2015-05-28 | 2015-06-30
6 | 1.2.3.8.1.1 | Create Segment Material Risk Inventory (Aggregation) | 100% | 24d | 2015-05-28 | 2015-06-30 |  | Collect Documentation
6 | 1.2.3.8.1.2 | Automotive Finance Material Risk Inventory Prepared | 100% | 0d | 2015-06-30 | 2015-06-30 | Alhadeff/Carbone
4 | 1.2.3.9 | MILESTONE: Commerical Real Estate Material Risk Inventory | 100% | 24d | 2015-06-29 | 2015-07-31
5 | 1.2.3.9.1 | TASK: Commerical Real Estate Material Risk Inventory | 100% | 24d | 2015-06-29 | 2015-07-31
6 | 1.2.3.9.1.1 | Deliver Final Inventory to SBNA and SHUSA ERM | 100% | 24d | 2015-06-29 | 2015-07-30 |  | Collect Documentation
6 | 1.2.3.9.1.2 | Commerical Real Estate Material Risk Inventory Prepared | 100% | 0d | 2015-07-31 | 2015-07-31 | Alhadeff/Carbone
4 | 1.2.3.10 | MILESTONE:Financial Management Material Risk Inventory | N/A | 24d | 2015-06-29 | 2015-07-31 |  |  | LOB merged away in reorg. No longer relevant
5 | 1.2.3.10.1 | TASK: Financial Management Material Risk Inventory | N/A | 24d | 2015-06-29 | 2015-07-31 |  |  | LOB merged away in reorg. No longer relevant
6 | 1.2.3.10.1.1 | Deliver Final Inventory to SBNA and SHUSA ERM | N/A | 24d | 2015-06-29 | 2015-07-30 |  | Collect Documentation | LOB merged away in reorg. No longer relevant
6 | 1.2.3.10.1.2 | Financial Management Material Risk Inventory Prepared | N/A | 0d | 2015-07-31 | 2015-07-31 | Alhadeff/Carbone |  | LOB merged away in reorg. No longer relevant
4 | 1.2.3.11 | MILESTONE:Corporate Center Material Risk Inventory | N/A | 24d | 2015-06-29 | 2015-07-31 |  |  | LOB merged away in reorg. No longer relevant
5 | 1.2.3.11.1 | TASK: Corporate Center Material Risk Inventory | N/A | 24d | 2015-06-29 | 2015-07-31 |  |  | LOB merged away in reorg. No longer relevant
6 | 1.2.3.11.1.1 | Deliver Final Inventory to SBNA and SHUSA ERM | N/A | 24d | 2015-06-29 | 2015-07-30 |  | Collect Documentation | LOB merged away in reorg. No longer relevant
6 | 1.2.3.11.1.2 | Corporate Center Material Risk Inventory Prepared | N/A | 0d | 2015-07-31 | 2015-07-31 | Alhadeff/Carbone |  | LOB merged away in reorg. No longer relevant
4 | 1.2.3.12 | MILESTONE: Legal Material Risk Inventory | 100% | 26d | 2015-06-26 | 2015-07-31
5 | 1.2.3.12.1 | TASK: Legal Material Risk Inventory | 100% | 26d | 2015-06-26 | 2015-07-31
6 | 1.2.3.12.1.1 | Deliver Final Inventory to SBNA and SHUSA ERM | 100% | 26d | 2015-06-26 | 2015-07-31 |  | Collect Documentation
6 | 1.2.3.12.1.2 | Legal Material Risk Inventory Prepared | 100% | 1d | 2015-07-31 | 2015-07-31 | Alhadeff/Carbone
4 | 1.2.3.13 | MILESTONE:HR Material Risk Inventory | 100% | 26d | 2015-06-26 | 2015-07-31
5 | 1.2.3.13.1 | TASK: HR Material Risk Inventory | 100% | 26d | 2015-06-26 | 2015-07-31
6 | 1.2.3.13.1.1 | Deliver Final Inventory to SBNA and SHUSA ERM | 100% | 25d | 2015-06-26 | 2015-07-30 |  | Collect Documentation
6 | 1.2.3.13.1.2 | HR Material Risk Inventory Prepared | 100% | 1d | 2015-07-31 | 2015-07-31 | Alhadeff/Carbone
4 | 1.2.3.14 | MILESTONE:Tech and Operations Material Risk Inventory | 100% | 26d | 2015-06-26 | 2015-07-31
5 | 1.2.3.14.1 | TASK: Tech and Operations Material Risk Inventory | 100% | 26d | 2015-06-26 | 2015-07-31
6 | 1.2.3.14.1.1 | Deliver Final Inventory to SBNA and SHUSA ERM | 100% | 2d | 2015-07-29 | 2015-07-30 |  | Collect Documentation
6 | 1.2.3.14.1.2 | Tech and Operations Material Risk Inventory Prepared | 100% | 0d | 2015-07-31 | 2015-07-31 | Alhadeff/Carbone
4 | 1.2.3.15 | MILESTONE:Finance Material Risk Inventory | 100% | 24d | 2015-06-29 | 2015-07-31
5 | 1.2.3.15.1 | TASK: Finance Material Risk Inventory | 100% | 24d | 2015-06-29 | 2015-07-31
6 | 1.2.3.15.1.1 | Deliver Final Inventory to SBNA and SHUSA ERM | 100% | 24d | 2015-06-29 | 2015-07-30 |  | Collect Documentation
6 | 1.2.3.15.1.2 | Finance Material Risk Inventory Prepared | 100% | 0d | 2015-07-31 | 2015-07-31 | Alhadeff/Carbone
4 | 1.2.3.16 | MILESTONE:Hold SBNA Aggregation Workshops (include 2nd LOD challenge) | 50% | 45d | 2015-08-03 | 2015-10-02
5 | 1.2.3.16.1 | TASK: Credit Risk Aggregation | 50% | 41d? | 2015-08-03 | 2015-09-28 |  |  | Dates & task names have changed and need to be updated
6 | 1.2.3.16.1.1 | ERM disseminates Workshop Pre-Read Materials to Risk Managers | 50% | 16d? | 2015-08-03 | 2015-08-24 |  |  | Dates & task names have changed and need to be updated
6 | 1.2.3.16.1.2 | ERM facilitates Aggregation and Enrichment Activities | 50% | 25d? | 2015-08-25 | 2015-09-28 |  |  | Dates & task names have changed and need to be updated
6 | 1.2.3.16.1.3 | Risk Manager presents inventory to level II subcommittee | 50% | 1d? | 2015-08-03 | 2015-08-03 |  |  | Dates & task names have changed and need to be updated
6 | 1.2.3.16.1.4 | Credit Risk Aggregation Prepared | 50% | 0d | 2015-08-03 | 2015-08-03 | Alhadeff/Carbone |  | Dates & task names have changed and need to be updated
5 | 1.2.3.16.2 | TASK: Operational Risk Material Risk Aggregation | 50% | 41d? | 2015-08-03 | 2015-09-28 |  |  | Dates & task names have changed and need to be updated
6 | 1.2.3.16.2.1 | ERM disseminates Workshop Pre-Read Materials to Risk Managers | 50% | 16d? | 2015-08-03 | 2015-08-24 |  |  | Dates & task names have changed and need to be updated
6 | 1.2.3.16.2.2 | ERM facilitates Aggregation and Enrichment Activities | 50% | 25d? | 2015-08-25 | 2015-09-28 |  |  | Dates & task names have changed and need to be updated
6 | 1.2.3.16.2.3 | Risk Manager presents inventory to level II subcommittee | 50% | 1d? | 2015-08-03 | 2015-08-03 |  |  | Dates & task names have changed and need to be updated
6 | 1.2.3.16.2.4 | Operational Risk Material Risk Aggregation Prepared | 50% | 0d | 2015-08-03 | 2015-08-03 | Alhadeff/Carbone |  | Dates & task names have changed and need to be updated
5 | 1.2.3.16.3 | TASK: Compliance Material Risk Aggregation | 50% | 41d? | 2015-08-03 | 2015-09-28 |  |  | Dates & task names have changed and need to be updated
6 | 1.2.3.16.3.1 | ERM disseminates Workshop Pre-Read Materials to Risk Managers | 50% | 16d? | 2015-08-03 | 2015-08-24 |  |  | Dates & task names have changed and need to be updated
6 | 1.2.3.16.3.2 | ERM facilitates Aggregation and Enrichment Activities | 50% | 25d? | 2015-08-25 | 2015-09-28 |  |  | Dates & task names have changed and need to be updated
6 | 1.2.3.16.3.3 | Risk Manager presents inventory to level II subcommittee | 50% | 1d? | 2015-08-03 | 2015-08-03 |  |  | Dates & task names have changed and need to be updated
6 | 1.2.3.16.3.4 | Compliance Material Risk Aggregation Prepared | 50% | 0d | 2015-08-03 | 2015-08-03 | Alhadeff/Carbone |  | Dates & task names have changed and need to be updated
5 | 1.2.3.16.4 | TASK: Model Material Risk Aggregation | 50% | 41d? | 2015-08-03 | 2015-09-28 |  |  | Dates & task names have changed and need to be updated
6 | 1.2.3.16.4.1 | ERM disseminates Workshop Pre-Read Materials to Risk Managers | 50% | 16d? | 2015-08-03 | 2015-08-24 |  |  | Dates & task names have changed and need to be updated
6 | 1.2.3.16.4.2 | ERM facilitates Aggregation and Enrichment Activities | 50% | 25d? | 2015-08-25 | 2015-09-28 |  |  | Dates & task names have changed and need to be updated
6 | 1.2.3.16.4.3 | Risk Manager presents inventory to level II subcommittee | 50% | 1d? | 2015-08-03 | 2015-08-03 |  |  | Dates & task names have changed and need to be updated
6 | 1.2.3.16.4.4 | Model Material Risk Aggregation Prepared | 50% | 0d | 2015-08-03 | 2015-08-03 | Alhadeff/Carbone |  | Dates & task names have changed and need to be updated
5 | 1.2.3.16.5 | TASK: Liquidity/Market Material Risk Aggregation | 50% | 41d? | 2015-08-03 | 2015-09-28 |  |  | Dates & task names have changed and need to be updated
6 | 1.2.3.16.5.1 | ERM disseminates Workshop Pre-Read Materials to Risk Managers | 50% | 16d? | 2015-08-03 | 2015-08-24 |  |  | Dates & task names have changed and need to be updated
6 | 1.2.3.16.5.2 | ERM facilitates Aggregation and Enrichment Activities | 50% | 25d? | 2015-08-25 | 2015-09-28 |  |  | Dates & task names have changed and need to be updated
6 | 1.2.3.16.5.3 | Risk Manager presents inventory to level II subcommittee | 50% | 1d? | 2015-08-03 | 2015-08-03 |  |  | Dates & task names have changed and need to be updated
6 | 1.2.3.16.5.4 | Liquidity/Market Material Risk Aggregation Prepared | 50% | 0d | 2015-08-03 | 2015-08-03 | Alhadeff/Carbone |  | Dates & task names have changed and need to be updated
5 | 1.2.3.16.6 | TASK: Reputational/Strategic Material Risk Aggregation | 50% | 41d? | 2015-08-03 | 2015-09-28 |  |  | Dates & task names have changed and need to be updated
6 | 1.2.3.16.6.1 | ERM disseminates Workshop Pre-Read Materials to Risk Managers | 50% | 16d? | 2015-08-03 | 2015-08-24 |  |  | Dates & task names have changed and need to be updated
6 | 1.2.3.16.6.2 | ERM facilitates Aggregation and Enrichment Workshop | 50% | 25d? | 2015-08-25 | 2015-09-28 |  |  | Dates & task names have changed and need to be updated
6 | 1.2.3.16.6.3 | Risk Manager presents inventory to level II subcommittee | 50% | 1d? | 2015-08-03 | 2015-08-03
6 | 1.2.3.16.6.4 | Reputational/Strategic Material Risk Aggregation Prepared | 50% | 0d | 2015-08-03 | 2015-08-03 | Alhadeff/Carbone
4 | 1.2.3.17 | Present Results to SBNA ERMC | 0% | 48d | 2015-07-28 | 2015-10-01 | Alhadeff/Carbone
4 | 1.2.3.18 | Present Results to SBNA BERC | 0% | 48d | 2015-07-28 | 2015-10-01 | Alhadeff/Carbone
4 | 1.2.3.19 | Present SBNA Results to CCAR | 0% | 25d | 2015-08-31 | 2015-10-02
4 | 1.2.3.20 | Deliver SBNA Material Risks to CCAR and Capital Plan | 0% | 0d | 2015-10-02 | 2015-10-02 |  | CCAR
3 | 1.2.4 | DELIVERABLE: Design and execute the Material Risk Program across SCUSA | 2% | 92d | 2015-05-28 | 2015-10-02 | D. Allaire |  | SCUSA now has only 3 inventories and completely new dates.
4 | 1.2.4.1 | MILESTONE: Automotive Finance Material Risk Inventory | 8% | 25d | 2015-06-29 | 2015-07-31 |  |  | SCUSA now has only 3 inventories and completely new dates.
5 | 1.2.4.1.1 | TASK:Automotive Finance Material Risk Inventory | 8% | 25d | 2015-06-29 | 2015-07-31 |  |  | SCUSA now has only 3 inventories and completely new dates.
6 | 1.2.4.1.1.1 | Deliver Final Inventory to SCUSA SHUSA ERM | 4% | 25d | 2015-06-29 | 2015-07-31 |  | Collect Documentation | SCUSA now has only 3 inventories and completely new dates.
6 | 1.2.4.1.1.2 | Automotive Finance Material Risk Inventory Prepared | 100% | 1d | 2015-07-31 | 2015-07-31 | Ploetz/Smith |  | SCUSA now has only 3 inventories and completely new dates.
4 | 1.2.4.2 | MILESTONE: Personal Lending Material Risk Inventory | 8% | 25d | 2015-06-29 | 2015-07-31 |  |  | SCUSA now has only 3 inventories and completely new dates.
5 | 1.2.4.2.1 | TASK:Personal Lending Material Risk Inventory | 8% | 25d | 2015-06-29 | 2015-07-31 |  |  | SCUSA now has only 3 inventories and completely new dates.
6 | 1.2.4.2.1.1 | Deliver Final Inventory to SCUSA SHUSA ERM | 4% | 25d | 2015-06-29 | 2015-07-31 |  | Collect Documentation | SCUSA now has only 3 inventories and completely new dates.
6 | 1.2.4.2.1.2 | Personal Lending Material Risk Inventory Prepared | 99% | 1d | 2015-07-31 | 2015-07-31 | Ploetz/Smith |  | SCUSA now has only 3 inventories and completely new dates.
4 | 1.2.4.3 | MILESTONE: Human Resources Material Risk Inventory | 8% | 25d | 2015-06-29 | 2015-07-31 |  |  | SCUSA now has only 3 inventories and completely new dates.
5 | 1.2.4.3.1 | TASK:Human Resources Material Risk Inventory | 8% | 25d | 2015-06-29 | 2015-07-31 |  |  | SCUSA now has only 3 inventories and completely new dates.
6 | 1.2.4.3.1.1 | Deliver Final Inventory to SCUSA SHUSA ERM | 4% | 25d | 2015-06-29 | 2015-07-31 |  | Collect Documentation | SCUSA now has only 3 inventories and completely new dates.
6 | 1.2.4.3.1.2 | Human Resources Material Risk Inventory Prepared | 100% | 1d | 2015-07-31 | 2015-07-31 | Ploetz/Smith |  | SCUSA now has only 3 inventories and completely new dates.
4 | 1.2.4.4 | MILESTONE: Finance and Accounting Material Risk Inventory | 8% | 25d | 2015-06-29 | 2015-07-31 |  |  | SCUSA now has only 3 inventories and completely new dates.
5 | 1.2.4.4.1 | TASK:Finance and Accounting Material Risk Inventory | 8% | 25d | 2015-06-29 | 2015-07-31 |  |  | SCUSA now has only 3 inventories and completely new dates.
6 | 1.2.4.4.1.1 | Deliver Final Inventory to SCUSA SHUSA ERM | 4% | 25d | 2015-06-29 | 2015-07-31 |  | Collect Documentation | SCUSA now has only 3 inventories and completely new dates.
6 | 1.2.4.4.1.2 | Finance and Accounting Material Risk Inventory Prepared | 100% | 1d | 2015-07-31 | 2015-07-31 | Ploetz/Smith |  | SCUSA now has only 3 inventories and completely new dates.
4 | 1.2.4.5 | MILESTONE: Technology and Operations Material Risk Inventory | 8% | 25d | 2015-06-29 | 2015-07-31 |  |  | SCUSA now has only 3 inventories and completely new dates.
5 | 1.2.4.5.1 | TASK:Technology and Operations Material Risk Inventory | 8% | 25d | 2015-06-29 | 2015-07-31 |  |  | SCUSA now has only 3 inventories and completely new dates.
6 | 1.2.4.5.1.1 | Deliver Final Inventory to SCUSA SHUSA ERM | 4% | 25d | 2015-06-29 | 2015-07-31 |  | Collect Documentation | SCUSA now has only 3 inventories and completely new dates.
6 | 1.2.4.5.1.2 | Technology and Operations Material Risk Inventory Prepared | 100% | 1d | 2015-07-31 | 2015-07-31 | Ploetz/Smith |  | SCUSA now has only 3 inventories and completely new dates.
4 | 1.2.4.6 | MILESTONE: Legal Material Risk Inventory | 8% | 25d | 2015-06-29 | 2015-07-31 |  |  | SCUSA now has only 3 inventories and completely new dates.
5 | 1.2.4.6.1 | TASK:Legal Material Risk Inventory | 8% | 25d | 2015-06-29 | 2015-07-31 |  |  | SCUSA now has only 3 inventories and completely new dates.
6 | 1.2.4.6.1.1 | Deliver Final Inventory to SCUSA SHUSA ERM | 4% | 25d | 2015-06-29 | 2015-07-31 |  | Collect Documentation | SCUSA now has only 3 inventories and completely new dates.
6 | 1.2.4.6.1.2 | Legal Material Risk Inventory Prepared | 100% | 1d | 2015-07-31 | 2015-07-31 | Ploetz/Smith |  | SCUSA now has only 3 inventories and completely new dates.
4 | 1.2.4.7 | MILESTONE: SCUSA Aggregation Workshops (include 2 LOD challenge) | 0% | 45d | 2015-08-03 | 2015-10-02 |  |  | SCUSA now has only 3 inventories and completely new dates.
5 | 1.2.4.7.1 | TASK: Credit Risk Aggregation | 0% | 41d? | 2015-08-03 | 2015-09-28 |  |  | SCUSA now has only 3 inventories and completely new dates.
6 | 1.2.4.7.1.1 | ERM disseminates Workshop Pre-Read Materials to Risk Managers | 0% | 16d? | 2015-08-03 | 2015-08-24 |  |  | SCUSA now has only 3 inventories and completely new dates.
6 | 1.2.4.7.1.2 | ERM facilitates Aggregation and Enrichment Activities | 0% | 25d? | 2015-08-25 | 2015-09-28 |  |  | SCUSA now has only 3 inventories and completely new dates.
6 | 1.2.4.7.1.3 | Risk Manager presents inventory to level II subcommittee | 0% | 1d? | 2015-08-03 | 2015-08-03 |  |  | SCUSA now has only 3 inventories and completely new dates.
6 | 1.2.4.7.1.4 | Credit Risk Aggregation Prepared | 0% | 0d | 2015-08-03 | 2015-08-03 | Ploetz/Smith |  | SCUSA now has only 3 inventories and completely new dates.
5 | 1.2.4.7.2 | TASK: Operational Risk Material Risk Aggregation | 0% | 41d? | 2015-08-03 | 2015-09-28 |  |  | SCUSA now has only 3 inventories and completely new dates.
6 | 1.2.4.7.2.1 | ERM disseminates Workshop Pre-Read Materials to Risk Managers | 0% | 16d? | 2015-08-03 | 2015-08-24 |  |  | SCUSA now has only 3 inventories and completely new dates.
6 | 1.2.4.7.2.2 | ERM facilitates Aggregation and Enrichment Activities | 0% | 25d? | 2015-08-25 | 2015-09-28 |  |  | SCUSA now has only 3 inventories and completely new dates.
6 | 1.2.4.7.2.3 | Risk Manager presents inventory to level II subcommittee | 0% | 1d? | 2015-08-03 | 2015-08-03 |  |  | SCUSA now has only 3 inventories and completely new dates.
6 | 1.2.4.7.2.4 | Operational Risk Material Risk Aggregation Prepared | 0% | 0d | 2015-08-03 | 2015-08-03 | Ploetz/Smith |  | SCUSA now has only 3 inventories and completely new dates.
5 | 1.2.4.7.3 | TASK: Compliance Material Risk Aggregation | 0% | 41d? | 2015-08-03 | 2015-09-28 |  |  | SCUSA now has only 3 inventories and completely new dates.
6 | 1.2.4.7.3.1 | ERM disseminates Workshop Pre-Read Materials to Risk Managers | 0% | 16d? | 2015-08-03 | 2015-08-24 |  |  | SCUSA now has only 3 inventories and completely new dates.
6 | 1.2.4.7.3.2 | ERM facilitates Aggregation and Enrichment Activities | 0% | 25d? | 2015-08-25 | 2015-09-28 |  |  | SCUSA now has only 3 inventories and completely new dates.
6 | 1.2.4.7.3.3 | Risk Manager presents inventory to level II subcommittee | 0% | 1d? | 2015-08-03 | 2015-08-03 |  |  | SCUSA now has only 3 inventories and completely new dates.
6 | 1.2.4.7.3.4 | Compliance Material Risk Aggregation Prepared | 0% | 0d | 2015-08-03 | 2015-08-03 | Ploetz/Smith |  | SCUSA now has only 3 inventories and completely new dates.
5 | 1.2.4.7.4 | TASK: Model Material Risk Aggregation | 0% | 41d? | 2015-08-03 | 2015-09-28 |  |  | SCUSA now has only 3 inventories and completely new dates.
6 | 1.2.4.7.4.1 | ERM disseminates Workshop Pre-Read Materials to Risk Managers | 0% | 16d? | 2015-08-03 | 2015-08-24 |  |  | SCUSA now has only 3 inventories and completely new dates.
6 | 1.2.4.7.4.2 | ERM facilitates Aggregation and Enrichment Activities | 0% | 25d? | 2015-08-25 | 2015-09-28 |  |  | SCUSA now has only 3 inventories and completely new dates.
6 | 1.2.4.7.4.3 | Risk Manager presents inventory to level II subcommittee | 0% | 1d? | 2015-08-03 | 2015-08-03 |  |  | SCUSA now has only 3 inventories and completely new dates.
6 | 1.2.4.7.4.4 | Model Material Risk Aggregation Prepared | 0% | 0d | 2015-08-03 | 2015-08-03 | Ploetz/Smith |  | SCUSA now has only 3 inventories and completely new dates.
5 | 1.2.4.7.5 | TASK: Liquidity/Market Material Risk Aggregation | 0% | 41d? | 2015-08-03 | 2015-09-28 |  |  | SCUSA now has only 3 inventories and completely new dates.
6 | 1.2.4.7.5.1 | ERM disseminates Workshop Pre-Read Materials to Risk Managers | 0% | 16d? | 2015-08-03 | 2015-08-24 |  |  | SCUSA now has only 3 inventories and completely new dates.
6 | 1.2.4.7.5.2 | ERM facilitates Aggregation and Enrichment Activities | 0% | 25d? | 2015-08-25 | 2015-09-28 |  |  | SCUSA now has only 3 inventories and completely new dates.
6 | 1.2.4.7.5.3 | Risk Manager presents inventory to level II subcommittee | 0% | 1d? | 2015-08-03 | 2015-08-03 |  |  | SCUSA now has only 3 inventories and completely new dates.
6 | 1.2.4.7.5.4 | Liquidity/Market Material Risk Aggregation Prepared | 0% | 0d | 2015-08-03 | 2015-08-03 | Ploetz/Smith |  | SCUSA now has only 3 inventories and completely new dates.
5 | 1.2.4.7.6 | TASK: Reputational/Strategic Material Risk Aggregation | 0% | 41d? | 2015-08-03 | 2015-09-28 |  |  | SCUSA now has only 3 inventories and completely new dates.
6 | 1.2.4.7.6.1 | ERM disseminates Workshop Pre-Read Materials to Risk Managers | 0% | 16d? | 2015-08-03 | 2015-08-24 |  |  | SCUSA now has only 3 inventories and completely new dates.
6 | 1.2.4.7.6.2 | ERM facilitates Aggregation and Enrichment Workshop | 0% | 25d? | 2015-08-25 | 2015-09-28 |  |  | SCUSA now has only 3 inventories and completely new dates.
6 | 1.2.4.7.6.3 | Risk Manager presents inventory to level II subcommittee | 0% | 1d? | 2015-08-03 | 2015-08-03 |  |  | SCUSA now has only 3 inventories and completely new dates.
6 | 1.2.4.7.6.4 | Reputational/Strategic Material Risk Aggregation Prepared | 0% | 0d | 2015-08-03 | 2015-08-03 | Ploetz/Smith |  | SCUSA now has only 3 inventories and completely new dates.
4 | 1.2.4.8 | MILESTONE:Present Results to SCUSA ERMC | 0% | 48d | 2015-07-28 | 2015-10-01 | Ploetz/Smith |  | SCUSA now has only 3 inventories and completely new dates.
4 | 1.2.4.9 | MILESTONE:Present Results to SCUSA BERC | 0% | 48d | 2015-07-28 | 2015-10-01 | Ploetz/Smith |  | SCUSA now has only 3 inventories and completely new dates.
4 | 1.2.4.10 | Present SCUSA Material Risks to CCAR | 0% | 2d | 2015-10-01 | 2015-10-02 |  |  | SCUSA now has only 3 inventories and completely new dates.
4 | 1.2.4.11 | Deliver SCUSA Material Risks to CCAR and Capital Plan | 0% | 0d | 2015-10-02 | 2015-10-02 |  | CCAR
3 | 1.2.5 | DELIVERABLE: Design and execute the Material Risk Program across New York Santander Investment Securities (SIS) | 10% | 92d | 2015-05-28 | 2015-10-02 | D. Allaire
4 | 1.2.5.1 | MILESTONE:GBM-Cash Equities Brokerage Material Risk Inventory | 100% | 2d | 2015-06-29 | 2015-06-30
5 | 1.2.5.1.1 | TASK:GBM-Cash Equities Brokerage Material Risk Inventory | 100% | 2d | 2015-06-29 | 2015-06-30
6 | 1.2.5.1.1.1 | Deliver Final Inventory to SIS and SHUSA ERM | 100% | 2d | 2015-06-29 | 2015-06-30 |  | Collect Documentation
6 | 1.2.5.1.1.2 | Present inventory to ERMC | 100% | 2d | 2015-06-29 | 2015-06-30
6 | 1.2.5.1.1.3 | Cash Equities Brokerage Material Risk Inventory Prepared | 100% | 0d | 2015-06-30 | 2015-06-30 | Murphy/Khurana
4 | 1.2.5.2 | MILESTONE:GBM- Debt Underwriting Material Risk Inventory | 100% | 2d | 2015-06-29 | 2015-06-30
5 | 1.2.5.2.1 | TASK:GBM- Debt Underwriting Material Risk Inventory | 100% | 2d | 2015-06-29 | 2015-06-30
6 | 1.2.5.2.1.1 | Deliver Final Inventory to SIS and SHUSA ERM | 100% | 2d | 2015-06-29 | 2015-06-30 |  | Collect Documentation
6 | 1.2.5.2.1.2 | Present inventory to ERMC | 100% | 2d | 2015-06-29 | 2015-06-30
6 | 1.2.5.2.1.3 | Debt Underwriting Material Risk Inventory Prepared | 100% | 0d | 2015-06-30 | 2015-06-30 | Murphy/Khurana
4 | 1.2.5.3 | MILESTONE:GBM Equity Underwriting Material Risk Inventory | 100% | 2d | 2015-06-29 | 2015-06-30
5 | 1.2.5.3.1 | TASK:GBM Equity Underwriting Material Risk Inventory | 100% | 2d | 2015-06-29 | 2015-06-30
6 | 1.2.5.3.1.1 | Deliver Final Inventory to SIS and SHUSA ERM | 100% | 2d | 2015-06-29 | 2015-06-30 |  | Collect Documentation
6 | 1.2.5.3.1.2 | Present inventory to ERMC | 100% | 2d | 2015-06-29 | 2015-06-30
6 | 1.2.5.3.1.3 | Equity Underwriting Material Risk Inventory Prepared | 100% | 0d | 2015-06-30 | 2015-06-30 | Murphy/Khurana
4 | 1.2.5.4 | MILESTONE:GBM- Fixed Income/Bond TradingMaterial Risk Inventory | 100% | 2d | 2015-06-29 | 2015-06-30
5 | 1.2.5.4.1 | TASK:GBM- Fixed Income/Bond TradingMaterial Risk Inventory | 100% | 2d | 2015-06-29 | 2015-06-30
6 | 1.2.5.4.1.1 | Deliver Final Inventory to SIS and SHUSA ERM | 100% | 2d | 2015-06-29 | 2015-06-30 |  | Collect Documentation
6 | 1.2.5.4.1.2 | Present inventory to ERMC | 100% | 2d | 2015-06-29 | 2015-06-30
6 | 1.2.5.4.1.3 | Fixed Income/Bond TradingMaterial Risk Inventory Prepared | 100% | 0d | 2015-06-30 | 2015-06-30 | Murphy/Khurana
4 | 1.2.5.5 | MILESTONE:GBM - Futures Brokerage Material Risk Inventory | 100% | 2d | 2015-06-29 | 2015-06-30
5 | 1.2.5.5.1 | TASK:GBM - Futures Brokerage Material Risk Inventory | 100% | 2d | 2015-06-29 | 2015-06-30
6 | 1.2.5.5.1.1 | Deliver Final Inventory to SIS and SHUSA ERM | 100% | 2d | 2015-06-29 | 2015-06-30 |  | Collect Documentation
6 | 1.2.5.5.1.2 | Present inventory to ERMC | 100% | 2d | 2015-06-29 | 2015-06-30
6 | 1.2.5.5.1.3 | Futures Brokerage Material Risk Inventory Prepared | 100% | 0d | 2015-06-30 | 2015-06-30
4 | 1.2.5.6 | MILESTONE:GBM - Fixed Income and Equity Research Material Risk Inventory | 100% | 2d | 2015-06-29 | 2015-06-30
5 | 1.2.5.6.1 | TASK:GBM - Fixed Income and Equity Research Material Risk Inventory | 100% | 2d | 2015-06-29 | 2015-06-30
6 | 1.2.5.6.1.1 | Deliver Final Inventory to SIS and SHUSA ERM | 100% | 2d | 2015-06-29 | 2015-06-30 |  | Collect Documentation
6 | 1.2.5.6.1.2 | Present inventory to ERMC | 100% | 2d | 2015-06-29 | 2015-06-30
6 | 1.2.5.6.1.3 | Fixed Income and Equity Research Material Risk Inventory Prepared | 100% | 0d | 2015-06-30 | 2015-06-30 | Murphy/Khurana
4 | 1.2.5.7 | MILESTONE:Human Resources Material Risk Inventory | 100% | 2d | 2015-06-29 | 2015-06-30
5 | 1.2.5.7.1 | TASK:Human Resources Material Risk Inventory | 100% | 2d | 2015-06-29 | 2015-06-30
6 | 1.2.5.7.1.1 | Deliver Final Inventory to SIS and SHUSA ERM | 100% | 2d | 2015-06-29 | 2015-06-30 |  | Collect Documentation
6 | 1.2.5.7.1.2 | Present inventory to ERMC | 100% | 2d | 2015-06-29 | 2015-06-30
6 | 1.2.5.7.1.3 | Human Resources Material Risk Inventory Prepared | 100% | 0d | 2015-06-30 | 2015-06-30 | Murphy/Khurana
4 | 1.2.5.8 | MILESTONE:Finance Material Risk Inventory | 100% | 2d | 2015-06-29 | 2015-06-30
5 | 1.2.5.8.1 | TASK:Finance Material Risk Inventory | 100% | 2d | 2015-06-29 | 2015-06-30
6 | 1.2.5.8.1.1 | Deliver Final Inventory to SIS and SHUSA ERM | 100% | 2d | 2015-06-29 | 2015-06-30 |  | Collect Documentation
6 | 1.2.5.8.1.2 | Present inventory to ERMC | 100% | 2d | 2015-06-29 | 2015-06-30
6 | 1.2.5.8.1.3 | Finance Material Risk Inventory Prepared | 100% | 0d | 2015-06-30 | 2015-06-30 | Murphy/Khurana
4 | 1.2.5.9 | MILESTONE:Technology and Operations Material Risk Inventory | 100% | 2d | 2015-06-29 | 2015-06-30
5 | 1.2.5.9.1 | TASK:Technology and Operations Material Risk Inventory | 100% | 2d | 2015-06-29 | 2015-06-30
6 | 1.2.5.9.1.1 | Deliver Final Inventory to SIS and SHUSA ERM | 100% | 2d | 2015-06-29 | 2015-06-30 |  | Collect Documentation
6 | 1.2.5.9.1.2 | Present inventory to ERMC | 100% | 2d | 2015-06-29 | 2015-06-30
6 | 1.2.5.9.1.3 | Technology and Operations Material Risk Inventory Prepared | 100% | 0d | 2015-06-30 | 2015-06-30 | Murphy/Khurana
4 | 1.2.5.10 | MILESTONE:Legal Material Risk Inventory | 100% | 2d | 2015-06-29 | 2015-06-30
5 | 1.2.5.10.1 | TASK:Legal Material Risk Inventory | 100% | 2d | 2015-06-29 | 2015-06-30
6 | 1.2.5.10.1.1 | Deliver Final Inventory to SIS and SHUSA ERM | 100% | 2d | 2015-06-29 | 2015-06-30 |  | Collect Documentation
6 | 1.2.5.10.1.2 | Present inventory to ERMC | 100% | 2d | 2015-06-29 | 2015-06-30
6 | 1.2.5.10.1.3 | Legal Material Risk Inventory Prepared | 100% | 0d | 2015-06-30 | 2015-06-30 | Murphy/Khurana
4 | 1.2.5.11 | MILESTONE: Hold NY SIS Aggregation Workshops (include 2nd LOD challenge) | 0% | 45d | 2015-08-03 | 2015-10-02
5 | 1.2.5.11.1 | TASK: Credit Risk Aggregation |  | 41d? | 2015-08-03 | 2015-09-28
6 | 1.2.5.11.1.1 | ERM disseminates Workshop Pre-Read Materials to Risk Managers | 100% | 16d? | 2015-08-03 | 2015-08-24 |  |  | Dates & task names have changed and need to be updated
6 | 1.2.5.11.1.2 | ERM facilitates Aggregation and Enrichment Activities | 100% | 25d? | 2015-08-25 | 2015-09-28 |  |  | Dates & task names have changed and need to be updated
6 | 1.2.5.11.1.3 | Risk Manager presents inventory to level II subcommittee | 50% | 1d? | 2015-08-03 | 2015-08-03 |  |  | Dates & task names have changed and need to be updated
6 | 1.2.5.11.1.4 | Credit Risk Aggregation Prepared | 50% | 0d | 2015-08-03 | 2015-08-03 | Murphy/Khurana |  | Dates & task names have changed and need to be updated
5 | 1.2.5.11.2 | TASK: Operational Risk Material Risk Aggregation | 0% | 41d? | 2015-08-03 | 2015-09-28 |  |  | Dates & task names have changed and need to be updated
6 | 1.2.5.11.2.1 | ERM disseminates Workshop Pre-Read Materials to Risk Managers | 100% | 16d? | 2015-08-03 | 2015-08-24 |  |  | Dates & task names have changed and need to be updated
6 | 1.2.5.11.2.2 | ERM facilitates Aggregation and Enrichment Activities | 100% | 25d? | 2015-08-25 | 2015-09-28 |  |  | Dates & task names have changed and need to be updated
6 | 1.2.5.11.2.3 | Risk Manager presents inventory to level II subcommittee | 50% | 1d? | 2015-08-03 | 2015-08-03 |  |  | Dates & task names have changed and need to be updated
6 | 1.2.5.11.2.4 | Operational Risk Material Risk Aggregation Prepared | 50% | 0d | 2015-08-03 | 2015-08-03 | Murphy/Khurana |  | Dates & task names have changed and need to be updated
5 | 1.2.5.11.3 | TASK: Compliance Material Risk Aggregation | 0% | 41d? | 2015-08-03 | 2015-09-28 |  |  | Dates & task names have changed and need to be updated
6 | 1.2.5.11.3.1 | ERM disseminates Workshop Pre-Read Materials to Risk Managers | 100% | 16d? | 2015-08-03 | 2015-08-24 |  |  | Dates & task names have changed and need to be updated
6 | 1.2.5.11.3.2 | ERM facilitates Aggregation and Enrichment Activities | 100% | 25d? | 2015-08-25 | 2015-09-28 |  |  | Dates & task names have changed and need to be updated
6 | 1.2.5.11.3.3 | Risk Manager presents inventory to level II subcommittee | 50% | 1d? | 2015-08-03 | 2015-08-03 |  |  | Dates & task names have changed and need to be updated
6 | 1.2.5.11.3.4 | Compliance Material Risk Aggregation Prepared | 50% | 0d | 2015-08-03 | 2015-08-03 | Murphy/Khurana |  | Dates & task names have changed and need to be updated
5 | 1.2.5.11.4 | TASK: Model Material Risk Aggregation | 0% | 41d? | 2015-08-03 | 2015-09-28 |  |  | Dates & task names have changed and need to be updated
6 | 1.2.5.11.4.1 | ERM disseminates Workshop Pre-Read Materials to Risk Managers | 100% | 16d? | 2015-08-03 | 2015-08-24 |  |  | Dates & task names have changed and need to be updated
6 | 1.2.5.11.4.2 | ERM facilitates Aggregation and Enrichment Workshop | 100% | 25d? | 2015-08-25 | 2015-09-28 |  |  | Dates & task names have changed and need to be updated
6 | 1.2.5.11.4.3 | Risk Manager presents inventory to level II subcommittee | 50% | 1d? | 2015-08-03 | 2015-08-03 |  |  | Dates & task names have changed and need to be updated
6 | 1.2.5.11.4.4 | Model Material Risk Aggregation Prepared | 50% | 0d | 2015-08-03 | 2015-08-03 | Murphy/Khurana |  | Dates & task names have changed and need to be updated
5 | 1.2.5.11.5 | TASK: Liquidity/Market Material Risk Aggregation | 0% | 41d? | 2015-08-03 | 2015-09-28 |  |  | Dates & task names have changed and need to be updated
6 | 1.2.5.11.5.1 | ERM disseminates Workshop Pre-Read Materials to Risk Managers | 100% | 16d? | 2015-08-03 | 2015-08-24 |  |  | Dates & task names have changed and need to be updated
6 | 1.2.5.11.5.2 | ERM facilitates Aggregation and Enrichment Activities | 100% | 25d? | 2015-08-25 | 2015-09-28 |  |  | Dates & task names have changed and need to be updated
6 | 1.2.5.11.5.3 | Risk Manager presents inventory to level II subcommittee | 50% | 1d? | 2015-08-03 | 2015-08-03 |  |  | Dates & task names have changed and need to be updated
6 | 1.2.5.11.5.4 | Liquidity/Market Material Risk Aggregation Prepared | 50% | 0d | 2015-08-03 | 2015-08-03 | Murphy/Khurana |  | Dates & task names have changed and need to be updated
5 | 1.2.5.11.6 | TASK: Reputational/Strategic Material Risk Aggregation | 0% | 41d? | 2015-08-03 | 2015-09-28 |  |  | Dates & task names have changed and need to be updated
6 | 1.2.5.11.6.1 | ERM disseminates Workshop Pre-Read Materials to Risk Managers | 100% | 16d? | 2015-08-03 | 2015-08-24 |  |  | Dates & task names have changed and need to be updated
6 | 1.2.5.11.6.2 | ERM facilitates Aggregation and Enrichment Activities | 100% | 25d? | 2015-08-25 | 2015-09-28 |  |  | Dates & task names have changed and need to be updated
6 | 1.2.5.11.6.3 | Risk Manager presents inventory to level II subcommittee | 50% | 1d? | 2015-08-03 | 2015-08-03 |  |  | Dates & task names have changed and need to be updated
6 | 1.2.5.11.6.4 | Reputational/Strategic Material Risk Aggregation Prepared | 50% | 0d | 2015-08-03 | 2015-08-03 | Murphy/Khurana
4 | 1.2.5.12 | MILESTONE:Present Results to NY SIS ERMC | 0% | 48d | 2015-07-28 | 2015-10-01 | Murphy/Khurana
4 | 1.2.5.13 | MILESTONE:Present Results to NY SIS BERC | 0% | 48d | 2015-07-28 | 2015-10-01 | Murphy/Khurana
4 | 1.2.5.14 | Present NY SIS Material Risks to CCAR | 0% | 2d | 2015-10-01 | 2015-10-02
4 | 1.2.5.15 | Deliver NY SIS Material Risks to CCAR and Capital Plan | 0% | 0d | 2015-10-02 | 2015-10-02 |  | CCAR
3 | 1.2.6 | DELIVERABLE: Design and execute the Material Risk Program across Puerto Rico | 89% | 92d | 2015-05-28 | 2015-10-02 | D. Allaire
4 | 1.2.6.1 | MILESTONE:Retail Banking Material Risk Inventory | 95% | 25d | 2015-06-29 | 2015-07-31
5 | 1.2.6.1.1 | TASK: Personal Loans Banking Material Risk Inventory | 100% | 25d | 2015-06-29 | 2015-07-31
6 | 1.2.6.1.1.1 | Deliver Final Inventory to PR and SHUSA ERM | 100% | 25d | 2015-06-29 | 2015-07-31 |  | Collect Documentation
6 | 1.2.6.1.1.2 | Personal Loans Banking Material Risk Inventory Prepared | 100% | 0d | 2015-07-31 | 2015-07-31 | Jurado/Fabricio
5 | 1.2.6.1.2 | TASK: Small Business Banking Material Risk Inventory | 100% | 25d | 2015-06-29 | 2015-07-31
6 | 1.2.6.1.2.1 | Deliver Final Inventory to PR and SHUSA ERM | 100% | 25d | 2015-06-29 | 2015-07-31 |  | Collect Documentation
6 | 1.2.6.1.2.2 | Small Business Banking Material Risk Inventory Prepared | 100% | 1d | 2015-07-31 | 2015-07-31 | Jurado/Fabricio
5 | 1.2.6.1.3 | TASK: Santander Insurance Agency Material Risk Inventory | 100% | 25d | 2015-06-29 | 2015-07-31
6 | 1.2.6.1.3.1 | Deliver Final Inventory to PR and SHUSA ERM | 100% | 25d | 2015-06-29 | 2015-07-31 |  | Collect Documentation
6 | 1.2.6.1.3.2 | Santander Insurance Agency Material Risk Inventory Prepared | 100% | 0d | 2015-07-31 | 2015-07-31 | Jurado/Fabricio
5 | 1.2.6.1.4 | TASK: Credit Cards Material Risk Inventory | 100% | 25d | 2015-06-29 | 2015-07-31
6 | 1.2.6.1.4.1 | Deliver Final Inventory to PR and SHUSA ERM | 100% | 25d | 2015-06-29 | 2015-07-31 |  | Collect Documentation
6 | 1.2.6.1.4.2 | Credit Cards Material Risk Inventory Prepared | 100% | 1d | 2015-07-31 | 2015-07-31 | Jurado/Fabricio
5 | 1.2.6.1.5 | TASK: Mortgages Material Risk Inventory | 100% | 25d | 2015-06-29 | 2015-07-31 |  |  | Inventory received, Awaiting approval 7/31, has been escalated
6 | 1.2.6.1.5.1 | Deliver Final Inventory to PR and SHUSA ERM | 100% | 25d | 2015-06-29 | 2015-07-31 |  | Collect Documentation | Inventory received, Awaiting approval 7/31, has been escalated
6 | 1.2.6.1.5.2 | Mortgages Material Risk Inventory Prepared | 100% | 1d | 2015-07-31 | 2015-07-31 | Jurado/Fabricio |  | Inventory received, Awaiting approval 7/31, has been escalated
4 | 1.2.6.2 | MILESTONE:Global Banking/Commercial Banking and CRE/Speciality and Gov't Banking Material Risk Inventory | 100% | 25d | 2015-06-29 | 2015-07-31
5 | 1.2.6.2.1 | TASK: GBM Material Risk Inventory | 100% | 25d | 2015-06-29 | 2015-07-31
6 | 1.2.6.2.1.1 | Deliver Final Inventory to PR and SHUSA ERM | 100% | 25d | 2015-06-29 | 2015-07-31 |  | Collect Documentation
6 | 1.2.6.2.1.2 | GBM Material Risk Inventory Prepared | 100% | 0d | 2015-07-31 | 2015-07-31 | Jurado/Fabricio
5 | 1.2.6.2.2 | TASK: Enterprise Material Risk Inventory | 100% | 25d | 2015-06-29 | 2015-07-31
6 | 1.2.6.2.2.1 | Deliver Final Inventory to PR and SHUSA ERM | 100% | 25d | 2015-06-29 | 2015-07-31 |  | Collect Documentation
6 | 1.2.6.2.2.2 | Enterprise Material Risk Inventory Prepared | 100% | 0d | 2015-07-31 | 2015-07-31 | Jurado/Fabricio
5 | 1.2.6.2.3 | TASK: Institutional/Public Sector Material Risk Inventory | 100% | 25d | 2015-06-29 | 2015-07-31
6 | 1.2.6.2.3.1 | Deliver Final Inventory to PR and SHUSA ERM | 100% | 25d | 2015-06-29 | 2015-07-31 |  | Collect Documentation
6 | 1.2.6.2.3.2 | Institutional/Public Sector Material Risk Inventory Prepared | 100% | 0d | 2015-07-31 | 2015-07-31 | Jurado/Fabricio
4 | 1.2.6.3 | MILESTONE:Global Banking/Commercial Banking/CRE & Speciality: Create Global Banking Material Risk Inventory | 100% | 47d | 2015-05-28 | 2015-07-31
5 | 1.2.6.3.1 | TASK:Global Banking/Commercial Banking/CRE & Speciality: Create Global Banking Material Risk Inventory | 100% | 47d | 2015-05-28 | 2015-07-31
6 | 1.2.6.3.1.1 | Create Segment Material Risk Inventory (Aggregation) | 100% | 47d | 2015-05-28 | 2015-07-31 |  | Collect Documentation
6 | 1.2.6.3.1.2 | Segment head presents inventory to ERMC | 100% | 25d | 2015-06-29 | 2015-07-31
6 | 1.2.6.3.1.3 | Global Banking Material Risk Inventory Prepared | 100% | 0d | 2015-07-31 | 2015-07-31 | Jurado/Fabricio
4 | 1.2.6.4 | MILESTONE:Mortgage Servicing Material Risk Inventory | 100% | 25d | 2015-06-29 | 2015-07-31
5 | 1.2.6.4.1 | TASK:Mortgage Servicing Material Risk Inventory | 100% | 25d | 2015-06-29 | 2015-07-31
6 | 1.2.6.4.1.1 | Deliver Final Inventory to PR and SHUSA ERM | 100% | 25d | 2015-06-29 | 2015-07-31 |  | Collect Documentation
6 | 1.2.6.4.1.2 | Present inventory to ERMC | 100% | 25d | 2015-06-29 | 2015-07-31
6 | 1.2.6.4.1.3 | Mortgage Servicing Material Risk Inventory Prepared | 100% | 0d | 2015-07-31 | 2015-07-31 | Jurado/Fabricio
4 | 1.2.6.5 | MILESTONE:Investment Services Material Risk Inventory | 95% | 25d | 2015-06-29 | 2015-07-31 |  |  | Inventory received, Awaiting approval 7/31, has been escalated
5 | 1.2.6.5.1 | TASK:Investment Services Material Risk Inventory | 95% | 25d | 2015-06-29 | 2015-07-31 |  |  | Inventory received, Awaiting approval 7/31, has been escalated
6 | 1.2.6.5.1.1 | Deliver Final Inventory to PR and SHUSA ERM | 95% | 25d | 2015-06-29 | 2015-07-31 |  | Collect Documentation | Inventory received, Awaiting approval 7/31, has been escalated
6 | 1.2.6.5.1.2 | Present inventory to ERMC | 95% | 25d | 2015-06-29 | 2015-07-31 |  |  | Inventory received, Awaiting approval 7/31, has been escalated
6 | 1.2.6.5.1.3 | Investment Services Material Risk Inventory Prepared | 95% | 0d | 2015-07-31 | 2015-07-31 | Jurado/Fabricio |  | Inventory received, Awaiting approval 7/31, has been escalated
4 | 1.2.6.6 | MILESTONE:Trust Material Risk Inventory | 100% | 25d | 2015-06-29 | 2015-07-31
5 | 1.2.6.6.1 | TASK:Trust Material Risk Inventory | 100% | 25d | 2015-06-29 | 2015-07-31
6 | 1.2.6.6.1.1 | Deliver Final Inventory to PR and SHUSA ERM | 100% | 25d | 2015-06-29 | 2015-07-31 |  | Collect Documentation
6 | 1.2.6.6.1.2 | Present inventory to ERMC | 100% | 25d | 2015-06-29 | 2015-07-31
6 | 1.2.6.6.1.3 | Trust Material Risk Inventory Prepared | 100% | 0d | 2015-07-31 | 2015-07-31 | Jurado/Fabricio
4 | 1.2.6.7 | MILESTONE:Pension Plan Material Risk Inventory | 95% | 25d | 2015-06-29 | 2015-07-31 |  |  | Inventory received, Awaiting approval 7/31, has been escalated
5 | 1.2.6.7.1 | TASK:Pension Plan Material Risk Inventory | 95% | 25d | 2015-06-29 | 2015-07-31 |  |  | Inventory received, Awaiting approval 7/31, has been escalated
6 | 1.2.6.7.1.1 | Deliver Final Inventory to PR and SHUSA ERM | 95% | 25d | 2015-06-29 | 2015-07-31 |  | Collect Documentation | Inventory received, Awaiting approval 7/31, has been escalated
6 | 1.2.6.7.1.2 | Present inventory to ERMC | 95% | 25d | 2015-06-29 | 2015-07-31 |  |  | Inventory received, Awaiting approval 7/31, has been escalated
6 | 1.2.6.7.1.3 | Pension Plan Material Risk Inventory Prepared | 95% | 0d | 2015-07-31 | 2015-07-31 | Jurado/Fabricio |  | Inventory received, Awaiting approval 7/31, has been escalated
4 | 1.2.6.8 | MILESTONE:Foreign Accounts Material Risk Inventory | 95% | 25d | 2015-06-29 | 2015-07-31 |  |  | Inventory received, Awaiting approval 7/31, has been escalated
5 | 1.2.6.8.1 | TASK:Foreign Accounts Material Risk Inventory | 95% | 25d | 2015-06-29 | 2015-07-31 |  |  | Inventory received, Awaiting approval 7/31, has been escalated
6 | 1.2.6.8.1.1 | Deliver Final Inventory to PR and SHUSA ERM | 95% | 25d | 2015-06-29 | 2015-07-31 |  | Collect Documentation | Inventory received, Awaiting approval 7/31, has been escalated
6 | 1.2.6.8.1.2 | Present inventory to ERMC | 95% | 25d | 2015-06-29 | 2015-07-31 |  |  | Inventory received, Awaiting approval 7/31, has been escalated
6 | 1.2.6.8.1.3 | Foreign Accounts Material Risk Inventory Prepared | 95% | 1d | 2015-07-31 | 2015-07-31 | Jurado/Fabricio |  | Inventory received, Awaiting approval 7/31, has been escalated
4 | 1.2.6.9 | MILESTONE:Human Resources Material Risk Inventory | N/A | 47d | 2015-05-28 | 2015-07-31 |  |  | Inventory received, Awaiting approval 7/31, has been escalated
5 | 1.2.6.9.1 | TASK:Human Resources Material Risk Inventory | N/A | 47d | 2015-05-28 | 2015-07-31 |  |  | Inventory received, Awaiting approval 7/31, has been escalated
6 | 1.2.6.9.1.1 | Create risk Inventory | N/A | 38d | 2015-05-28 | 2015-07-20
6 | 1.2.6.9.1.2 | Deliver Final Inventory to PR and SHUSA ERM | N/A | 25d | 2015-06-29 | 2015-07-31 |  | Updated from file 0715. Collect Documentation | HR and T&O inventories not performed in PR. These tasks should be removed/flagged out.
6 | 1.2.6.9.1.3 | Present inventory to ERMC | N/A | 25d | 2015-06-29 | 2015-07-31 |  | Updated from file 0715 | HR and T&O inventories not performed in PR. These tasks should be removed/flagged out.
6 | 1.2.6.9.1.4 | Human Resources Material Risk Inventory Prepared | N/A | 0d | 2015-07-31 | 2015-07-31 | Jurado/Fabricio | Updated from file 0715 | HR and T&O inventories not performed in PR. These tasks should be removed/flagged out.
4 | 1.2.6.10 | MILESTONE:Technology and Operations Material Risk Inventory | N/A | 25d | 2015-06-29 | 2015-07-31 |  | Updated from file 0715 | HR and T&O inventories not performed in PR. These tasks should be removed/flagged out.
5 | 1.2.6.10.1 | TASK:Technology and Operations Material Risk Inventory | N/A | 25d | 2015-06-29 | 2015-07-31 |  | Updated from file 0715 | HR and T&O inventories not performed in PR. These tasks should be removed/flagged out.
6 | 1.2.6.10.1.1 | Deliver Final Inventory to PR and SHUSA ERM | N/A | 25d | 2015-06-29 | 2015-07-31 |  | Updated from file 0715. Collect Documentation | HR and T&O inventories not performed in PR. These tasks should be removed/flagged out.
6 | 1.2.6.10.1.2 | Present inventory to ERMC | N/A | 25d | 2015-06-29 | 2015-07-31 |  | Updated from file 0715 | HR and T&O inventories not performed in PR. These tasks should be removed/flagged out.
6 | 1.2.6.10.1.3 | Technology and Operations Material Risk Inventory Prepared | N/A | 0d | 2015-07-31 | 2015-07-31 | Jurado/Fabricio | Updated from file 0715 | HR and T&O inventories not performed in PR. These tasks should be removed/flagged out.
4 | 1.2.6.11 | MILESTONE:Legal Material Risk Inventory | N/A | 25d | 2015-06-29 | 2015-07-31 |  | Updated from file 0715 | HR and T&O inventories not performed in PR. These tasks should be removed/flagged out.
5 | 1.2.6.11.1 | TASK:Legal Material Risk Inventory | N/A | 25d | 2015-06-29 | 2015-07-31 |  | Updated from file 0715 | HR and T&O inventories not performed in PR. These tasks should be removed/flagged out.
6 | 1.2.6.11.1.1 | Deliver Final Inventory to PR and SHUSA ERM | N/A | 25d | 2015-06-29 | 2015-07-31 |  | Updated from file 0715. Collect Documentation | HR and T&O inventories not performed in PR. These tasks should be removed/flagged out.
6 | 1.2.6.11.1.2 | Present inventory to ERMC | N/A | 25d | 2015-06-29 | 2015-07-31 |  | Updated from file 0715 | HR and T&O inventories not performed in PR. These tasks should be removed/flagged out.
6 | 1.2.6.11.1.3 | Legal Material Risk Inventory Prepared | N/A | 0d | 2015-07-31 | 2015-07-31 | Jurado/Fabricio | Updated from file 0715 | HR and T&O inventories not performed in PR. These tasks should be removed/flagged out.
4 | 1.2.6.12 | MILESTONE:Finance Material Risk Inventory | 100% | 25d | 2015-06-29 | 2015-07-31
5 | 1.2.6.12.1 | TASK:Finance Material Risk Inventory | 100% | 25d | 2015-06-29 | 2015-07-31
6 | 1.2.6.12.1.1 | Deliver Final Inventory to PR and SHUSA ERM | 100% | 25d | 2015-06-29 | 2015-07-31 |  | Collect Documentation
6 | 1.2.6.12.1.2 | Present inventory to ERMC | 100% | 25d | 2015-06-29 | 2015-07-31
6 | 1.2.6.12.1.3 | Finance Material Risk Inventory Prepared | 100% | 0d | 2015-07-31 | 2015-07-31 | Jurado/Fabricio
4 | 1.2.6.13 | MILESTONE:SFS - Island Finance Material Risk Inventory | 100% | 25d | 2015-06-29 | 2015-07-31
5 | 1.2.6.13.1 | TASK:SFS - Island Finance Material Risk Inventory | 100% | 25d | 2015-06-29 | 2015-07-31
6 | 1.2.6.13.1.1 | Deliver Final Inventory to PR and SHUSA ERM | 100% | 25d | 2015-06-29 | 2015-07-31 |  | Collect Documentation
6 | 1.2.6.13.1.2 | Present inventory to ERMC | 100% | 25d | 2015-06-29 | 2015-07-31
6 | 1.2.6.13.1.3 | SFS - Island Finance Material Risk Inventory Prepared | 100% | 0d | 2015-07-31 | 2015-07-31 | Jurado/Fabricio
4 | 1.2.6.14 | MILESTONE:SFS - Special Assets Material Risk Inventory | 100% | 25d | 2015-06-29 | 2015-07-31
5 | 1.2.6.14.1 | TASK:SFS - Special Assets Material Risk Inventory | 100% | 25d | 2015-06-29 | 2015-07-31
6 | 1.2.6.14.1.1 | Deliver Final Inventory to PR and SHUSA ERM | 100% | 25d | 2015-06-29 | 2015-07-31 |  | Collect Documentation
6 | 1.2.6.14.1.2 | Present inventory to ERMC | 100% | 25d | 2015-06-29 | 2015-07-31
6 | 1.2.6.14.1.3 | SFS - Special Assets Material Risk Inventory Prepared | 100% | 0d | 2015-07-31 | 2015-07-31 | Jurado/Fabricio
4 | 1.2.6.15 | MILESTONE:Santander Overseas Bank - GBM Material Risk Inventory | 100% | 25d | 2015-06-29 | 2015-07-31
5 | 1.2.6.15.1 | TASK:Santander Overseas Bank - GBM Material Risk Inventory | 100% | 25d | 2015-06-29 | 2015-07-31
6 | 1.2.6.15.1.1 | Deliver Final Inventory to PR and SHUSA ERM | 100% | 25d | 2015-06-29 | 2015-07-31 |  | Collect Documentation
6 | 1.2.6.15.1.2 | Present inventory to ERMC | 100% | 25d | 2015-06-29 | 2015-07-31
6 | 1.2.6.15.1.3 | Santander Overseas Bank - GBM Material Risk Inventory Prepared | 100% | 1d | 2015-07-31 | 2015-07-31 | Jurado/Fabricio
4 | 1.2.6.16 | MILESTONE: Hold Puerto Rico Aggregation Workshops (include 2nd LOD challenge) | 98% | 45d | 2015-08-03 | 2015-10-02 |  |  | Dates & task names have changed and need to be updated
5 | 1.2.6.16.1 | TASK: Credit Risk Aggregation | 98% | 41d? | 2015-08-03 | 2015-09-28 |  |  | Dates & task names have changed and need to be updated
6 | 1.2.6.16.1.1 | ERM disseminates Workshop Pre-Read Materials to Risk Managers | 50% | 16d? | 2015-08-03 | 2015-08-24 |  |  | Dates & task names have changed and need to be updated
6 | 1.2.6.16.1.2 | ERM facilitates Aggregation and Enrichment Activities | 50% | 25d? | 2015-08-25 | 2015-09-28 |  |  | Dates & task names have changed and need to be updated
6 | 1.2.6.16.1.3 | Risk Manager presents inventory to level II subcommittee | 0% | 1d? | 2015-08-03 | 2015-08-03 |  |  | Dates & task names have changed and need to be updated
6 | 1.2.6.16.1.4 | Credit Risk Aggregation Prepared | 0% | 0d | 2015-08-03 | 2015-08-03 | Jurado/Fabricio |  | Dates & task names have changed and need to be updated
5 | 1.2.6.16.2 | TASK: Operational Risk Material Risk Aggregation | 98% | 41d? | 2015-08-03 | 2015-09-28 |  |  | Dates & task names have changed and need to be updated
6 | 1.2.6.16.2.1 | ERM disseminates Workshop Pre-Read Materials to Risk Managers | 50% | 16d? | 2015-08-03 | 2015-08-24 |  |  | Dates & task names have changed and need to be updated
6 | 1.2.6.16.2.2 | ERM facilitates Aggregation and Enrichment Activities | 50% | 25d? | 2015-08-25 | 2015-09-28 |  |  | Dates & task names have changed and need to be updated
6 | 1.2.6.16.2.3 | Risk Manager presents inventory to level II subcommittee | 0% | 1d? | 2015-08-03 | 2015-08-03 |  |  | Dates & task names have changed and need to be updated
6 | 1.2.6.16.2.4 | Operational Risk Material Risk Aggregation Prepared | 0% | 0d | 2015-08-03 | 2015-08-03 | Jurado/Fabricio |  | Dates & task names have changed and need to be updated
5 | 1.2.6.16.3 | TASK: Compliance Material Risk Aggregation | 98% | 41d? | 2015-08-03 | 2015-09-28 |  |  | Dates & task names have changed and need to be updated
6 | 1.2.6.16.3.1 | ERM disseminates Workshop Pre-Read Materials to Risk Managers | 50% | 16d? | 2015-08-03 | 2015-08-24 |  |  | Dates & task names have changed and need to be updated
6 | 1.2.6.16.3.2 | ERM facilitates Aggregation and Enrichment Workshop | 50% | 25d? | 2015-08-25 | 2015-09-28 |  |  | Dates & task names have changed and need to be updated
6 | 1.2.6.16.3.3 | Risk Manager presents inventory to level II subcommittee | 0% | 1d? | 2015-08-03 | 2015-08-03 |  |  | Dates & task names have changed and need to be updated
6 | 1.2.6.16.3.4 | Compliance Material Risk Aggregation Prepared | 0% | 0d | 2015-08-03 | 2015-08-03 | Jurado/Fabricio |  | Dates & task names have changed and need to be updated
5 | 1.2.6.16.4 | TASK: Model Material Risk Aggregation | 98% | 41d? | 2015-08-03 | 2015-09-28 |  |  | Dates & task names have changed and need to be updated
6 | 1.2.6.16.4.1 | ERM disseminates Workshop Pre-Read Materials to Risk Managers | 50% | 16d? | 2015-08-03 | 2015-08-24 |  |  | Dates & task names have changed and need to be updated
6 | 1.2.6.16.4.2 | ERM facilitates Aggregation and Enrichment Activities | 50% | 25d? | 2015-08-25 | 2015-09-28 |  |  | Dates & task names have changed and need to be updated
6 | 1.2.6.16.4.3 | Risk Manager presents inventory to level II subcommittee | 0% | 1d? | 2015-08-03 | 2015-08-03 |  |  | Dates & task names have changed and need to be updated
6 | 1.2.6.16.4.4 | Model Material Risk Aggregation Prepared | 0% | 0d | 2015-08-03 | 2015-08-03 | Jurado/Fabricio |  | Dates & task names have changed and need to be updated
5 | 1.2.6.16.5 | TASK: Liquidity/Market Material Risk Aggregation | 98% | 41d? | 2015-08-03 | 2015-09-28 |  |  | Dates & task names have changed and need to be updated
6 | 1.2.6.16.5.1 | ERM disseminates Workshop Pre-Read Materials to Risk Managers | 50% | 16d? | 2015-08-03 | 2015-08-24 |  |  | Dates & task names have changed and need to be updated
6 | 1.2.6.16.5.2 | ERM facilitates Aggregation and Enrichment Activities | 50% | 25d? | 2015-08-25 | 2015-09-28 |  |  | Dates & task names have changed and need to be updated
6 | 1.2.6.16.5.3 | Risk Manager presents inventory to level II subcommittee | 0% | 1d? | 2015-08-03 | 2015-08-03 |  |  | Dates & task names have changed and need to be updated
6 | 1.2.6.16.5.4 | Liquidity/Market Material Risk Aggregation Prepared | 0% | 0d | 2015-08-03 | 2015-08-03 | Jurado/Fabricio |  | Dates & task names have changed and need to be updated
5 | 1.2.6.16.6 | TASK: Reputational/Strategic Material Risk Aggregation | 98% | 41d? | 2015-08-03 | 2015-09-28 |  |  | Dates & task names have changed and need to be updated
6 | 1.2.6.16.6.1 | ERM disseminates Workshop Pre-Read Materials to Risk Managers | 50% | 16d? | 2015-08-03 | 2015-08-24 |  |  | Dates & task names have changed and need to be updated
6 | 1.2.6.16.6.2 | ERM facilitates Aggregation and Enrichment Workshop | 50% | 25d? | 2015-08-25 | 2015-09-28
6 | 1.2.6.16.6.3 | Risk Manager presents inventory to level II subcommittee | 0% | 1d? | 2015-08-03 | 2015-08-03
6 | 1.2.6.16.6.4 | Reputational/Strategic Material Risk Aggregation Prepared | 0% | 0d | 2015-08-03 | 2015-08-03 | Jurado/Fabricio
4 | 1.2.6.17 | MILESTONE:Present Results to PR Santander Bancorp ERMC | 50% | 48d | 2015-07-28 | 2015-10-01 | Jurado/Fabricio
4 | 1.2.6.18 | MILESTONE:Present Results to PR Santander Bancorp BERC | 50% | 48d | 2015-07-28 | 2015-10-01 | Jurado/Fabricio
4 | 1.2.6.19 | Present Puerto Rico Material Risks to CCAR | 0% | 2d | 2015-10-01 | 2015-10-02
4 | 1.2.6.20 | Deliver Puerto Rico Material Risks to CCAR and Capital Plan | 0% | 0d | 2015-10-02 | 2015-10-02 |  | CCAR
3 | 1.2.7 | DELIVERABLE: Design and execute the Material Risk Program across Miami | 2% | 92d | 2015-05-28 | 2015-10-02 | D. Allaire
4 | 1.2.7.1 | MILESTONE:Private Banking Material Risk Inventory | 100% | 2d | 2015-06-29 | 2015-06-30
5 | 1.2.7.1.1 | TASK:Private Banking Material Risk Inventory | 100% | 2d | 2015-06-29 | 2015-06-30
6 | 1.2.7.1.1.1 | Deliver Final Inventory to Miami and SHUSA ERM | 100% | 2d | 2015-06-29 | 2015-06-30 |  | Collect Documentation
6 | 1.2.7.1.1.2 | Present inventory to ERMC | 100% | 2d | 2015-06-29 | 2015-06-30
6 | 1.2.7.1.1.3 | Private Banking Material Risk Inventory Prepared | 100% | 0d | 2015-06-30 | 2015-06-30 | Prado/Madargia
4 | 1.2.7.2 | MILESTONE:Personal Lending Material Risk Inventory | 100% | 2d | 2015-06-29 | 2015-06-30
5 | 1.2.7.2.1 | TASK:Personal Lending Material Risk Inventory | 100% | 2d | 2015-06-29 | 2015-06-30
6 | 1.2.7.2.1.1 | Deliver Final Inventory to Miami and SHUSA ERM | 100% | 2d | 2015-06-29 | 2015-06-30 |  | Collect Documentation
6 | 1.2.7.2.1.2 | Present inventory to ERMC | 100% | 2d | 2015-06-29 | 2015-06-30
6 | 1.2.7.2.1.3 | Personal Lending Material Risk Inventory Prepared | 100% | 0d | 2015-06-30 | 2015-06-30 | Prado/Madargia
4 | 1.2.7.3 | MILESTONE: Hold Miami Aggregation Workshops (include 2 LOD challenge) | 0% | 45d | 2015-08-03 | 2015-10-02
5 | 1.2.7.3.1 | TASK: Credit Risk Aggregation | 0% | 41d? | 2015-08-03 | 2015-09-28
6 | 1.2.7.3.1.1 | ERM disseminates Workshop Pre-Read Materials to Risk Managers | 100% | 16d? | 2015-08-03 | 2015-08-24 |  |  | Dates have changed and need to be updated
6 | 1.2.7.3.1.2 | ERM facilitates Aggregation and Enrichment Activities | 100% | 25d? | 2015-08-25 | 2015-09-28 |  |  | Dates have changed and need to be updated
6 | 1.2.7.3.1.3 | Risk Manager presents inventory to level II subcommittee | 50% | 1d? | 2015-08-03 | 2015-08-03 |  |  | Dates have changed and need to be updated
6 | 1.2.7.3.1.4 | Credit Risk Aggregation Prepared | 50% | 0d | 2015-08-03 | 2015-08-03 | Prado/Madargia |  | Dates have changed and need to be updated
5 | 1.2.7.3.2 | TASK: Operational Risk Material Risk Aggregation | 0% | 41d? | 2015-08-03 | 2015-09-28 |  |  | Dates have changed and need to be updated
6 | 1.2.7.3.2.1 | ERM disseminates Workshop Pre-Read Materials to Risk Managers | 100% | 16d? | 2015-08-03 | 2015-08-24 |  |  | Dates have changed and need to be updated
6 | 1.2.7.3.2.2 | ERM facilitates Aggregation and Enrichment Activities | 100% | 25d? | 2015-08-25 | 2015-09-28 |  |  | Dates have changed and need to be updated
6 | 1.2.7.3.2.3 | Risk Manager presents inventory to level II subcommittee | 50% | 1d? | 2015-08-03 | 2015-08-03 |  |  | Dates have changed and need to be updated
6 | 1.2.7.3.2.4 | Operational Risk Material Risk Aggregation Prepared | 50% | 0d | 2015-08-03 | 2015-08-03 | Prado/Madargia |  | Dates have changed and need to be updated
5 | 1.2.7.3.3 | TASK: Compliance Material Risk Aggregation | 0% | 41d? | 2015-08-03 | 2015-09-28 |  |  | Dates have changed and need to be updated
6 | 1.2.7.3.3.1 | ERM disseminates Workshop Pre-Read Materials to Risk Managers | 100% | 16d? | 2015-08-03 | 2015-08-24 |  |  | Dates have changed and need to be updated
6 | 1.2.7.3.3.2 | ERM facilitates Aggregation and Enrichment Activities | 100% | 25d? | 2015-08-25 | 2015-09-28 |  |  | Dates have changed and need to be updated
6 | 1.2.7.3.3.3 | Risk Manager presents inventory to level II subcommittee | 50% | 1d? | 2015-08-03 | 2015-08-03 |  |  | Dates have changed and need to be updated
6 | 1.2.7.3.3.4 | Compliance Material Risk Aggregation Prepared | 50% | 0d | 2015-08-03 | 2015-08-03 | Prado/Madargia |  | Dates have changed and need to be updated
5 | 1.2.7.3.4 | TASK: Model Material Risk Aggregation | 0% | 41d? | 2015-08-03 | 2015-09-28 |  |  | Dates have changed and need to be updated
6 | 1.2.7.3.4.1 | ERM disseminates Workshop Pre-Read Materials to Risk Managers | 100% | 16d? | 2015-08-03 | 2015-08-24 |  |  | Dates have changed and need to be updated
6 | 1.2.7.3.4.2 | ERM facilitates Aggregation and Enrichment Workshop | 100% | 25d? | 2015-08-25 | 2015-09-28 |  |  | Dates have changed and need to be updated
6 | 1.2.7.3.4.3 | Risk Manager presents inventory to level II subcommittee | 50% | 1d? | 2015-08-03 | 2015-08-03 |  |  | Dates have changed and need to be updated
6 | 1.2.7.3.4.4 | Model Material Risk Aggregation Prepared | 50% | 0d | 2015-08-03 | 2015-08-03 | Prado/Madargia |  | Dates have changed and need to be updated
5 | 1.2.7.3.5 | TASK: Liquidity/Market Material Risk Aggregation | 0% | 41d? | 2015-08-03 | 2015-09-28 |  |  | Dates have changed and need to be updated
6 | 1.2.7.3.5.1 | ERM disseminates Workshop Pre-Read Materials to Risk Managers | 100% | 16d? | 2015-08-03 | 2015-08-24 |  |  | Dates have changed and need to be updated
6 | 1.2.7.3.5.2 | ERM facilitates Aggregation and Enrichment Activities | 100% | 25d? | 2015-08-25 | 2015-09-28 |  |  | Dates have changed and need to be updated
6 | 1.2.7.3.5.3 | Risk Manager presents inventory to level II subcommittee | 50% | 1d? | 2015-08-03 | 2015-08-03 |  |  | Dates have changed and need to be updated
6 | 1.2.7.3.5.4 | Liquidity/Market Material Risk Aggregation Prepared | 50% | 0d | 2015-08-03 | 2015-08-03 | Prado/Madargia |  | Dates have changed and need to be updated
5 | 1.2.7.3.6 | TASK: Reputational/Strategic Material Risk Aggregation | 0% | 41d? | 2015-08-03 | 2015-09-28 |  |  | Dates have changed and need to be updated
6 | 1.2.7.3.6.1 | ERM disseminates Workshop Pre-Read Materials to Risk Managers | 100% | 16d? | 2015-08-03 | 2015-08-24 |  |  | Dates have changed and need to be updated
6 | 1.2.7.3.6.2 | ERM facilitates Aggregation and Enrichment Workshop | 100% | 25d? | 2015-08-25 | 2015-09-28 |  |  | Dates have changed and need to be updated
6 | 1.2.7.3.6.3 | Risk Manager presents inventory to level II subcommittee | 50% | 1d? | 2015-08-03 | 2015-08-03
6 | 1.2.7.3.6.4 | Reputational/Strategic Material Risk Aggregation Prepared | 50% | 0d | 2015-08-03 | 2015-08-03 | Prado/Madargia
4 | 1.2.7.4 | MILESTONE:Present Miami to SCUSA ERMC | 0% | 48d | 2015-07-28 | 2015-10-01 | Prado/Madargia
4 | 1.2.7.5 | MILESTONE:Present Miami to SCUSA BERC | 0% | 48d | 2015-07-28 | 2015-10-01 | Prado/Madargia
4 | 1.2.7.6 | Present Miami Material Risks to CCAR | 0% | 2d | 2015-10-01 | 2015-10-02
4 | 1.2.7.7 | Deliver Miami Material Risks to CCAR and Capital Plan | 0% | 0d | 2015-10-02 | 2015-10-02 |  | CCAR
2 | 1.3 | Review foundational Risk ID processes including data and technology supporting the Material Risk Program and build multi-year enhancement objectives | 0% | 95d | 2016-01-18 | 2016-05-27 | E. Smith
3 | 1.3.1 | DELIVERABLE: Assess foundational Risk ID processes and ensure complete Foundational Risk Inventory is in place | 0% | 30d | 2016-01-18 | 2016-02-26 | D. Allaire
4 | 1.3.1.1 | MILESTONE: Assess Foundational Risk Processes and ensure complete foundational risk inventory is in place | 0% | 30d | 2016-01-18 | 2016-02-26
5 | 1.3.1.1.1 | Identify existing Foundational Risk Processes | 0% | 30d | 2016-01-18 | 2016-02-26
5 | 1.3.1.1.2 | Confirm and validated foundational risk inventory - develop or enhance as needed | 0% | 30d | 2016-01-18 | 2016-02-26
5 | 1.3.1.1.3 | MILESTONE: Landscape of Foundational Risk Processes and risk inventory confirmed | 0% | 1d | 2016-02-26 | 2016-02-26
3 | 1.3.2 | DELIVERABLE: Review each foundational Risk ID process, identify deficiencies in data, technology and processes, and use gap analyses to determine how to optimize | 0% | 55d | 2016-02-29 | 2016-05-13 | D. Allaire | Chg verb to noun
4 | 1.3.2.1 | MILESTONE: Review each Foundational Risk Process, identify deficient processes, and use gap analyses to determine how to optimize processes | 0% | 55d | 2016-02-29 | 2016-05-13
5 | 1.3.2.1.1 | Review and assess each Foundational Risk Process | 0% | 55d | 2016-02-29 | 2016-05-13
5 | 1.3.2.1.2 | Determine optimal future state for each process | 0% | 55d | 2016-02-29 | 2016-05-13
5 | 1.3.2.1.3 | Perform gap analyses for processes determined to be deficient | 0% | 55d | 2016-02-29 | 2016-05-13
5 | 1.3.2.1.4 | MILESTONE: Each Foundational Risk Process reviewed and assessed | 0% | 0d | 2016-03-31 | 2016-03-31
3 | 1.3.3 | DELIVERABLE: Develop remediation plans for foundational Risk ID processes | 0% | 23d | 2016-04-27 | 2016-05-27 | D. Allaire | Chg verb to noun
4 | 1.3.3.1 | MILESTONE: Remediation of Foundational Risk Process plan Developed | 0% | 23d | 2016-04-27 | 2016-05-27
5 | 1.3.3.1.1 | Identify deficiencies in current plan | 0% | 23d | 2016-04-27 | 2016-05-27
5 | 1.3.3.1.2 | Determine optimal state for plan | 0% | 23d | 2016-04-27 | 2016-05-27
5 | 1.3.3.1.3 | Perform gap analysis in order to develop plan remediation | 0% | 23d | 2016-04-27 | 2016-05-27
5 | 1.3.3.1.4 | MILESTONE: Plan remediation developed | 0% | 0d | 2016-04-27 | 2016-04-27
2 | 1.4 | DELIVERABLE: Execute remediation plans for foundational Risk ID processes, including requirements definition, development and implementation of planned data and technology solutions to support risk identification | 0% |  | 2016-05-30 |  | E. Smith
2 | 1.5 | Long Term Planning Package | 0% | 295d | 2015-11-30 | 2017-01-13
3 | 1.5.1 | DELIVERABLE: Updated SHUSA Risk taxonomy for Material Risk Program | 0% | 35d | 2015-11-30 | 2016-01-15 | D. Allaire
4 | 1.5.1.1 | MILESTONE: Draft of updated risk taxonomy based on 2015 results | 0% | 16d | 2015-11-30 | 2015-12-20
4 | 1.5.1.2 | MILESTONE: Final updated risk taxonomy based on 2015 results | 0% | 24d | 2015-12-15 | 2016-01-15
3 | 1.5.2 | DELIVERABLE: Updated material risk inventory template and guidance for Material Risk Program | 0% | 30d | 2016-01-18 | 2016-02-26 | D. Allaire
4 | 1.5.2.1 | MILESTONE: Updated material risk inventory template | 0% | 30d | 2016-01-18 | 2016-02-26
4 | 1.5.2.2 | MILESTONE: Updated material risk guidance | 0% | 30d | 2016-01-18 | 2016-02-26
4 | 1.5.2.3 | MILESTONE: Updated aggregation and enrichment guidance | 0% | 30d | 2016-01-18 | 2016-02-26
3 | 1.5.3 | DELIVERABLE: Identify technology needs, requirements definition and implementation planning to support risk identification | 0% | 50d | 2016-05-16 | 2016-07-22 | D. Allaire
4 | 1.5.3.1 | MILESTONE: Technology requirements and BRD for risk inventory template web interface | 0% | 14d | 2016-01-01 | 2016-01-20
4 | 1.5.3.2 | Deliver Technology requirements and BRD for Risk inventory template web interface | 0% | 0d | 2016-01-22 | 2016-01-22 |  | Technology
4 | 1.5.3.3 | MILESTONE: Implementation of web interface for risk inventory template | 0% | 24d | 2016-01-20 | 2016-02-22
4 | 1.5.3.4 | MILESTONE: Web interface pilot with selected business entities | 0% | 20d | 2016-02-22 | 2016-03-18
4 | 1.5.3.5 | MILESTONE: Roll out of web interface across business entities | 0% | 10d | 2016-03-18 | 2016-03-31
3 | 1.5.4 | DELIVERABLE: Develop training materials, policies and procedures based on updated Material Risk Program process | 0% | 80d | 2016-02-29 | 2016-06-17 | D. Allaire
4 | 1.5.4.1 | MILESTONE: Development and rollout of training package for material risk ID process | 0% | 80d | 2016-02-29 | 2016-06-17
4 | 1.5.4.2 | MILESTONE: Update and rollout of Policies and procedures for material risk ID process | 0% | 80d | 2016-02-29 | 2016-06-17
3 | 1.5.5 | DELIVERABLE: Develop and implement planned data and technology solutions (e.g. automated interface for risk inventory template, database for foundational inputs and data sources for risk identification, etc.) | 0% | 175d | 2016-05-16 | 2017-01-13 | D. Allaire
4 | 1.5.5.1 | MILESTONE: Development of technology requirements and BRDs for database with business entity level foundational inputs and data sources | 0% | 24d | 2016-03-15 | 2016-04-15
4 | 1.5.5.2 | MILESTONE: Implementation of database for foundational inputs and data sources | 0% | 110d | 2016-03-15 | 2016-08-15
4 | 1.5.5.3 | MILESTONE: Database pilot for selected business entities | 0% | 23d | 2016-08-15 | 2016-09-14
4 | 1.5.5.4 | MILESTONE: Roll out of database across business entities | 0% | 45d | 2016-09-14 | 2016-11-15
3 | 1.5.6 | DELIVERABLE: Training materials, policies and procedures for risk ID database and process | 0% | 44d | 2016-11-15 | 2017-01-13 | D. Allaire
4 | 1.5.6.1 | MILESTONE: Training package for material risk ID database and process developed and rolled out | 0% | 44d | 2016-11-15 | 2017-01-13
4 | 1.5.6.2 | MILESTONE: Policies and procedures for material risk ID process updated and rolled out | 0% | 44d | 2016-11-15 | 2017-01-13

## Required Changes
WBS | Change type | Change required | Start | Finish | Comment
0
1
1.1
1.1.1
1.1.2
1.1.3 | Contact | Allaire -> M. Carbone
1.1.4 | Contact | Allaire -> T. Ploetz
1.1.5 | Contact | Allaire -> J. Bathon
1.1.6 | Contact | Allaire -> Jurado
1.1.7 | Contact | Allaire -> Prado
1.1.8 | Contact | Allaire -> E. Smith
1.1.9 | Contact | Allaire -> E. Smith
1.1.10 | Contact | Allaire -> E. Smith
1.1.11 | Contact | Allaire -> E. Smith
1.1.12 | Contact | Allaire -> E. Smith
1.1.13 | Contact | Allaire -> E. Smith
1.1.14 | Contact | Allaire -> E. Smith
1.1.15 | Delete | remove from plan
1.1.16
1.2
1.2.1
1.2.1.1
1.2.2
1.2.2.1 | Date Change |  | 2015-09-01 | 2015-09-09
1.2.2.1.1 | Delete | Remove detail |  |  | Unnecessary detail complicates the plan
1.2.2.1.2 | Delete | Remove detail |  |  | Unnecessary detail complicates the plan
1.2.2.1.3 | Delete | Remove detail |  |  | Unnecessary detail complicates the plan
1.2.2.1.4 | Delete | Remove detail |  |  | Unnecessary detail complicates the plan
1.2.2.1.5 | Delete | Remove detail |  |  | Unnecessary detail complicates the plan
1.2.2.2 | Date Change |  | 2015-09-01 | 2015-09-30
1.2.2.2.1 | Date Change |  | 2015-09-01 | 2015-09-30
1.2.2.2.1.1 | Delete | Remove detail |  |  | Unnecessary detail complicates the plan
1.2.2.2.1.2 | Delete | Remove detail |  |  | Unnecessary detail complicates the plan
1.2.2.2.1.3 | Delete | Remove detail |  |  | Unnecessary detail complicates the plan
1.2.2.2.1.4 | Delete | Remove detail |  |  | Unnecessary detail complicates the plan
1.2.2.2.1.5 | Delete | Remove detail |  |  | Unnecessary detail complicates the plan
1.2.2.2.2 | Date Change |  | 2015-09-01 | 2015-09-30
1.2.2.2.2.1 | Delete | Remove detail |  |  | Unnecessary detail complicates the plan
1.2.2.2.2.2 | Delete | Remove detail |  |  | Unnecessary detail complicates the plan
1.2.2.2.2.3 | Delete | Remove detail |  |  | Unnecessary detail complicates the plan
1.2.2.2.2.4 | Delete | Remove detail |  |  | Unnecessary detail complicates the plan
1.2.2.2.2.5 | Delete | Remove detail |  |  | Unnecessary detail complicates the plan
1.2.2.2.3 | Date Change |  | 2015-09-01 | 2015-09-30
1.2.2.2.3.1 | Delete | Remove detail |  |  | Unnecessary detail complicates the plan
1.2.2.2.3.2 | Delete | Remove detail |  |  | Unnecessary detail complicates the plan
1.2.2.2.3.3 | Delete | Remove detail |  |  | Unnecessary detail complicates the plan
1.2.2.2.3.4 | Delete | Remove detail |  |  | Unnecessary detail complicates the plan
1.2.2.2.3.5 | Delete | Remove detail |  |  | Unnecessary detail complicates the plan
1.2.2.2.4 | Date Change |  | 2015-09-01 | 2015-09-30
1.2.2.2.4.1 | Delete | Remove detail |  |  | Unnecessary detail complicates the plan
1.2.2.2.4.2 | Delete | Remove detail |  |  | Unnecessary detail complicates the plan
1.2.2.2.4.3 | Delete | Remove detail |  |  | Unnecessary detail complicates the plan
1.2.2.2.4.4 | Delete | Remove detail |  |  | Unnecessary detail complicates the plan
1.2.2.2.4.5 | Delete | Remove detail |  |  | Unnecessary detail complicates the plan
1.2.2.2.5 | Date Change |  | 2015-09-01 | 2015-09-30
1.2.2.2.5.1 | Delete | Remove detail |  |  | Unnecessary detail complicates the plan
1.2.2.2.5.2 | Delete | Remove detail |  |  | Unnecessary detail complicates the plan
1.2.2.2.5.3 | Delete | Remove detail |  |  | Unnecessary detail complicates the plan
1.2.2.2.5.4 | Delete | Remove detail |  |  | Unnecessary detail complicates the plan
1.2.2.2.5.5 | Delete | Remove detail |  |  | Unnecessary detail complicates the plan
1.2.2.2.6 | Date Change |  | 2015-09-01 | 2015-09-30
1.2.2.2.6.1 | Delete | Remove detail |  |  | Unnecessary detail complicates the plan
1.2.2.2.6.2 | Delete | Remove detail |  |  | Unnecessary detail complicates the plan
1.2.2.2.6.3 | Delete | Remove detail |  |  | Unnecessary detail complicates the plan
1.2.2.2.6.4 | Delete | Remove detail |  |  | Unnecessary detail complicates the plan
1.2.2.2.6.5 | Delete | Remove detail |  |  | Unnecessary detail complicates the plan
1.2.2.2.7 | Date Change |  | 2015-09-01 | 2015-09-30
1.2.2.2.7.1 | Delete | Remove detail |  |  | Unnecessary detail complicates the plan
1.2.2.2.7.2 | Delete | Remove detail |  |  | Unnecessary detail complicates the plan
1.2.2.2.7.3 | Delete | Remove detail |  |  | Unnecessary detail complicates the plan
1.2.2.2.7.4 | Delete | Remove detail |  |  | Unnecessary detail complicates the plan
1.2.2.2.7.5 | Delete | Remove detail |  |  | Unnecessary detail complicates the plan
1.2.2.2.8 | Date Change |  | 2015-09-01 | 2015-09-30
1.2.2.2.8.1 | Delete | Remove detail |  |  | Unnecessary detail complicates the plan
1.2.2.2.8.2 | Delete | Remove detail |  |  | Unnecessary detail complicates the plan
1.2.2.2.8.3 | Delete | Remove detail |  |  | Unnecessary detail complicates the plan
1.2.2.2.8.4 | Delete | Remove detail |  |  | Unnecessary detail complicates the plan
1.2.2.2.8.5 | Delete | Remove detail |  |  | Unnecessary detail complicates the plan
1.2.2.3
1.2.2.3.1 | Rename/Date Change | "Synthesis Activities Inventory" | 2015-09-30 | 2015-10-31
1.2.2.3.1.1 | Delete | Remove detail |  |  | Unnecessary detail complicates the plan
1.2.2.3.1.2 | Delete | Remove detail |  |  | Unnecessary detail complicates the plan
1.2.2.3.1.3 | Delete | Remove detail |  |  | Unnecessary detail complicates the plan
1.2.2.3.1.4 | Delete | Remove detail |  |  | Unnecessary detail complicates the plan
1.2.2.4
1.2.2.4.1 | Clarification/else delete |  |  |  | Please inform where these came from
1.2.2.4.1.1 | Clarification/else delete |  |  |  | Please inform where these came from
1.2.2.4.1.2 | Clarification/else delete |  |  |  | Please inform where these came from
1.2.2.4.2
1.2.2.4.2.1
1.2.2.4.2.2
1.2.2.4.2.3
1.2.2.5
1.2.2.5.1
1.2.2.5.1.1
1.2.2.5.1.2
1.2.2.5.1.3
1.2.2.5.1.4
1.2.3 | Contact | Allaire -> M. Carbone
1.2.3.1
1.2.3.1.1
1.2.3.1.1.1
1.2.3.1.1.2 | Contact | Alhadeff/Carbone -> M. Carbone
1.2.3.1.2
1.2.3.1.2.1
1.2.3.1.2.2 | Contact | Alhadeff/Carbone -> M. Carbone
1.2.3.1.3
1.2.3.1.3.1
1.2.3.1.3.2 | Contact | Alhadeff/Carbone -> M. Carbone
1.2.3.1.4 | Delete |  |  |  | No longer LOB after re-org
1.2.3.1.4.1 | Delete |  |  |  | No longer LOB after re-org
1.2.3.1.4.2 | Delete |  |  |  | No longer LOB after re-org
1.2.3.1.5 | Delete |  |  |  | No longer LOB after re-org
1.2.3.1.5.1 | Delete |  |  |  | No longer LOB after re-org
1.2.3.1.5.2 | Delete |  |  |  | No longer LOB after re-org
1.2.3.1.6 | Delete |  |  |  | No longer LOB after re-org
1.2.3.1.6.1 | Delete |  |  |  | No longer LOB after re-org
1.2.3.1.6.2 | Delete |  |  |  | No longer LOB after re-org
1.2.3.2
1.2.3.2.1
1.2.3.2.1.1
1.2.3.2.1.2 | Contact | Alhadeff/Carbone -> M. Carbone
1.2.3.3
1.2.3.3.1
1.2.3.3.1.1
1.2.3.3.1.2 | Contact | Alhadeff/Carbone -> M. Carbone
1.2.3.3.2
1.2.3.3.2.1
1.2.3.3.2.2 | Contact | Alhadeff/Carbone -> M. Carbone
1.2.3.3.3
1.2.3.3.3.1
1.2.3.3.3.2
1.2.3.4
1.2.3.4.1
1.2.3.4.1.1
1.2.3.4.1.2 | Contact | Alhadeff/Carbone -> M. Carbone
1.2.3.5
1.2.3.5.1
1.2.3.5.1.1
1.2.3.5.1.2 | Contact | Alhadeff/Carbone -> M. Carbone
1.2.3.5.2
1.2.3.5.2.1
1.2.3.5.2.2 | Contact | Alhadeff/Carbone -> M. Carbone
1.2.3.6
1.2.3.6.1
1.2.3.6.1.1
1.2.3.6.1.2 | Contact | Alhadeff/Carbone -> M. Carbone
1.2.3.7
1.2.3.7.1
1.2.3.7.1.1
1.2.3.7.1.2 | Contact | Alhadeff/Carbone -> M. Carbone
1.2.3.7.2
1.2.3.7.2.1
1.2.3.7.2.2 | Contact | Alhadeff/Carbone -> M. Carbone
1.2.3.7.3
1.2.3.7.3.1
1.2.3.7.3.2 | Contact | Alhadeff/Carbone -> M. Carbone
1.2.3.8
1.2.3.8.1
1.2.3.8.1.1
1.2.3.8.1.2 | Contact | Alhadeff/Carbone -> M. Carbone
1.2.3.9
1.2.3.9.1
1.2.3.9.1.1
1.2.3.9.1.2 | Contact | Alhadeff/Carbone -> M. Carbone
1.2.3.10 | Delete |  |  |  | No longer LOB after re-org
1.2.3.10.1 | Delete |  |  |  | No longer LOB after re-org
1.2.3.10.1.1 | Delete |  |  |  | No longer LOB after re-org
1.2.3.10.1.2 | Delete |  |  |  | No longer LOB after re-org
1.2.3.11 | Delete |  |  |  | No longer LOB after re-org
1.2.3.11.1 | Delete |  |  |  | No longer LOB after re-org
1.2.3.11.1.1 | Delete |  |  |  | No longer LOB after re-org
1.2.3.11.1.2 | Delete |  |  |  | No longer LOB after re-org
1.2.3.12
1.2.3.12.1
1.2.3.12.1.1
1.2.3.12.1.2 | Contact | Alhadeff/Carbone -> M. Carbone
1.2.3.13
1.2.3.13.1
1.2.3.13.1.1
1.2.3.13.1.2 | Contact | Alhadeff/Carbone -> M. Carbone
1.2.3.14
1.2.3.14.1
1.2.3.14.1.1
1.2.3.14.1.2 | Contact | Alhadeff/Carbone -> M. Carbone
1.2.3.15
1.2.3.15.1
1.2.3.15.1.1
1.2.3.15.1.2 | Contact | Alhadeff/Carbone -> M. Carbone
1.2.3.16
1.2.3.16.1 | Date Change |  | 2015-08-01 | 2015-08-31
1.2.3.16.1.1 | Delete | Remove detail |  |  | Unnecessary detail complicates the plan
1.2.3.16.1.2 | Delete | Remove detail |  |  | Unnecessary detail complicates the plan
1.2.3.16.1.3 | Delete | Remove detail |  |  | Unnecessary detail complicates the plan
1.2.3.16.1.4 | Delete | Remove detail |  |  | Unnecessary detail complicates the plan
1.2.3.16.2 | Date Change |  | 2015-08-01 | 2015-08-31
1.2.3.16.2.1 | Delete | Remove detail |  |  | Unnecessary detail complicates the plan
1.2.3.16.2.2 | Delete | Remove detail |  |  | Unnecessary detail complicates the plan
1.2.3.16.2.3 | Delete | Remove detail |  |  | Unnecessary detail complicates the plan
1.2.3.16.2.4 | Delete | Remove detail |  |  | Unnecessary detail complicates the plan
1.2.3.16.3 | Date Change |  | 2015-08-01 | 2015-08-31
1.2.3.16.3.1 | Delete | Remove detail |  |  | Unnecessary detail complicates the plan
1.2.3.16.3.2 | Delete | Remove detail |  |  | Unnecessary detail complicates the plan
1.2.3.16.3.3 | Delete | Remove detail |  |  | Unnecessary detail complicates the plan
1.2.3.16.3.4 | Delete | Remove detail |  |  | Unnecessary detail complicates the plan
1.2.3.16.4 | Date Change |  | 2015-08-01 | 2015-08-31
1.2.3.16.4.1 | Delete | Remove detail |  |  | Unnecessary detail complicates the plan
1.2.3.16.4.2 | Delete | Remove detail |  |  | Unnecessary detail complicates the plan
1.2.3.16.4.3 | Delete | Remove detail |  |  | Unnecessary detail complicates the plan
1.2.3.16.4.4 | Delete | Remove detail |  |  | Unnecessary detail complicates the plan
1.2.3.16.5 | Date Change |  | 2015-08-01 | 2015-08-31
1.2.3.16.5.1 | Delete | Remove detail |  |  | Unnecessary detail complicates the plan
1.2.3.16.5.2 | Delete | Remove detail |  |  | Unnecessary detail complicates the plan
1.2.3.16.5.3 | Delete | Remove detail |  |  | Unnecessary detail complicates the plan
1.2.3.16.5.4 | Delete | Remove detail |  |  | Unnecessary detail complicates the plan
1.2.3.16.6 | Date Change |  | 2015-08-01 | 2015-08-31
1.2.3.16.6.1 | Delete | Remove detail |  |  | Unnecessary detail complicates the plan
1.2.3.16.6.2 | Delete | Remove detail |  |  | Unnecessary detail complicates the plan
1.2.3.16.6.3 | Delete | Remove detail |  |  | Unnecessary detail complicates the plan
1.2.3.16.6.4 | Delete | Remove detail |  |  | Unnecessary detail complicates the plan
1.2.3.17
1.2.3.18
1.2.3.19 | Delete |  |  |  | This should not be in the plan
1.2.3.20 | Delete |  |  |  | This should not be in the plan
1.2.4 | Contact | Allaire -> T. Ploetz
1.2.4.1 | Date Change |  | 2015-08-01 | 2015-08-31 | New dates approved for SCUSA
1.2.4.1.1 | Date Change |  | 2015-08-01 | 2015-08-31 | New dates approved for SCUSA
1.2.4.1.1.1 | Delete | Remove detail |  |  | Unnecessary detail complicates the plan
1.2.4.1.1.2 | Delete | Remove detail |  |  | Unnecessary detail complicates the plan
1.2.4.2 | Date Change |  | 2015-08-01 | 2015-08-31 | New dates approved for SCUSA
1.2.4.2.1 | Date Change |  | 2015-08-01 | 2015-08-31 | New dates approved for SCUSA
1.2.4.2.1.1 | Delete | Remove detail |  |  | Unnecessary detail complicates the plan
1.2.4.2.1.2 | Delete | Remove detail |  |  | Unnecessary detail complicates the plan
1.2.4.3 | Rename/Date Change | "Support Functions Inventory" | 2015-08-01 | 2015-08-31 | Change to process approved for SCUSA
1.2.4.3.1 | Date Change |  | 2015-08-01 | 2015-08-31 | New dates approved for SCUSA
1.2.4.3.1.1 | Delete | Remove detail |  |  | Unnecessary detail complicates the plan
1.2.4.3.1.2 | Delete | Remove detail |  |  | Unnecessary detail complicates the plan
1.2.4.4 | Delete |  |  |  | SCUSA not creating these inventories
1.2.4.4.1 | Delete |  |  |  | SCUSA not creating these inventories
1.2.4.4.1.1 | Delete |  |  |  | SCUSA not creating these inventories
1.2.4.4.1.2 | Delete |  |  |  | SCUSA not creating these inventories
1.2.4.5 | Delete |  |  |  | SCUSA not creating these inventories
1.2.4.5.1 | Delete |  |  |  | SCUSA not creating these inventories
1.2.4.5.1.1 | Delete |  |  |  | SCUSA not creating these inventories
1.2.4.5.1.2 | Delete |  |  |  | SCUSA not creating these inventories
1.2.4.6 | Delete |  |  |  | SCUSA not creating these inventories
1.2.4.6.1 | Delete |  |  |  | SCUSA not creating these inventories
1.2.4.6.1.1 | Delete |  |  |  | SCUSA not creating these inventories
1.2.4.6.1.2 | Delete |  |  |  | SCUSA not creating these inventories
1.2.4.7 | Date Change |  | 2015-08-01 | 2015-08-31 | New dates approved for SCUSA
1.2.4.7.1 | Date Change |  | 2015-08-01 | 2015-08-31 | New dates approved for SCUSA
1.2.4.7.1.1 | Delete | Remove detail |  |  | Unnecessary detail complicates the plan
1.2.4.7.1.2 | Delete | Remove detail |  |  | Unnecessary detail complicates the plan
1.2.4.7.1.3 | Delete | Remove detail |  |  | Unnecessary detail complicates the plan
1.2.4.7.1.4 | Delete | Remove detail |  |  | Unnecessary detail complicates the plan
1.2.4.7.2 | Date Change |  | 2015-08-01 | 2015-08-31 | New dates approved for SCUSA
1.2.4.7.2.1 | Delete | Remove detail |  |  | Unnecessary detail complicates the plan
1.2.4.7.2.2 | Delete | Remove detail |  |  | Unnecessary detail complicates the plan
1.2.4.7.2.3 | Delete | Remove detail |  |  | Unnecessary detail complicates the plan
1.2.4.7.2.4 | Delete | Remove detail |  |  | Unnecessary detail complicates the plan
1.2.4.7.3 | Date Change |  | 2015-08-01 | 2015-08-31 | New dates approved for SCUSA
1.2.4.7.3.1 | Delete | Remove detail |  |  | Unnecessary detail complicates the plan
1.2.4.7.3.2 | Delete | Remove detail |  |  | Unnecessary detail complicates the plan
1.2.4.7.3.3 | Delete | Remove detail |  |  | Unnecessary detail complicates the plan
1.2.4.7.3.4 | Delete | Remove detail |  |  | Unnecessary detail complicates the plan
1.2.4.7.4 | Date Change |  | 2015-08-01 | 2015-08-31 | New dates approved for SCUSA
1.2.4.7.4.1 | Delete | Remove detail |  |  | Unnecessary detail complicates the plan
1.2.4.7.4.2 | Delete | Remove detail |  |  | Unnecessary detail complicates the plan
1.2.4.7.4.3 | Delete | Remove detail |  |  | Unnecessary detail complicates the plan
1.2.4.7.4.4 | Delete | Remove detail |  |  | Unnecessary detail complicates the plan
1.2.4.7.5 | Date Change |  | 2015-08-01 | 2015-08-31 | New dates approved for SCUSA
1.2.4.7.5.1 | Delete | Remove detail |  |  | Unnecessary detail complicates the plan
1.2.4.7.5.2 | Delete | Remove detail |  |  | Unnecessary detail complicates the plan
1.2.4.7.5.3 | Delete | Remove detail |  |  | Unnecessary detail complicates the plan
1.2.4.7.5.4 | Delete | Remove detail |  |  | Unnecessary detail complicates the plan
1.2.4.7.6 | Date Change |  | 2015-08-01 | 2015-08-31 | New dates approved for SCUSA
1.2.4.7.6.1 | Delete | Remove detail |  |  | Unnecessary detail complicates the plan
1.2.4.7.6.2 | Delete | Remove detail |  |  | Unnecessary detail complicates the plan
1.2.4.7.6.3 | Delete | Remove detail |  |  | Unnecessary detail complicates the plan
1.2.4.7.6.4 | Delete | Remove detail |  |  | Unnecessary detail complicates the plan
1.2.4.8 | Contact | Ploetz/Smith -> T. Ploetz
1.2.4.9 | Contact | Ploetz/Smith -> T. Ploetz
1.2.4.10 | Delete |  |  |  | This should not be in the plan
1.2.4.11 | Delete |  |  |  | This should not be in the plan
1.2.5 | Contact | Allaire -> J. Bathon
1.2.5.1 | Date Change |  | 2015-06-29 | 2015-07-31
1.2.5.1.1 | Date Change |  | 2015-06-29 | 2015-07-31
1.2.5.1.1.1 | Date Change |  | 2015-06-29 | 2015-07-31
1.2.5.1.1.2 | Date Change |  | 2015-06-29 | 2015-07-31
1.2.5.1.1.3 | Date Change |  | 2015-06-29 | 2015-07-31
1.2.5.2 | Date Change |  | 2015-06-29 | 2015-07-31
1.2.5.2.1 | Date Change |  | 2015-06-29 | 2015-07-31
1.2.5.2.1.1 | Date Change |  | 2015-06-29 | 2015-07-31
1.2.5.2.1.2 | Date Change |  | 2015-06-29 | 2015-07-31
1.2.5.2.1.3 | Date Change |  | 2015-06-29 | 2015-07-31
1.2.5.3 | Date Change |  | 2015-06-29 | 2015-07-31
1.2.5.3.1 | Date Change |  | 2015-06-29 | 2015-07-31
1.2.5.3.1.1 | Date Change |  | 2015-06-29 | 2015-07-31
1.2.5.3.1.2 | Date Change |  | 2015-06-29 | 2015-07-31
1.2.5.3.1.3 | Date Change |  | 2015-06-29 | 2015-07-31
1.2.5.4 | Date Change |  | 2015-06-29 | 2015-07-31
1.2.5.4.1 | Date Change |  | 2015-06-29 | 2015-07-31
1.2.5.4.1.1 | Date Change |  | 2015-06-29 | 2015-07-31
1.2.5.4.1.2 | Date Change |  | 2015-06-29 | 2015-07-31
1.2.5.4.1.3 | Date Change |  | 2015-06-29 | 2015-07-31
1.2.5.5 | Date Change |  | 2015-06-29 | 2015-07-31
1.2.5.5.1 | Date Change |  | 2015-06-29 | 2015-07-31
1.2.5.5.1.1 | Date Change |  | 2015-06-29 | 2015-07-31
1.2.5.5.1.2 | Date Change |  | 2015-06-29 | 2015-07-31
1.2.5.5.1.3 | Date Change |  | 2015-06-29 | 2015-07-31
1.2.5.6 | Date Change |  | 2015-06-29 | 2015-07-31
1.2.5.6.1 | Date Change |  | 2015-06-29 | 2015-07-31
1.2.5.6.1.1 | Date Change |  | 2015-06-29 | 2015-07-31
1.2.5.6.1.2 | Date Change |  | 2015-06-29 | 2015-07-31
1.2.5.6.1.3 | Date Change |  | 2015-06-29 | 2015-07-31
1.2.5.7 | Delete |  |  |  | SIS not creating these inventories
1.2.5.7.1 | Delete |  |  |  | SIS not creating these inventories
1.2.5.7.1.1 | Delete |  |  |  | SIS not creating these inventories
1.2.5.7.1.2 | Delete |  |  |  | SIS not creating these inventories
1.2.5.7.1.3 | Delete |  |  |  | SIS not creating these inventories
1.2.5.8 | Delete |  |  |  | SIS not creating these inventories
1.2.5.8.1 | Delete |  |  |  | SIS not creating these inventories
1.2.5.8.1.1 | Delete |  |  |  | SIS not creating these inventories
1.2.5.8.1.2 | Delete |  |  |  | SIS not creating these inventories
1.2.5.8.1.3 | Delete |  |  |  | SIS not creating these inventories
1.2.5.9 | Delete |  |  |  | SIS not creating these inventories
1.2.5.9.1 | Delete |  |  |  | SIS not creating these inventories
1.2.5.9.1.1 | Delete |  |  |  | SIS not creating these inventories
1.2.5.9.1.2 | Delete |  |  |  | SIS not creating these inventories
1.2.5.9.1.3 | Delete |  |  |  | SIS not creating these inventories
1.2.5.10 | Delete |  |  |  | SIS not creating these inventories
1.2.5.10.1 | Delete |  |  |  | SIS not creating these inventories
1.2.5.10.1.1 | Delete |  |  |  | SIS not creating these inventories
1.2.5.10.1.2 | Delete |  |  |  | SIS not creating these inventories
1.2.5.10.1.3 | Delete |  |  |  | SIS not creating these inventories
1.2.5.11 | Date Change |  | 2015-08-01 | 2015-08-31
1.2.5.11.1 | Date Change |  | 2015-08-01 | 2015-08-31
1.2.5.11.1.1 | Delete | Remove detail |  |  | Unnecessary detail complicates the plan
1.2.5.11.1.2 | Delete | Remove detail |  |  | Unnecessary detail complicates the plan
1.2.5.11.1.3 | Delete | Remove detail |  |  | Unnecessary detail complicates the plan
1.2.5.11.1.4 | Delete | Remove detail |  |  | Unnecessary detail complicates the plan
1.2.5.11.2 | Date Change |  | 2015-08-01 | 2015-08-31
1.2.5.11.2.1 | Delete | Remove detail |  |  | Unnecessary detail complicates the plan
1.2.5.11.2.2 | Delete | Remove detail |  |  | Unnecessary detail complicates the plan
1.2.5.11.2.3 | Delete | Remove detail |  |  | Unnecessary detail complicates the plan
1.2.5.11.2.4 | Delete | Remove detail |  |  | Unnecessary detail complicates the plan
1.2.5.11.3 | Date Change |  | 2015-08-01 | 2015-08-31
1.2.5.11.3.1 | Delete | Remove detail |  |  | Unnecessary detail complicates the plan
1.2.5.11.3.2 | Delete | Remove detail |  |  | Unnecessary detail complicates the plan
1.2.5.11.3.3 | Delete | Remove detail |  |  | Unnecessary detail complicates the plan
1.2.5.11.3.4 | Delete | Remove detail |  |  | Unnecessary detail complicates the plan
1.2.5.11.4 | Date Change |  | 2015-08-01 | 2015-08-31
1.2.5.11.4.1 | Delete | Remove detail |  |  | Unnecessary detail complicates the plan
1.2.5.11.4.2 | Delete | Remove detail |  |  | Unnecessary detail complicates the plan
1.2.5.11.4.3 | Delete | Remove detail |  |  | Unnecessary detail complicates the plan
1.2.5.11.4.4 | Delete | Remove detail |  |  | Unnecessary detail complicates the plan
1.2.5.11.5 | Date Change |  | 2015-08-01 | 2015-08-31
1.2.5.11.5.1 | Delete | Remove detail |  |  | Unnecessary detail complicates the plan
1.2.5.11.5.2 | Delete | Remove detail |  |  | Unnecessary detail complicates the plan
1.2.5.11.5.3 | Delete | Remove detail |  |  | Unnecessary detail complicates the plan
1.2.5.11.5.4 | Delete | Remove detail |  |  | Unnecessary detail complicates the plan
1.2.5.11.6 | Date Change |  | 2015-08-01 | 2015-08-31
1.2.5.11.6.1 | Delete | Remove detail |  |  | Unnecessary detail complicates the plan
1.2.5.11.6.2 | Delete | Remove detail |  |  | Unnecessary detail complicates the plan
1.2.5.11.6.3 | Delete | Remove detail |  |  | Unnecessary detail complicates the plan
1.2.5.11.6.4 | Delete | Remove detail |  |  | Unnecessary detail complicates the plan
1.2.5.12 | Contact | Murphy/Khurana -> J. Bathon
1.2.5.13 | Contact | Murphy/Khurana -> J. Bathon
1.2.5.14 | Delete |  |  |  | This should not be in the plan
1.2.5.15 | Delete |  |  |  | This should not be in the plan
1.2.6 | Contact | Allaire -> Jurado
1.2.6.1
1.2.6.1.1
1.2.6.1.1.1
1.2.6.1.1.2 | Contact | Jurado/Fabricio -> Jurado
1.2.6.1.2
1.2.6.1.2.1
1.2.6.1.2.2 | Contact | Jurado/Fabricio -> Jurado
1.2.6.1.3
1.2.6.1.3.1
1.2.6.1.3.2 | Contact | Jurado/Fabricio -> Jurado
1.2.6.1.4
1.2.6.1.4.1
1.2.6.1.4.2 | Contact | Jurado/Fabricio -> Jurado
1.2.6.1.5
1.2.6.1.5.1
1.2.6.1.5.2 | Contact | Jurado/Fabricio -> Jurado
1.2.6.2
1.2.6.2.1
1.2.6.2.1.1
1.2.6.2.1.2 | Contact | Jurado/Fabricio -> Jurado
1.2.6.2.2
1.2.6.2.2.1
1.2.6.2.2.2 | Contact | Jurado/Fabricio -> Jurado
1.2.6.2.3
1.2.6.2.3.1
1.2.6.2.3.2 | Contact | Jurado/Fabricio -> Jurado
1.2.6.3
1.2.6.3.1
1.2.6.3.1.1
1.2.6.3.1.2
1.2.6.3.1.3 | Contact | Jurado/Fabricio -> Jurado
1.2.6.4
1.2.6.4.1
1.2.6.4.1.1
1.2.6.4.1.2
1.2.6.4.1.3 | Contact | Jurado/Fabricio -> Jurado
1.2.6.5
1.2.6.5.1
1.2.6.5.1.1
1.2.6.5.1.2
1.2.6.5.1.3 | Contact | Jurado/Fabricio -> Jurado
1.2.6.6
1.2.6.6.1
1.2.6.6.1.1
1.2.6.6.1.2
1.2.6.6.1.3 | Contact | Jurado/Fabricio -> Jurado
1.2.6.7
1.2.6.7.1
1.2.6.7.1.1
1.2.6.7.1.2
1.2.6.7.1.3 | Contact | Jurado/Fabricio -> Jurado
1.2.6.8
1.2.6.8.1
1.2.6.8.1.1
1.2.6.8.1.2
1.2.6.8.1.3 | Contact | Jurado/Fabricio -> Jurado
1.2.6.9 | Delete |  |  |  | PR is not creating these inventories
1.2.6.9.1 | Delete |  |  |  | PR is not creating these inventories
1.2.6.9.1.1 | Delete |  |  |  | PR is not creating these inventories
1.2.6.9.1.2 | Delete |  |  |  | PR is not creating these inventories
1.2.6.9.1.3 | Delete |  |  |  | PR is not creating these inventories
1.2.6.9.1.4 | Delete |  |  |  | PR is not creating these inventories
1.2.6.10 | Delete |  |  |  | PR is not creating these inventories
1.2.6.10.1 | Delete |  |  |  | PR is not creating these inventories
1.2.6.10.1.1 | Delete |  |  |  | PR is not creating these inventories
1.2.6.10.1.2 | Delete |  |  |  | PR is not creating these inventories
1.2.6.10.1.3 | Delete |  |  |  | PR is not creating these inventories
1.2.6.11 | Delete |  |  |  | PR is not creating these inventories
1.2.6.11.1 | Delete |  |  |  | PR is not creating these inventories
1.2.6.11.1.1 | Delete |  |  |  | PR is not creating these inventories
1.2.6.11.1.2 | Delete |  |  |  | PR is not creating these inventories
1.2.6.11.1.3 | Delete |  |  |  | PR is not creating these inventories
1.2.6.12
1.2.6.12.1
1.2.6.12.1.1
1.2.6.12.1.2
1.2.6.12.1.3 | Contact | Jurado/Fabricio -> Jurado
1.2.6.13
1.2.6.13.1
1.2.6.13.1.1
1.2.6.13.1.2
1.2.6.13.1.3 | Contact | Jurado/Fabricio -> Jurado
1.2.6.14
1.2.6.14.1
1.2.6.14.1.1
1.2.6.14.1.2
1.2.6.14.1.3 | Contact | Jurado/Fabricio -> Jurado
1.2.6.15
1.2.6.15.1
1.2.6.15.1.1
1.2.6.15.1.2
1.2.6.15.1.3 | Contact | Jurado/Fabricio -> Jurado
1.2.6.16 | Date Change |  | 2015-08-01 | 2015-08-31
1.2.6.16.1 | Date Change |  | 2015-08-01 | 2015-08-31
1.2.6.16.1.1 | Delete | Remove detail |  |  | Unnecessary detail complicates the plan
1.2.6.16.1.2 | Delete | Remove detail |  |  | Unnecessary detail complicates the plan
1.2.6.16.1.3 | Delete | Remove detail |  |  | Unnecessary detail complicates the plan
1.2.6.16.1.4 | Delete | Remove detail |  |  | Unnecessary detail complicates the plan
1.2.6.16.2 | Date Change |  | 2015-08-01 | 2015-08-31
1.2.6.16.2.1 | Delete | Remove detail |  |  | Unnecessary detail complicates the plan
1.2.6.16.2.2 | Delete | Remove detail |  |  | Unnecessary detail complicates the plan
1.2.6.16.2.3 | Delete | Remove detail |  |  | Unnecessary detail complicates the plan
1.2.6.16.2.4 | Delete | Remove detail |  |  | Unnecessary detail complicates the plan
1.2.6.16.3 | Date Change |  | 2015-08-01 | 2015-08-31
1.2.6.16.3.1 | Delete | Remove detail |  |  | Unnecessary detail complicates the plan
1.2.6.16.3.2 | Delete | Remove detail |  |  | Unnecessary detail complicates the plan
1.2.6.16.3.3 | Delete | Remove detail |  |  | Unnecessary detail complicates the plan
1.2.6.16.3.4 | Delete | Remove detail |  |  | Unnecessary detail complicates the plan
1.2.6.16.4 | Date Change |  | 2015-08-01 | 2015-08-31
1.2.6.16.4.1 | Delete | Remove detail |  |  | Unnecessary detail complicates the plan
1.2.6.16.4.2 | Delete | Remove detail |  |  | Unnecessary detail complicates the plan
1.2.6.16.4.3 | Delete | Remove detail |  |  | Unnecessary detail complicates the plan
1.2.6.16.4.4 | Delete | Remove detail |  |  | Unnecessary detail complicates the plan
1.2.6.16.5 | Date Change |  | 2015-08-01 | 2015-08-31
1.2.6.16.5.1 | Delete | Remove detail |  |  | Unnecessary detail complicates the plan
1.2.6.16.5.2 | Delete | Remove detail |  |  | Unnecessary detail complicates the plan
1.2.6.16.5.3 | Delete | Remove detail |  |  | Unnecessary detail complicates the plan
1.2.6.16.5.4 | Delete | Remove detail |  |  | Unnecessary detail complicates the plan
1.2.6.16.6 | Date Change |  | 2015-08-01 | 2015-08-31
1.2.6.16.6.1 | Delete | Remove detail |  |  | Unnecessary detail complicates the plan
1.2.6.16.6.2 | Delete | Remove detail |  |  | Unnecessary detail complicates the plan
1.2.6.16.6.3 | Delete | Remove detail |  |  | Unnecessary detail complicates the plan
1.2.6.16.6.4 | Delete | Remove detail |  |  | Unnecessary detail complicates the plan
1.2.6.17 | Contact | Jurado/Fabricio -> Jurado
1.2.6.18 | Contact | Jurado/Fabricio -> Jurado
1.2.6.19 | Delete |  |  |  | This should not be in the plan
1.2.6.20 | Delete |  |  |  | This should not be in the plan
1.2.7 | Contact | Allaire -> Prado
1.2.7.1 | Date Change |  | 2015-06-29 | 2015-07-31
1.2.7.1.1 | Date/Name Change: "BSI" |  | 2015-06-29 | 2015-07-31 | Miami produced single MRI as "BSI"
1.2.7.1.1.1 | Date Change |  | 2015-06-29 | 2015-07-31
1.2.7.1.1.2 | Date Change |  | 2015-06-29 | 2015-07-31
1.2.7.1.1.3 | Date Change/Contact | Prado/Madargia -> Prado | 2015-06-29 | 2015-07-31
1.2.7.2 | Delete |  |  |  | BSI is not creating these inventories
1.2.7.2.1 | Delete |  |  |  | BSI is not creating these inventories
1.2.7.2.1.1 | Delete |  |  |  | BSI is not creating these inventories
1.2.7.2.1.2 | Delete |  |  |  | BSI is not creating these inventories
1.2.7.2.1.3 | Delete |  |  |  | BSI is not creating these inventories
1.2.7.3 | Date Change |  | 2015-08-01 | 2015-08-31
1.2.7.3.1 | Date Change |  | 2015-08-01 | 2015-08-31
1.2.7.3.1.1 | Delete | Remove detail |  |  | Unnecessary detail complicates the plan
1.2.7.3.1.2 | Delete | Remove detail |  |  | Unnecessary detail complicates the plan
1.2.7.3.1.3 | Delete | Remove detail |  |  | Unnecessary detail complicates the plan
1.2.7.3.1.4 | Delete | Remove detail |  |  | Unnecessary detail complicates the plan
1.2.7.3.2 | Date Change |  | 2015-08-01 | 2015-08-31
1.2.7.3.2.1 | Delete | Remove detail |  |  | Unnecessary detail complicates the plan
1.2.7.3.2.2 | Delete | Remove detail |  |  | Unnecessary detail complicates the plan
1.2.7.3.2.3 | Delete | Remove detail |  |  | Unnecessary detail complicates the plan
1.2.7.3.2.4 | Delete | Remove detail |  |  | Unnecessary detail complicates the plan
1.2.7.3.3 | Date Change |  | 2015-08-01 | 2015-08-31
1.2.7.3.3.1 | Delete | Remove detail |  |  | Unnecessary detail complicates the plan
1.2.7.3.3.2 | Delete | Remove detail |  |  | Unnecessary detail complicates the plan
1.2.7.3.3.3 | Delete | Remove detail |  |  | Unnecessary detail complicates the plan
1.2.7.3.3.4 | Delete | Remove detail |  |  | Unnecessary detail complicates the plan
1.2.7.3.4 | Date Change |  | 2015-08-01 | 2015-08-31
1.2.7.3.4.1 | Delete | Remove detail |  |  | Unnecessary detail complicates the plan
1.2.7.3.4.2 | Delete | Remove detail |  |  | Unnecessary detail complicates the plan
1.2.7.3.4.3 | Delete | Remove detail |  |  | Unnecessary detail complicates the plan
1.2.7.3.4.4 | Delete | Remove detail |  |  | Unnecessary detail complicates the plan
1.2.7.3.5 | Date Change |  | 2015-08-01 | 2015-08-31
1.2.7.3.5.1 | Delete | Remove detail |  |  | Unnecessary detail complicates the plan
1.2.7.3.5.2 | Delete | Remove detail |  |  | Unnecessary detail complicates the plan
1.2.7.3.5.3 | Delete | Remove detail |  |  | Unnecessary detail complicates the plan
1.2.7.3.5.4 | Delete | Remove detail |  |  | Unnecessary detail complicates the plan
1.2.7.3.6 | Date Change |  | 2015-08-01 | 2015-08-31
1.2.7.3.6.1 | Delete | Remove detail |  |  | Unnecessary detail complicates the plan
1.2.7.3.6.2 | Delete | Remove detail |  |  | Unnecessary detail complicates the plan
1.2.7.3.6.3 | Delete | Remove detail |  |  | Unnecessary detail complicates the plan
1.2.7.3.6.4 | Delete | Remove detail |  |  | Unnecessary detail complicates the plan
1.2.7.4 | Contact | Prado/Madargia -> Prado
1.2.7.5 | Contact | Prado/Madargia -> Prado
1.2.7.6 | Delete |  |  |  | This should not be in the plan
1.2.7.7 | Delete |  |  |  | This should not be in the plan
1.3
1.3.1 | Contact | D. Allaire -> E. Smith
1.3.1.1
1.3.1.1.1
1.3.1.1.2
1.3.1.1.3
1.3.2 | Contact | D. Allaire -> E. Smith
1.3.2.1
1.3.2.1.1
1.3.2.1.2
1.3.2.1.3
1.3.2.1.4
1.3.3 | Contact | D. Allaire -> E. Smith
1.3.3.1
1.3.3.1.1
1.3.3.1.2
1.3.3.1.3
1.3.3.1.4
1.4 | Delete |  |  |  | This should not be in the plan
1.5
1.5.1 | Contact | D. Allaire -> E. Smith
1.5.1.1
1.5.1.2
1.5.2 | Contact | D. Allaire -> E. Smith
1.5.2.1
1.5.2.2
1.5.2.3
1.5.3 | Delete |  |  |  | This should not be in the plan
1.5.3.1 | Delete |  |  |  | This should not be in the plan
1.5.3.2 | Delete |  |  |  | This should not be in the plan
1.5.3.3 | Delete |  |  |  | This should not be in the plan
1.5.3.4 | Delete |  |  |  | This should not be in the plan
1.5.3.5 | Delete |  |  |  | This should not be in the plan
1.5.4 | Contact | D. Allaire -> E. Smith
1.5.4.1
1.5.4.2
1.5.5 | Delete |  |  |  | This should not be in the plan
1.5.5.1 | Delete |  |  |  | This should not be in the plan
1.5.5.2 | Delete |  |  |  | This should not be in the plan
1.5.5.3 | Delete |  |  |  | This should not be in the plan
1.5.5.4 | Delete |  |  |  | This should not be in the plan
1.5.6 | Delete |  |  |  | This should not be in the plan
1.5.6.1 | Delete |  |  |  | This should not be in the plan
1.5.6.2 | Delete |  |  |  | This should not be in the plan

## Sheet1
Allaire - | M. Carbone
Allaire - | T. Ploetz
Allaire - | J. Bathon
Allaire - | Jurado
Allaire - | Prado
Allaire - | E. Smith
Allaire - | E. Smith
Allaire - | E. Smith
Allaire - | E. Smith
Allaire - | E. Smith
Allaire - | E. Smith
Allaire - | E. Smith
Allaire - | M. Carbone
Alhadeff/Carbone - | M. Carbone
Alhadeff/Carbone - | M. Carbone
Alhadeff/Carbone - | M. Carbone
Alhadeff/Carbone - | M. Carbone
Alhadeff/Carbone - | M. Carbone
Alhadeff/Carbone - | M. Carbone
Alhadeff/Carbone - | M. Carbone
Alhadeff/Carbone - | M. Carbone
Alhadeff/Carbone - | M. Carbone
Alhadeff/Carbone - | M. Carbone
Alhadeff/Carbone - | M. Carbone
Alhadeff/Carbone - | M. Carbone
Alhadeff/Carbone - | M. Carbone
Alhadeff/Carbone - | M. Carbone
Alhadeff/Carbone - | M. Carbone
Alhadeff/Carbone - | M. Carbone
Alhadeff/Carbone - | M. Carbone
Alhadeff/Carbone - | M. Carbone
Alhadeff/Carbone - | M. Carbone
Allaire - | T. Ploetz
Ploetz/Smith - | T. Ploetz
Ploetz/Smith - | T. Ploetz
Allaire - | J. Bathon
Murphy/Khurana - | J. Bathon
Murphy/Khurana - | J. Bathon
Allaire - | Jurado
Jurado/Fabricio - | Jurado
Jurado/Fabricio - | Jurado
Jurado/Fabricio - | Jurado
Jurado/Fabricio - | Jurado
Jurado/Fabricio - | Jurado
Jurado/Fabricio - | Jurado
Jurado/Fabricio - | Jurado
Jurado/Fabricio - | Jurado
Jurado/Fabricio - | Jurado
Jurado/Fabricio - | Jurado
Jurado/Fabricio - | Jurado
Jurado/Fabricio - | Jurado
Jurado/Fabricio - | Jurado
Jurado/Fabricio - | Jurado
Jurado/Fabricio - | Jurado
Jurado/Fabricio - | Jurado
Jurado/Fabricio - | Jurado
Jurado/Fabricio - | Jurado
Jurado/Fabricio - | Jurado
Jurado/Fabricio - | Jurado
Allaire - | Prado
Prado/Madargia - | Prado
Prado/Madargia - | Prado
D. Allaire - | E. Smith
D. Allaire - | E. Smith
D. Allaire - | E. Smith
D. Allaire - | E. Smith
D. Allaire - | E. Smith
D. Allaire - | E. Smith